# Milestone M4 Runs Defects Jira

Table of Contents

# MILESTONE M4 — Test Runs, Defects & Jira Integration

Organization: Iksula Services Pvt Ltd
Milestone: M4 (Weeks 14–16)
Duration: 3 weeks | 2026-07-06 → 2026-07-26
Status: Specification Document (Locked Scope)
Version: 1.0
Authors: Agent Milestone (M4 Generator), reviewed against MILESTONE_REGISTRY.md

## TABLE OF CONTENTS

- Executive Summary

- What Was Delivered Before (M0–M3)

- M4 Scope (Locked)

- Technical Stack

- Definition of Ready (DoR) = M3 DoD

- Tasks (MS4-T001–T060)

- Week-Wise Breakdown

- Acceptance Criteria (MS4-AC001–AC045)

- API Contracts & Endpoints

- Database Changes

- Testing Strategy

- Feature Flags

- Risks & Mitigations

- Rollback Plan

- Deliverables Checklist

- Next Milestone Preview (M5)

## EXECUTIVE SUMMARY

Mission: Users execute test runs manually, capture evidence inline, log defects with AI-powered root-cause analysis (Agent A4), and sync defects bidirectionally with Jira. Run dashboards track progress in real-time.

Headline Scope:

- Test Runs: Create from test plan, assign tester, track execution (in-progress → pass/fail/blocked)

- Test Executions: One-per-test-case step-by-step executor page with evidence capture (screenshot paste, file upload to R2), actual-result entry

- Defect Lifecycle: New → Triaged → In Progress → Ready for QA → Verified → Closed (+ Reopened)

- Defect Detail Pop-Up: Tabs—Details | History | Linked Tests | AI RCA (5-layer analysis)

- Agent A4 (Defect Intelligence): LangGraph flow analyzing defect evidence → 5 root-cause layers (surface, component, data/state, dependency, root + preventive). Langfuse traced.

- Jira Bidirectional Sync: OAuth 2.0 3-legged, issue mapping (QA Nexus Defect ↔ Jira Issue), status transitions synced, comments + attachments synced via webhook + 2-min poll fallback

- Run Dashboard: Real-time active runs, pass/fail rates, blockers flagged

- Evidence Storage: R2 signed URLs, secure attachment download

Why This Matters: Defects are the currency of QA. Without frictionless logging + AI analysis + Jira sync, QA teams lose hours to manual triage. M4 closes that loop.

## CONTEXT / PREDECESSORS: WHAT WAS DELIVERED BEFORE (M0–M3)

This milestone sits in position M4 of the PM1 (MVP) phase, which runs M0–M6 (21 weeks total). Canonical predecessor order per MILESTONE_REGISTRY.md v3.2:

### M0: Setup & Infrastructure (Weeks 1–2)

- BetterAuth (email/password, session, password reset)

- 4-role RBAC (Admin, Lead, QA, Mgmt) with profile attributes (Jr/Sr/Automation)

- PostgreSQL 15 + pgvector on Oracle Always Free VM

- Vercel deployment + GitHub Actions CI/CD

- SigNoz, GlitchTip, Langfuse observability

- Doppler + GitHub Secrets for env management

### M1: Users & Roles (Weeks 3–4)

- 4-role RBAC fully enforced (Admin/Lead/QA/Stakeholder)

- Project CRUD (create, list, delete)

- Row-Level Security (RLS) enabled on all tables

- User profile attributes (Jr/Sr/Automation)

- User invitations and org management

### M2: Test Documents & Knowledge Base — Core Doc Catalog (12 templates) (Weeks 5–7)

- KB CRUD + approval workflow

- RAG pipeline (BGE embeddings + pgvector)

- 12 document templates (Strategy, Plan, RTM, Daily/Weekly/Sprint/Release reports, Defect Report, RCA, Charter, Regression)

- Document Intelligence Layer (A1 context-gathering)

- PDF export + versioning

### M3: Test Cases & AI Generation — Test Case Management (Weeks 8–10)

- Test case CRUD (TipTap editor, BDD + traditional modes)

- A1 Test Case Generator (LangGraph, Clarification Questions gate)

- A2 Dedup (live chips, semantic similarity scoring)

- RTM linking, tags, priority, stability sparklines

- Bulk import (CSV, TestRail, Zephyr, Xray, qTest)

- Test Case Management complete and core test case data model populated

M3 Handoff to M4:

- Test runs table populated (100+ runs across 3–5 projects)

- Defects table seeded (50+ defects with evidence attachments)

- Jira OAuth integration validated (token flow working)

- A4 RCA agent ready (trained on 50-defect corpus, Langfuse instrumented)

## M4 SCOPE (LOCKED)

### Feature 1: Complete Test Execution Flow (Weeks 1–2)

- Execution page redesign for manual testers: expanded step panel, evidence capture inline

- Evidence capture mechanisms: screenshot paste (Ctrl+V), file upload dialog, automatic snapshot on failure

- R2 integration: signed URLs for secure evidence access, TTL-based expiry (7 days)

- Actual-result entry: rich text field, reference screenshots, mark pass/fail/blocked

- Defect creation pop-up: triggered mid-execution, pre-filled with test context (run ID, case ID, step #, evidence refs)

### Feature 2: Defect Lifecycle & Detail Pop-Up (Weeks 1–2)

- Defect lifecycle states: New → Triaged → In Progress → Ready for QA → Verified → Closed (+ Reopened loop)

- Defect detail pop-up: modal with tabs:

  - Details: Title, description, category, severity, steps-to-reproduce, expected-vs-actual

  - History: State transitions, assignee changes, comments, timestamps

  - Linked Tests: List of test cases that surfaced this defect

  - AI RCA: Agent A4 output (5 layers, confidence per layer, root cause statement, preventive action)

- Defect assignments: Auto-assign based on component (from evidence analysis) or manual override

- Comments thread: @-mentions, markdown, linked defects

### Feature 3: Agent A4 — Defect Intelligence (Week 2–3)

- 5-Layer RCA Flow (LangGraph):

  - Layer 1 (Surface): Parse error message, stack trace, log lines → surface symptom

  - Layer 2 (Component): Map stack trace to architecture (backend/frontend/API/DB) → likely component

  - Layer 3 (Data/State): Analyze test data, environment variables, screenshots → data state anomaly

  - Layer 4 (Dependency): Correlate timing, external service failures, config drift → dependency failure

  - Layer 5 (Root + Preventive): Synthesize L1–L4 → root cause statement + actionable preventive steps

- Confidence scoring: Per-layer confidence (0.0–1.0), visual indicators (green=high, yellow=medium, red=low)

- Evidence analysis:

  - Extract text from screenshots (OCR if needed)

  - Parse HAR logs (response times, 4xx/5xx errors, headers)

  - Scan console logs for warnings/errors

  - Inspect env snapshot (browser version, test data ID, backend version)

- Async execution: RCA triggered on defect creation, populated into defect detail within 5–10 seconds

- Langfuse tracing: Full LangGraph execution logged (model inputs, outputs, latency, cost)

- Human feedback loop: Mark RCA layer as "Correct" / "Incorrect" → signal for continuous tuning

### Feature 4: Jira Bidirectional Sync (Week 3)

- OAuth 2.0 3-Legged Flow:

  - User clicks "Link to Jira" in settings

  - Redirects to Jira login → QA Nexus OAuth callback

  - Token stored (encrypted in DB), refresh token rotated on use

  - User selects Jira project, status mapping (QA Nexus → Jira field names)

- Issue Mapping:

  - QA Nexus Defect ID ↔ Jira Issue Key (stored in jira_links table)

  - One-to-one mapping; supports bulk re-mapping if Jira issue closed/merged

- Sync Events:

  - QA Nexus → Jira: Defect created/updated/transitioned → POST to Jira REST API v3 (issue create, issue update)

  - Jira → QA Nexus: Webhook (registered on OAuth callback) receives issue.updated events → update defect state in QA Nexus

  - Fallback: 2-min poll (if webhook delivery fails) queries Jira for linked issue status

- Synced Fields:

  - Status (with mapping: New→Open, Triaged→Open, In Progress→In Progress, Ready for QA→Ready for QA, Verified→Done, Closed→Closed)

  - Assignee (Jira assignee.email_address ↔ QA Nexus user.email)

  - Comments/descriptions (append "Synced from QA Nexus" or "Synced from Jira" footer)

  - Attachments (evidence screenshots, console logs uploaded as Jira issue attachments)

  - Custom fields (e.g., affected_version, environment, priority) if configured

- Webhook Processor: Hatchet consumer listening for Jira webhook events, parsing payload, updating defect via API

- Sync Audit Trail: jira_sync_logs table logs every sync event (timestamp, direction, payload hash, status)

### Feature 5: Run Dashboard (Week 2)

- Real-Time Metrics:

  - Active runs (count, list with project + assigned tester)

  - Pass rate (% of cases executed with PASS result)

  - Fail rate (% of cases executed with FAIL result)

  - Blocked count (cases blocked by blocker defect)

  - In-progress count (cases not yet executed in active runs)

- Charts:

  - Pass/fail/blocked trend line (last 7 days, auto-refresh every 30s)

  - Defect severity distribution (pie chart: Critical/High/Medium/Low)

- Run List:

  - Run name, test plan, assigned tester, execution %age, start time, estimated completion

  - Quick-action buttons: View Details, Download Evidence, Add Defect

- Live Updates: WebSocket or polling (30s interval) for real-time refresh

- Filtering: By project, by test plan, by tester, by status

## TECHNICAL STACK

| Component | Technology | Purpose | Notes |
| --- | --- | --- | --- |
| Async Job Queue | Hatchet | RCA job processing, Jira sync, evidence processing | 2 workers, 30s timeout for RCA |
| LLM for RCA | Ollama (Gemma 4) + Claude API fallback | Layer-by-layer RCA analysis | Langfuse traced; per-layer confidence scoring |
| File Storage | Cloudflare R2 | Evidence screenshots, logs, HAR files | Signed URLs, 7-day expiry |
| Jira REST API | Jira Cloud REST API v3 | Issue CRUD, status mapping, webhook registration | OAuth 2.0 3LO; token refresh |
| Webhooks | Hatchet consumer pattern | Jira issue.updated events → defect update | Retry logic; 2-min poll fallback if webhook fails |
| Event Tracing | Langfuse | A4 RCA execution, sync events, API calls | Public key-based sampling; 5% trace rate initially |
| Real-Time Updates | Server-Sent Events (SSE) or WebSocket | Run dashboard live refresh | Poll-based (30s) fallback if SSE unavailable |

## DEFINITION OF READY (DoR) = M3 DoD

M4 entry criteria (all of these must be complete before sprint planning):

- Test Run CRUD complete from M3 (create run, assign cases, manage environments)

- Execution UI functional from M3 (one-row-per-case, step detail, quick-status buttons)

- Auto-evidence capture working (screenshot, HAR, console logs, env snapshot)

- Defect CRUD from M3 (create from run, categorize, attachments)

- Jira OAuth 2.0 token flow working (3-legged, token refresh)

- Defect → Jira issue one-way creation validated

- Jira REST API v3 access tested (create, update, get issue calls)

- Webhook endpoint created (POST /webhooks/jira/issue-updated)

- R2 bucket configured with signed URL template

- Langfuse integration live (keys provisioned, trace sampling configured)

- Ollama Gemma 4 model warm + responsive (<5s inference for simple prompts)

- A4 RCA agent skeleton ready (prompt templates for L1–L5 defined)

- Test data: ≥50 defects seeded with evidence (screenshots, logs, HAR files)

- Database schema for jira_links, jira_webhook_events, jira_sync_logs created + indexed

## TASKS (MS4-T001–T060)

Estimation Methodology: T-shirt sizing (XS=2h, S=4h, M=8h, L=16h, XL=32h), 20% buffer applied to sprint capacity.

### Week 1: Execution UI + Evidence Capture

| Task ID | Title | Assignee | Type | Est. | Status | AC IDs |
| --- | --- | --- | --- | --- | --- | --- |
| MS4-T001 | Redesign execution page layout (step panel expansion) | Frontend | Story | M | TODO | AC001, AC002 |
| MS4-T002 | Implement screenshot paste handler (Ctrl+V → R2 upload) | Frontend | Feature | M | TODO | AC003 |
| MS4-T003 | Build file upload dialog (drag-drop, file picker) | Frontend | Feature | M | TODO | AC004 |
| MS4-T004 | Create R2 upload endpoint (multipart, signed URL generation) | Backend | Feature | M | TODO | AC005 |
| MS4-T005 | Implement R2 signed URL retrieval (TTL=7d expiry) | Backend | Feature | S | TODO | AC006 |
| MS4-T006 | Add evidence list to execution page (thumbnails + download links) | Frontend | Feature | S | TODO | AC007 |
| MS4-T007 | Build actual-result entry form (rich text, pass/fail/blocked buttons) | Frontend | Feature | M | TODO | AC008 |
| MS4-T008 | Create defect creation pop-up (pre-filled form, evidence ref) | Frontend | Feature | M | TODO | AC009 |
| MS4-T009 | Build POST /api/defects endpoint (from execution context) | Backend | Feature | M | TODO | AC010 |
| MS4-T010 | Implement execution state transitions (in-progress → pass/fail/blocked) | Backend | Feature | S | TODO | AC011 |
| MS4-T011 | Add execution history tab (timeline view) | Frontend | Feature | S | TODO | AC012 |
| MS4-T012 | Test execution UI end-to-end (Playwright) | QA | Test | M | TODO | AC013 |

Week 1 Subtotal: 14 tasks, ~112 hours (80h base + 20% buffer)

### Week 2: Defect Lifecycle + Detail Pop-Up + Run Dashboard

| Task ID | Title | Assignee | Type | Est. | Status | AC IDs |
| --- | --- | --- | --- | --- | --- | --- |
| MS4-T013 | Design defect detail pop-up layout (4 tabs) | Design | Story | S | TODO | AC014 |
| MS4-T014 | Build defect detail pop-up component (modal, tab nav) | Frontend | Feature | M | TODO | AC015 |
| MS4-T015 | Create Details tab (title, description, category, severity) | Frontend | Feature | M | TODO | AC016 |
| MS4-T016 | Create History tab (state transitions, assignee, comments) | Frontend | Feature | M | TODO | AC017 |
| MS4-T017 | Create Linked Tests tab (list of test cases) | Frontend | Feature | S | TODO | AC018 |
| MS4-T018 | Create AI RCA tab (layer display, confidence indicators) | Frontend | Feature | M | TODO | AC019 |
| MS4-T019 | Implement defect lifecycle state machine (6 states + transitions) | Backend | Feature | M | TODO | AC020 |
| MS4-T020 | Build defect update endpoint (PATCH /api/defects/{id}) | Backend | Feature | M | TODO | AC021 |
| MS4-T021 | Create comments thread UI (markdown, @-mentions) | Frontend | Feature | L | TODO | AC022 |
| MS4-T022 | Implement comments API (create, read, update) | Backend | Feature | M | TODO | AC023 |
| MS4-T023 | Add defect assignment logic (auto-assign by component) | Backend | Feature | M | TODO | AC024 |
| MS4-T024 | Build run dashboard page layout | Frontend | Feature | M | TODO | AC025 |
| MS4-T025 | Implement real-time metrics cards (active runs, pass/fail counts) | Frontend | Feature | M | TODO | AC026 |
| MS4-T026 | Create pass/fail/blocked trend chart (7-day history) | Frontend + Analytics | Feature | L | TODO | AC027 |
| MS4-T027 | Create defect severity pie chart | Frontend + Analytics | Feature | S | TODO | AC028 |
| MS4-T028 | Build run list with quick actions | Frontend | Feature | M | TODO | AC029 |
| MS4-T029 | Implement SSE subscription (30s poll fallback) for dashboard | Frontend | Feature | M | TODO | AC030 |
| MS4-T030 | Create dashboard filter controls (project, plan, tester, status) | Frontend | Feature | M | TODO | AC031 |
| MS4-T031 | Build GET /api/dashboards/runs (metrics + run list) | Backend | Feature | M | TODO | AC032 |
| MS4-T032 | Test run dashboard end-to-end | QA | Test | L | TODO | AC033 |

Week 2 Subtotal: 20 tasks, ~162 hours (130h base + 20% buffer)

### Week 3: Agent A4 + Jira Sync + Integration Testing

| Task ID | Title | Assignee | Type | Est. | Status | AC IDs |
| --- | --- | --- | --- | --- | --- | --- |
| MS4-T033 | Design A4 RCA LangGraph flow (5 layers) | AI/Eng | Design | M | TODO | AC034 |
| MS4-T034 | Implement Layer 1 prompt (surface symptom extraction) | AI | Feature | S | TODO | AC035 |
| MS4-T035 | Implement Layer 2 prompt (component classification) | AI | Feature | S | TODO | AC035 |
| MS4-T036 | Implement Layer 3 prompt (data/state analysis) | AI | Feature | S | TODO | AC035 |
| MS4-T037 | Implement Layer 4 prompt (dependency failure detection) | AI | Feature | S | TODO | AC035 |
| MS4-T038 | Implement Layer 5 prompt (root cause + preventive action) | AI | Feature | M | TODO | AC036 |
| MS4-T039 | Wire A4 agent to Hatchet (async RCA job) | Backend | Feature | M | TODO | AC037 |
| MS4-T040 | Add Langfuse tracing to RCA flow | Backend | Feature | S | TODO | AC038 |
| MS4-T041 | Implement RCA result storage (defect_rca table) | Backend | Feature | S | TODO | AC039 |
| MS4-T042 | Add confidence scoring to RCA output | AI | Feature | S | TODO | AC040 |
| MS4-T043 | Build RCA feedback mechanism (correct/incorrect buttons) | Frontend | Feature | S | TODO | AC041 |
| MS4-T044 | Implement Jira OAuth 2.0 3-legged flow (redirect + callback) | Backend | Feature | L | TODO | AC042 |
| MS4-T045 | Build Jira integration settings page (project + field mapping) | Frontend | Feature | M | TODO | AC043 |
| MS4-T046 | Create POST /api/jira/sync/defect (defect → Jira issue) | Backend | Feature | L | TODO | AC044 |
| MS4-T047 | Implement Jira webhook receiver (POST /webhooks/jira/issue-updated) | Backend | Feature | M | TODO | AC045 |
| MS4-T048 | Build Jira webhook → defect sync logic (status, assignee, comments) | Backend | Feature | L | TODO | AC046 |
| MS4-T049 | Create 2-min poll fallback (if webhook delivery fails) | Backend | Feature | M | TODO | AC047 |
| MS4-T050 | Implement jira_sync_logs table + audit trail | Backend | Feature | S | TODO | AC048 |
| MS4-T051 | Add sync error handling + retry logic | Backend | Feature | M | TODO | AC049 |
| MS4-T052 | Test Jira OAuth flow (mocked Jira sandbox) | QA | Test | M | TODO | AC050 |
| MS4-T053 | Test full defect-to-Jira sync (2-way) | QA | Test | L | TODO | AC051 |
| MS4-T054 | Test A4 RCA on golden defects (50-defect corpus) | AI/QA | Test | L | TODO | AC052 |
| MS4-T055 | Load test dashboard (10 concurrent users, 100 active runs) | QA | Test | L | TODO | AC053 |
| MS4-T056 | E2E test: plan → run → defect → Jira (Playwright) | QA | Test | XL | TODO | AC054 |
| MS4-T057 | Documentation: User guide (evidence, defect, RCA, Jira sync) | Tech Writer | Doc | M | TODO | AC055 |
| MS4-T058 | Documentation: API contract (endpoints, schemas, examples) | Tech Writer | Doc | M | TODO | AC056 |
| MS4-T059 | Documentation: Admin runbook (Jira mapping, webhook debugging) | Tech Writer | Doc | S | TODO | AC057 |
| MS4-T060 | Rollback plan validation (disable flags, manual defect creation) | DevOps | Test | S | TODO | AC058 |

Week 3 Subtotal: 28 tasks, ~224 hours (180h base + 20% buffer)

Total M4 Tasks: 62 tasks, ~498 hours (~100 story points, 6 eng FTE @ 80h/week = ~1 week buffer)

## WEEK-WISE BREAKDOWN

### Week 1 (2026-07-06 → 2026-07-12): Execution UI + Evidence Capture

Goal: Testers can execute steps, capture evidence inline, and pre-fill defect form.

Deliverables:

- Redesigned execution page (expanded step panel)

- Screenshot paste + file upload (→ R2)

- Evidence list with download links

- Actual-result form (pass/fail/blocked)

- Defect creation pop-up (pre-filled)

Key Milestones:

- Mon 7/08: R2 endpoint live, upload tested

- Wed 7/10: Execution UI with evidence capture in production

- Fri 7/11: Defect pop-up integrated, E2E tested

### Week 2 (2026-07-13 → 2026-07-19): Defect Lifecycle + Run Dashboard

Goal: Defect lifecycle states, detail pop-up, and real-time run dashboard operational.

Deliverables:

- Defect detail pop-up (4 tabs)

- Defect lifecycle state machine (6 states)

- Comments thread

- Run dashboard (metrics + charts)

- Dashboard live refresh (SSE + polling)

Key Milestones:

- Tue 7/15: Defect state machine + lifecycle complete

- Wed 7/16: Dashboard real-time metrics live

- Fri 7/19: Full dashboard in production

### Week 3 (2026-07-20 → 2026-07-26): Agent A4 + Jira Sync + E2E Testing

Goal: A4 RCA live, Jira bidirectional sync functional, E2E pipeline validated.

Deliverables:

- A4 RCA LangGraph flow (5 layers, confidence scoring)

- Jira OAuth 2.0 integration (token management)

- Jira issue creation + 2-way sync

- Webhook receiver + 2-min poll fallback

- Comprehensive E2E tests

Key Milestones:

- Mon 7/20: A4 RCA agent in production (async)

- Tue 7/21: Jira OAuth + webhook live

- Wed 7/22: 2-way sync validated

- Fri 7/26: E2E test suite passing, documentation complete

## ACCEPTANCE CRITERIA (MS4-AC001–AC045)

### Execution & Evidence (AC001–AC013)

| AC ID | Criterion | Type | Verification Method |
| --- | --- | --- | --- |
| AC001 | Execution page step panel expands to ≥50% viewport height | UI | Visual inspection + responsive test |
| AC002 | Tester can scroll through multiple steps without page reload | UI | Playwright navigation test |
| AC003 | Screenshot pasted (Ctrl+V) uploads to R2 within 3 seconds | Integration | Automated upload + verify R2 object exists |
| AC004 | File upload dialog accepts .png, .jpg, .zip, .txt, .log (max 50MB) | Validation | File type + size rejection test |
| AC005 | R2 upload endpoint returns signed URL with 7-day expiry | API | Verify URL decode + timestamp validation |
| AC006 | Signed URL accesses file without authentication (before expiry) | Security | HTTP GET without bearer token |
| AC007 | Evidence list displays thumbnails for images, file icons for logs | UI | Visual regression test |
| AC008 | Actual-result rich text editor supports bold, italic, code blocks | UI | TipTap editor feature test |
| AC009 | Defect pop-up pre-fills with run ID, case ID, step #, evidence refs | Data | Defect creation payload inspection |
| AC010 | POST /api/defects returns 201 with defect ID + initial state=New | API | Request/response schema validation |
| AC011 | Execution result persisted (PASS/FAIL/BLOCKED) in test_executions table | Data | DB query verification |
| AC012 | Execution history shows state transitions with timestamps | UI | Timeline rendering test |
| AC013 | E2E: Author → Create Run → Execute Step → Log Evidence → Create Defect (≤2 min) | E2E | Playwright scenario timing |

### Defect Lifecycle & Pop-Up (AC014–AC024)

| AC ID | Criterion | Type | Verification Method |
| --- | --- | --- | --- |
| AC014 | Defect detail pop-up renders 4 tabs (Details, History, Linked Tests, RCA) | UI | DOM inspection |
| AC015 | Pop-up modal is centered, dismissible via X or Esc key | UI | Visual + keyboard test |
| AC016 | Details tab displays title, description, category, severity, steps-to-reproduce | UI | Field rendering test |
| AC017 | History tab shows state transitions (date, old state, new state, actor) | UI | Data rendering test |
| AC018 | Linked Tests tab lists all test cases that produced this defect | Data | Query validation (defects ↔ test_executions join) |
| AC019 | RCA tab displays 5 layers with color-coded confidence (green/yellow/red) | UI | CSS class inspection |
| AC020 | Defect state transitions follow FSM: New → Triaged → In Progress → Ready for QA → Verified → Closed (+ Reopened) | Logic | State transition test (invalid transitions rejected) |
| AC021 | PATCH /api/defects/{id} updates state, assignee, category | API | Request/response validation |
| AC022 | Comments thread supports @-mentions, markdown, links | UI | Rich text rendering test |
| AC023 | Comments persisted to defect_comments table with user + timestamp | Data | DB query |
| AC024 | Auto-assignment logic assigns defect to component owner (if A4 identifies component) | Logic | RCA → component → owner mapping test |

### Run Dashboard (AC025–AC033)

| AC ID | Criterion | Type | Verification Method |
| --- | --- | --- | --- |
| AC025 | Dashboard displays active run count, pass rate, fail rate, blocked count | UI | Metrics card rendering |
| AC026 | Pass/fail/blocked trend chart shows 7-day history with ≥hourly granularity | Analytics | Chart data points validation |
| AC027 | Trend chart auto-refreshes every 30 seconds (SSE or polling) | Responsiveness | WebSocket/HTTP polling monitor |
| AC028 | Severity pie chart (Critical/High/Medium/Low) displays current open defects | Analytics | Pie slice calculation test |
| AC029 | Run list displays name, plan, tester, execution %, start time, estimated completion | UI | Table rendering |
| AC030 | Quick-action buttons (View Details, Download Evidence, Add Defect) functional | UI | Click handlers + routing |
| AC031 | Dashboard filter controls (project, plan, tester, status) apply to metrics + run list | Filtering | Filtered query validation |
| AC032 | GET /api/dashboards/runs returns metrics + run list in ≤500ms | Performance | Latency measurement |
| AC033 | E2E: View dashboard → apply filters → see updated metrics (≤2 min) | E2E | Playwright scenario |

### Agent A4 RCA (AC034–AC042)

| AC ID | Criterion | Type | Verification Method |
| --- | --- | --- | --- |
| AC034 | RCA LangGraph job completes within 10 seconds for defect with complete evidence | Performance | Langfuse trace latency |
| AC035 | RCA outputs text for all 5 layers (L1 surface, L2 component, L3 data/state, L4 dependency, L5 root) | Data | Output parsing test |
| AC036 | Layer 5 includes root cause statement + ≥2 actionable preventive steps | Content | Manual review of 10 RCAs |
| AC037 | RCA job queued immediately on defect creation, async notification on completion | Architecture | Hatchet job log + event trigger |
| AC038 | Langfuse trace captures model calls, input tokens, output tokens, latency per layer | Observability | Langfuse dashboard inspection |
| AC039 | RCA result stored in defect_rca table linked to defect ID | Data | DB query |
| AC040 | Per-layer confidence score (0.0–1.0) displayed with color gradient | UI | Confidence badge rendering |
| AC041 | User can mark RCA layer as "Correct" / "Incorrect" → signal logged for future retraining | Feedback | Button click + feedback table entry |
| AC042 | A4 achieves ≥75% top-layer accuracy on 50-defect golden corpus (human-verified) | Quality | Manual evaluation report |

### Jira Integration (AC043–AC051)

| AC ID | Criterion | Type | Verification Method |
| --- | --- | --- | --- |
| AC043 | OAuth 2.0 3-legged flow: user clicks "Link Jira" → redirected to Jira → token stored | Security | OAuth redirect capture + token table inspection |
| AC044 | Token refresh automatic (< 1 min before expiry) without user intervention | Architecture | Token refresh logs in jira_sync_logs |
| AC045 | Jira integration settings page allows project selection + status field mapping | UI | Settings form rendering + save |
| AC046 | POST /api/jira/sync/defect creates issue in Jira + records jira_links mapping | Integration | Jira API call logged; jira_links table inspected |
| AC047 | Webhook receives issue.updated event → updates defect state within 2 seconds | Real-time | Webhook delivery log + defect state change timestamp |
| AC048 | Sync fails gracefully: if webhook fails, 2-min poll queries Jira for status | Reliability | Webhook failure simulation + poll validation |
| AC049 | Sync audit trail (jira_sync_logs) records every sync event with direction, payload hash, status | Audit | Table query |
| AC050 | Defect status mapping (New→Open, Verified→Done, etc.) validated on mocked Jira | Integration | Mock Jira test API responses |
| AC051 | E2E: Create defect in QA Nexus → see issue in Jira → update in Jira → defect updates in QA Nexus (≤2 min round-trip) | E2E | Playwright scenario with Jira sandbox |

### Documentation & Runbooks (AC052–AC058)

| AC ID | Criterion | Type | Verification Method |
| --- | --- | --- | --- |
| AC052 | User guide covers evidence capture, defect lifecycle, RCA interpretation, Jira sync with screenshots | Documentation | Peer review |
| AC053 | API contract documents all endpoints (request, response, error codes, examples) | API Docs | API spec (OpenAPI 3.0) validation |
| AC054 | Admin runbook includes Jira OAuth setup, status mapping, webhook debugging, rollback steps | Operations | Runbook completeness review |
| AC055 | Rollback plan validated: disable feature flags → manual defect creation remains available | Deployment | Smoke test with flags disabled |
| AC056 | No P0 bugs remain open at M4 DoD | Quality | Bug tracking system query |
| AC057 | No untracked AI agent invocations (100% logged to Langfuse with user/action/timestamp) | Compliance | Audit log verification |
| AC058 | Jira sync latency p95 < 5 seconds (issue create), webhook delivery SLA 99% within 2 min | Performance | APM + webhook logs |

## API CONTRACTS & ENDPOINTS

### Runs & Executions

POST /api/test-runs
Content-Type: application/json

{
  "project_id": "proj_123",
  "test_plan_id": "plan_456",
  "name": "Smoke Test Run 2026-07-15",
  "assigned_tester_id": "user_789",
  "test_case_ids": ["case_001", "case_002"]
}

Response: 201 Created
{
  "run_id": "run_789",
  "status": "IN_PROGRESS",
  "created_at": "2026-07-15T10:30:00Z"
}

GET /api/test-runs/{run_id}/executions
Response: 200 OK
{
  "executions": [
    {
      "execution_id": "exec_001",
      "test_case_id": "case_001",
      "status": "PASSED",
      "result": "...",
      "actual_result": "...",
      "evidence_ids": ["evid_001", "evid_002"],
      "started_at": "2026-07-15T10:35:00Z",
      "ended_at": "2026-07-15T10:40:00Z"
    }
  ]
}

PATCH /api/test-executions/{execution_id}
Content-Type: application/json

{
  "status": "PASSED",
  "actual_result": "Feature rendered correctly on all browsers",
  "evidence_ids": ["evid_001"]
}

Response: 200 OK

### Evidence Storage

POST /api/evidence/upload
Content-Type: multipart/form-data

[file binary]

Response: 201 Created
{
  "evidence_id": "evid_001",
  "filename": "screenshot_2026-07-15_103500.png",
  "signed_url": "https://r2-bucket.example.com/evidence/evid_001?token=xyz&expires=2026-07-22",
  "expires_at": "2026-07-22T10:35:00Z"
}

GET /api/evidence/{evidence_id}
Response: 200 OK
{
  "evidence_id": "evid_001",
  "filename": "screenshot.png",
  "mime_type": "image/png",
  "size_bytes": 245621,
  "signed_url": "https://r2-bucket.example.com/..."
}

### Defects

POST /api/defects
Content-Type: application/json

{
  "project_id": "proj_123",
  "run_id": "run_789",
  "execution_id": "exec_001",
  "title": "Login button unresponsive on mobile",
  "description": "...",
  "category": "UI Bug",
  "severity": "HIGH",
  "steps_to_reproduce": "1. Open app on iPhone 14\n2. Click login button",
  "evidence_ids": ["evid_001", "evid_002"]
}

Response: 201 Created
{
  "defect_id": "defect_123",
  "status": "NEW",
  "created_at": "2026-07-15T10:45:00Z"
}

GET /api/defects/{defect_id}
Response: 200 OK
{
  "defect_id": "defect_123",
  "title": "...",
  "status": "TRIAGED",
  "assignee_id": "user_456",
  "linked_test_cases": ["case_001", "case_002"],
  "comments": [...],
  "rca": {
    "layer_1": { "text": "...", "confidence": 0.95 },
    "layer_2": { "text": "...", "confidence": 0.87 },
    ...
    "layer_5": { "text": "Root cause: CSS media query not triggered on viewport < 375px. Preventive: Add unit test for mobile breakpoints." }
  }
}

PATCH /api/defects/{defect_id}
Content-Type: application/json

{
  "status": "IN_PROGRESS",
  "assignee_id": "user_456"
}

Response: 200 OK

### Jira Sync

POST /api/jira/oauth/authorize
Response: 302 Found
Location: https://auth.atlassian.com/authorize?...

POST /api/jira/oauth/callback
Query: code=xyz, state=abc

Response: 302 Found
Location: /settings/integrations/jira?status=linked

(Token stored in jira_integrations table, encrypted)

POST /api/jira/sync/defect/{defect_id}
Content-Type: application/json

{
  "project_key": "PROJ"
}

Response: 200 OK
{
  "jira_issue_key": "PROJ-456",
  "jira_issue_id": "10001",
  "synced_at": "2026-07-15T10:50:00Z"
}

### Webhooks

POST /webhooks/jira/issue-updated
Content-Type: application/json
Authorization: Bearer webhook_token_xyz

{
  "issue": {
    "key": "PROJ-456",
    "id": "10001",
    "fields": {
      "status": { "name": "In Progress" },
      "assignee": { "email_address": "alice@example.com" }
    }
  }
}

Response: 200 OK
{ "status": "processed" }

### Dashboards

GET /api/dashboards/runs?project_id=proj_123&limit=10
Response: 200 OK
{
  "metrics": {
    "active_runs": 3,
    "total_cases_executed": 45,
    "pass_count": 38,
    "fail_count": 5,
    "blocked_count": 2,
    "pass_rate": 0.84
  },
  "runs": [
    {
      "run_id": "run_789",
      "name": "Smoke Test 2026-07-15",
      "plan_name": "...",
      "tester_name": "Alice",
      "execution_percent": 100,
      "started_at": "2026-07-15T10:30:00Z",
      "estimated_completion": "2026-07-15T13:00:00Z"
    }
  ],
  "trend": [
    { "timestamp": "2026-07-15T10:00:00Z", "pass_rate": 0.82, "fail_rate": 0.12, "blocked_rate": 0.06 },
    ...
  ]
}

## DATABASE CHANGES

### New Tables

test_runs (M3, enhanced)

ALTER TABLE test_runs ADD COLUMN
  started_at TIMESTAMP,
  completed_at TIMESTAMP,
  status VARCHAR (20) DEFAULT 'IN_PROGRESS'; -- IN_PROGRESS, COMPLETED, PAUSED

test_executions (M3, enhanced)

ALTER TABLE test_executions ADD COLUMNS
  actual_result TEXT,
  evidence_ids JSON, -- array of evidence IDs
  blocked_reason TEXT;

evidence (NEW, M4)

CREATE TABLE evidence (
  evidence_id UUID PRIMARY KEY,
  project_id UUID NOT NULL,
  execution_id UUID REFERENCES test_executions(execution_id),
  defect_id UUID REFERENCES defects(defect_id),
  filename VARCHAR(255),
  mime_type VARCHAR(50),
  size_bytes INT,
  r2_path VARCHAR(500),
  signed_url_expires_at TIMESTAMP,
  created_by UUID REFERENCES users(user_id),
  created_at TIMESTAMP DEFAULT NOW(),
  INDEX (project_id), INDEX (execution_id), INDEX (defect_id)
);

defects (M3, enhanced with state machine)

ALTER TABLE defects ADD COLUMNS
  state VARCHAR(20) DEFAULT 'NEW', -- NEW, TRIAGED, IN_PROGRESS, READY_FOR_QA, VERIFIED, CLOSED, REOPENED
  assignee_id UUID REFERENCES users(user_id),
  component VARCHAR(100), -- from A4 Layer 2
  verified_at TIMESTAMP,
  closed_at TIMESTAMP;

defect_history (M3, enhanced)

CREATE TABLE defect_history (
  history_id UUID PRIMARY KEY,
  defect_id UUID REFERENCES defects(defect_id),
  old_state VARCHAR(20),
  new_state VARCHAR(20),
  actor_id UUID REFERENCES users(user_id),
  comment TEXT,
  timestamp TIMESTAMP DEFAULT NOW(),
  INDEX (defect_id)
);

defect_comments (NEW, M4)

CREATE TABLE defect_comments (
  comment_id UUID PRIMARY KEY,
  defect_id UUID REFERENCES defects(defect_id),
  author_id UUID REFERENCES users(user_id),
  content TEXT, -- markdown
  mentions JSON, -- array of user IDs @-mentioned
  created_at TIMESTAMP DEFAULT NOW(),
  updated_at TIMESTAMP,
  INDEX (defect_id), INDEX (author_id)
);

defect_rca (NEW, M4)

CREATE TABLE defect_rca (
  rca_id UUID PRIMARY KEY,
  defect_id UUID REFERENCES defects(defect_id) UNIQUE,
  layer_1 TEXT, -- surface symptom
  layer_1_confidence FLOAT,
  layer_2 TEXT, -- component
  layer_2_confidence FLOAT,
  layer_3 TEXT, -- data/state
  layer_3_confidence FLOAT,
  layer_4 TEXT, -- dependency
  layer_4_confidence FLOAT,
  layer_5 TEXT, -- root cause + preventive
  layer_5_confidence FLOAT,
  generated_at TIMESTAMP DEFAULT NOW(),
  langfuse_trace_id VARCHAR(200),
  feedback JSON, -- { "layer_1": "correct" | "incorrect", ... }
  INDEX (defect_id)
);

jira_links (M3, enhanced)

CREATE TABLE jira_links (
  link_id UUID PRIMARY KEY,
  project_id UUID REFERENCES projects(project_id),
  defect_id UUID REFERENCES defects(defect_id),
  jira_issue_id VARCHAR(20), -- e.g., PROJ-456
  jira_issue_key VARCHAR(50),
  synced_at TIMESTAMP,
  sync_direction VARCHAR(20), -- NEXUS_TO_JIRA, JIRA_TO_NEXUS, BIDIRECTIONAL
  INDEX (project_id), INDEX (defect_id), UNIQUE (defect_id, jira_issue_id)
);

jira_integrations (M3, enhanced)

ALTER TABLE jira_integrations ADD COLUMNS
  oauth_token TEXT, -- encrypted
  oauth_token_expires_at TIMESTAMP,
  oauth_refresh_token TEXT, -- encrypted
  jira_project_key VARCHAR(20),
  status_mapping JSON, -- { "NEW": "Open", "VERIFIED": "Done", ... }
  last_sync_at TIMESTAMP;

jira_webhook_events (NEW, M4)

CREATE TABLE jira_webhook_events (
  event_id UUID PRIMARY KEY,
  project_id UUID REFERENCES projects(project_id),
  webhook_id VARCHAR(100),
  jira_issue_key VARCHAR(50),
  event_type VARCHAR(50), -- issue.updated, issue.created, etc.
  payload JSON,
  processed BOOLEAN DEFAULT FALSE,
  processed_at TIMESTAMP,
  result TEXT, -- success or error detail
  created_at TIMESTAMP DEFAULT NOW(),
  INDEX (project_id), INDEX (processed)
);

jira_sync_logs (NEW, M4)

CREATE TABLE jira_sync_logs (
  log_id UUID PRIMARY KEY,
  project_id UUID REFERENCES projects(project_id),
  defect_id UUID REFERENCES defects(defect_id),
  jira_issue_key VARCHAR(50),
  direction VARCHAR(20), -- NEXUS_TO_JIRA, JIRA_TO_NEXUS
  action VARCHAR(50), -- create, update_status, update_assignee, sync_comment, etc.
  payload_hash VARCHAR(64),
  http_status_code INT,
  response_body TEXT,
  latency_ms INT,
  success BOOLEAN,
  error_message TEXT,
  retried BOOLEAN DEFAULT FALSE,
  created_at TIMESTAMP DEFAULT NOW(),
  INDEX (project_id), INDEX (defect_id), INDEX (created_at)
);

## TESTING STRATEGY

### Unit Tests (Agile: TDD-driven)

- Defect state machine (invalid transitions rejected)

- RCA layer confidence scoring (edge cases: missing evidence)

- R2 signed URL generation + expiry validation

- Jira status mapping logic

- Comment markdown parsing

### Integration Tests

- Evidence upload → R2 → signed URL retrieval → HTTP GET (full flow)

- Defect creation → RCA job queued → result stored (async flow)

- Jira OAuth token exchange → token stored + refresh

- Jira webhook delivery → defect state updated

- 2-min poll fallback (webhook failure simulation)

### E2E Tests (Playwright)

- Execution Flow: Author → Create Run → Execute Step → Capture Evidence → Create Defect → View RCA

- Jira Sync: Create Defect in QA Nexus → Verify Issue in Jira → Update Status in Jira → Verify Update in QA Nexus

- Dashboard: View Run Dashboard → Apply Filters → Verify Metrics Update (Real-Time)

- RCA Feedback: View Defect RCA → Mark Layer as Incorrect → Verify Feedback Logged

### Performance Testing

- Dashboard latency (GET /api/dashboards/runs): p95 < 500ms for 100 active runs

- RCA job latency (L1–L5): p95 < 10s (with Ollama + Claude fallback)

- Jira issue creation latency: p95 < 5s (API + webhook registration)

- Evidence upload latency: p95 < 3s for 10MB file

### Golden Defects Corpus (M4)

- Curated 50 real defects from Iksula projects

- Each defect labeled with ground-truth root cause (Layer 5)

- A4 RCA evaluated: Layer 1–5 accuracy measured

- Human QA engineer reviews RCA output for top 50 defects

- Target: ≥75% Layer 5 accuracy

### Mocked Jira Sandbox

- Mock Jira REST API (responses + webhook events) using MSW

- OAuth token exchange mocked

- Test issue creation, status transition, comment sync

- No live Jira tenant required for CI/CD

## FEATURE FLAGS

| Flag Name | Feature | Default (M4) | Rollout Strategy | Kill Switch | Owner |
| --- | --- | --- | --- | --- | --- |
| ff_jira_2way_sync | Jira bidirectional sync (create, update, comment, attachments) | OFF | Dark (Day 1) → Internal (Day 2) → Canary 5% (Day 3) → GA | Sync error rate > 5% for 5+ min; revert to one-way | Backend Lead |
| ff_a4_rca_enabled | Agent A4 5-layer RCA analysis on defect creation | OFF | Dark (Day 2) → Internal (Day 3) → Canary 5% (Day 4) → GA | RCA false-root-cause rate > 40% OR latency > 20s | AI Eng Lead |
| ff_auto_evidence_capture | Automatic screenshot/HAR/console capture on failure | OFF | Dark (Day 1) → Internal (Day 2) → GA | Storage errors > 2% or latency > 5s | Frontend Lead |
| ff_webhook_receiver | Jira webhook processor (real-time sync vs. 2-min poll fallback) | OFF | Dark (Day 2) → Internal (Day 3) → GA | Webhook delivery failures > 10% for 5+ min | Backend Lead |

Rollout Process:

- New feature ships with flag disabled

- Day 1–2: Internal rollout (Iksula team + 1–2 pilot projects)

- Evaluation: Latency, errors, data consistency metrics

- If pass: Canary 5–10%, then graduated to GA (100%)

- If fail: Debug + fix, or Rollback (disable flag)

## RISKS & MITIGATIONS

### MS4-R001: Jira OAuth Token Expiry Handling

Risk: Token expires mid-sync, causing Jira API calls to fail silently.

Probability: Medium | Impact: High (sync loop breaks, data drift)

Mitigation:

- Automatic token refresh <1 min before expiry (cron job)

- Jira API error 401 → immediately refresh token

- jira_sync_logs logs all token refresh events

- Alert if 3+ consecutive token refresh failures

Owner: Backend (OAuth service)

### MS4-R002: Webhook Duplication & Idempotency

Risk: Jira webhook delivered twice → defect state updated twice → inconsistent history.

Probability: Medium | Impact: Medium (audit trail dirty, confusing to users)

Mitigation:

- Webhook deduplication: hash(event_id, timestamp, payload) → check jira_webhook_events before processing

- Idempotent defect updates: PATCH /api/defects treats same state transition as no-op

- Store webhook_id in jira_webhook_events for Jira webhook acknowledgment

Owner: Backend (webhook processor)

### MS4-R003: A4 False Root Causes Eroding Trust

Risk: RCA suggests incorrect root cause → engineer wastes time debugging wrong area → loses confidence in AI.

Probability: Medium | Impact: High (feature unusable, user churn)

Mitigation:

- Golden corpus evaluation: measure L5 accuracy before GA rollout (target ≥75%)

- Confidence scoring per-layer: low-confidence layers flagged as "needs human review"

- Feedback loop: user marks RCA as "Incorrect" → logged for retraining

- Langfuse traces all RCA invocations → weekly audit of top 20 outputs

- Fallback: if confidence < 50%, suppress RCA and show "Insufficient evidence" message

Owner: AI (A4 agent), QA (golden corpus evaluation)

### MS4-R004: R2 Signed URL Leak

Risk: Signed URL in error message / database log → attacker uses URL to access evidence.

Probability: Low | Impact: High (evidence exposure, privacy breach)

Mitigation:

- TTL validation: signed URLs expire within 7 days (minimal exposure window)

- Don't log full URLs: truncate after ? in logs (log only path, not token)

- Restricted R2 bucket policy: disallow public read, require signed URLs

- Daily rotation of R2 signing keys

Owner: DevOps (R2 bucket policy), Backend (URL handling)

### MS4-R005: Evidence Upload Large-File Timeout

Risk: User uploads 100MB HAR file → upload times out → evidence lost.

Probability: Low | Impact: Medium (manual re-capture needed)

Mitigation:

- Chunk-based upload: split files >50MB into 5MB chunks

- Resume capability: incomplete uploads can resume from last chunk

- Timeout: 5 min per chunk (adjustable)

- UI feedback: upload progress bar + ETA

Owner: Frontend (chunk upload), Backend (chunk assembly)

### MS4-R006: Jira Project Status Schema Drift

Risk: Customer reconfigures Jira status workflow → QA Nexus doesn't know the new status names → sync fails.

Probability: Medium | Impact: Medium (manual status mapping needed, 1-2 hour recovery)

Mitigation:

- Integration health widget: shows "Jira schema detected" vs. "Unknown status names"

- Manual mapping UI: admin can re-map statuses on settings page

- Fetch Jira project schema on OAuth callback (refresh annually)

- Webhook delivery monitoring: if status sync fails >3×, alert admin

Owner: Backend (schema validation), Frontend (mapping UI)

### MS4-R007: 2-Min Poll Fallback Overwhelms Jira API

Risk: 100 active defects, each polling Jira every 2 min = 50 API calls/min = quota exceeded.

Probability: Low | Impact: Medium (API quota exceeded, rate-limit errors)

Mitigation:

- Smart polling: only poll if webhook hasn't delivered in 5+ min

- Batch polling: fetch all linked issues in 1 API call (list issues by updated timestamp)

- Jira API quota monitoring: alert if usage > 80% of daily limit

- Backoff: if rate-limited, exponential backoff (max 10 min between polls)

Owner: Backend (polling scheduler)

## ROLLBACK PLAN

Rollback Trigger: Any of the following conditions met for >5 minutes:

- Jira sync error rate > 5% (100+ consecutive failures)

- A4 RCA latency p95 > 20s (agent hanging)

- A4 false-root-cause rate > 40% (detected in real-time via user "Incorrect" feedback)

- R2 signed URL leak detected (security incident)

- Dashboard latency p95 > 2s (infrastructure issue)

- Evidence upload failures > 10%

Rollback Procedure (Target RTO: <10 min):

- Kill Hatchet workers (A4 + Jira sync jobs stop)

- kubectl scale deployment hatchet-worker --replicas=0

- Disable feature flags (in Unleash):

- unleash disable jira.bidirectional_sync
unleash disable ai.a4_rca_enabled
unleash disable runs.live_dashboard

- Revert code (if needed):

- git revert SHA_OF_COMMIT
npm run build && npm run deploy

- Verify fallback behavior:

  - Defect creation still works (local state machine)

  - Manual Jira integration (copy/paste issue key)

  - Dashboard shows static 15-min-old metrics

  - RCA tab shows "Analysis unavailable"

- Notify stakeholders (Slack to #qa-nexus-incidents)

- ROLLBACK: Jira sync disabled (error rate 8%). Manual Jira linking available. ETA to fix: 2h.

- Post-Incident Review (within 24 hours)

  - Root cause analysis

  - Code fix + testing

  - Re-enable feature flag gradually (Canary 1% → GA)

Data Loss: None. All defects remain in QA Nexus. Jira sync queues cleared; resume after fix.

## DELIVERABLES CHECKLIST

### Code & Documentation

- ☐ Execution UI component (React, TypeScript)

- ☐ Evidence upload service (R2 integration)

- ☐ Defect lifecycle state machine

- ☐ Defect detail modal (4 tabs)

- ☐ Run dashboard component + API

- ☐ A4 RCA LangGraph flow (5 layers)

- ☐ Jira OAuth 2.0 handler + token refresh

- ☐ Jira webhook receiver (Hatchet consumer)

- ☐ 2-min poll fallback scheduler

- ☐ User guide + screenshots

- ☐ API contract (OpenAPI 3.0 spec)

- ☐ Admin runbook (Jira setup, webhook debugging)

### Artifacts

- ☐ Milestone_M4_Runs_Defects_Jira.md (this document)

- ☐ Milestone_M4_Runs_Defects_Jira.docx (Word export)

- ☐ Milestone_M4_workflow.drawio (LucidChart + draw.io XML)

- ☐ milestone_M4_charts/gantt.png (task timeline)

- ☐ milestone_M4_charts/risk_heatmap.png (risk matrix)

- ☐ milestone_M4_charts/defect_lifecycle.png (state diagram)

- ☐ milestone_M4_charts/jira_sync_events.png (event flow)

### Test Coverage

- ☐ Unit tests (defect state machine, RCA confidence, R2 URL)

- ☐ Integration tests (execution → defect → RCA → Jira)

- ☐ E2E Playwright tests (full user flow: plan → run → defect → sync)

- ☐ Performance tests (dashboard <500ms, RCA <10s)

- ☐ Golden corpus evaluation (50 defects, ≥75% accuracy)

- ☐ Mocked Jira sandbox (OAuth, sync, webhook)

### Deployment

- ☐ Feature flags configured in Unleash

- ☐ Hatchet workers deployed (2 replicas, autoscaling)

- ☐ Database migrations applied (new tables, indexes)

- ☐ R2 bucket created + signed URL template

- ☐ Langfuse integration validated (keys provisioned, sampling configured)

- ☐ Jira OAuth app credentials registered

## NEXT MILESTONE PREVIEW (M5)

M5 Scope (2026-07-27 → 2026-08-16, 3 weeks):

### Not in M4 scope; deferred to M5:

NOTE: Reporting deliverables (Daily, Weekly reports, simple dashboards) are owned by M5. Full reports (Sprint, Release, ROI) are owned by M6. M4 delivers only in-run execution visibility and defect triage.

- Reporting & Dashboards: Templated reports (Daily, Weekly, Sprint, Release), Exec Dashboard (pass rate, defect density, ROI), ROI calculator

- Advanced Features: Command-K omnibox, global search indexing, audit log dashboard

- Accessibility & Polish: WCAG 2.2 AA audit + fixes, performance optimization (p95 latencies), E2E load testing

- Pilot Launch: Onboarding materials, pilot intake, success metrics tracking

### Why M5?

- M4 delivers the core loop: execute → log → analyze → sync

- M5 adds business intelligence (reports, ROI) + accessibility (WCAG) + pilot readiness

- Clear dependency chain: M4 data → M5 reporting

## GLOSSARY

| Term | Definition |
| --- | --- |
| Agent A4 | 5-layer RCA engine; analyzes defect evidence to identify root cause |
| Evidence | Artifact captured during test execution (screenshot, log, HAR file, env snapshot) |
| Jira OAuth 2.0 3-Legged | Standard OAuth flow where user authenticates with Jira, grants QA Nexus access |
| R2 | Cloudflare's S3-compatible object storage; used for evidence files |
| Signed URL | Time-limited HTTP URL with embedded authentication token; no bearer token needed |
| Webhook | HTTP POST callback registered with Jira; triggered when issue updated |
| Langfuse | Open-source LLM tracing tool; logs model calls, tokens, latency, cost |
| Hatchet | Task queue / job processor; handles async RCA + Jira sync jobs |
| Defect Lifecycle | State machine: New → Triaged → In Progress → Ready for QA → Verified → Closed (+ Reopened) |
| RCA | Root Cause Analysis; 5-layer drill-down to identify underlying problem |
| TTL | Time-to-Live; expiry window for signed URLs (7 days in M4) |

Document Owner: Iksula Services QA Nexus Team
Last Updated: 2026-04-21
Status: Ready for Milestone Planning & Sprint Execution