# Milestone M5 Automation Basic Reports MVP Launch

Table of Contents

# MILESTONE M5: AUTOMATION + BASIC REPORTS + MVP LAUNCH

Organization: Iksula Services Pvt Ltd
Milestone: M5 (Weeks 16–18 of 18-week MVP)
Version: 1.0 (Final)
Date Created: 2026-04-21
Status Badge: On Track → MVP Launch Gate
Duration: 3 weeks (2026-07-27 → 2026-08-16)

## EXECUTIVE SUMMARY

M5 closes the MVP: Playwright automation runner ships with async job execution (Hatchet workers), R2 artifact storage, AI-assisted step generation (gated), flake detection (5-run strategy), and basic reports (3 KPI dashboards + trend charts). Pilot onboarding, MVP readiness checklist, and go/no-go gate lock on 2026-08-16. Two to three internal Iksula projects launch live.

Mission: Ship automation infrastructure + foundational reporting to enable pilots to log defects and track quality trends without manual assembly.

Key Deliverables:

- Playwright runner (headed/headless, isolated Hatchet workers, R2 uploads)

- Scheduled & on-demand runs via Hatchet cron + API

- AI step generation (LangGraph variant; ai.auto_playwright flag)

- Flake detection (5-run confidence, 20–80% pass rate threshold)

- Basic reports (3 dashboards: run summary, defect summary, 30-day trend)

- MVP launch checklist + pilot onboarding docs

- Zero P0 bugs, <3 P1, observability green for 7 days

## CONTEXT: WHAT WAS DELIVERED BEFORE

M0–M4 Summary: Authentication (4-role RBAC, BetterAuth), project workspace (CRUD, Jira key config), knowledge base + 12 document templates (A1 context-aware generation), test case authoring (TipTap editor, A2 dedup, RTM linking), test execution (manual runs, auto-evidence capture: screenshot + HAR + console logs + env snapshot), defects (A4 5-layer RCA, 4-category classification), Jira 2-way sync (OAuth 2.0, webhook + 2-min poll), reports framework (Daily/Weekly/Sprint/Release templates, auto-population, PDF export).

Deployment State:

- Vercel (frontend) + Oracle VM (backend: NestJS, FastAPI, Ollama Gemma 4, PostgreSQL, Redis, Neo4j)

- Cloudflare R2 operational (evidence storage)

- Langfuse + SigNoz + GlitchTip active (observability)

- Feature flags (Unleash): A1/A2/A4/Jira sync disabled by default; M5 enables basic reports + command-K

Available Databases:

- test_runs, test_results, evidence_files (M3)

- defects, defect_categories (M3)

- reports, report_templates (M4)

- automation_suites placeholder ready (M0 schema)

## TECH STACK (M5 SCOPE)

| Component | Version | Purpose | Status | Milestone |
| --- | --- | --- | --- | --- |
| Playwright | 1.48+ | Browser automation runner (headed/headless, cross-browser) | Configured | M5 |
| Hatchet (Postgres backend) | 0.33+ | Async job queue for automation + reports | Running (M1+) | M5 (new worker pool) |
| Cloudflare R2 | Live | Evidence storage + artifact blobs (video, trace, screenshots) | Operational (M3+) | M5 |
| LangGraph | 0.2.15+ | Agent orchestration variant for step generation | Ready (M1+) | M5 |
| PostgreSQL 15 | 15.x | Automation run schema + flake signals + materialized views | Live (M0+) | M5 |
| Redis 7 | 7.x | Flake detection cache (5-run window) | Live (M0+) | M5 |
| Ollama Gemma 4 | 2026-04 | LLM for AI step generation (fallback: Gemini 2.5 Flash) | Live (M1+) | M5 |
| recharts | 2.12+ | Frontend charts for basic reports (React components) | Ready (M4+) | M5 |
| Unleash | 5.3+ | Feature flags (automation.playwright_runner, ai.auto_playwright, reports.basic_v1) | Live (M0+) | M5 |

## DEFINITION OF READY (DoR)

Prerequisites Ensuring Viable Kickoff:

- Test execution data seeded (≥100 test runs with results, ≥500 results across 3 pilot projects)

- Defect data mature (≥100 defects with evidence, RCA complete, Jira sync proven)

- Report templates tested (Daily, Weekly, Sprint queries validated on staging DB)

- Hatchet infrastructure confirmed (job queue responsive, retry logic tested)

- Playwright environment setup (headed + headless modes working in Docker on Oracle VM)

- Pilot projects identified + contacts confirmed (2–3 Iksula internal projects ready to onboard week 1)

- Performance baselines captured (doc gen p95 <60s, RCA p95 <10s, API p95 <300ms)

- Feature flag infrastructure operational (Unleash SDKs deployed, flag registry synchronized)

- Observability dashboards prepared (SigNoz + GlitchTip dashboards created for M5 metrics)

- Load test plan finalized (synthetic user scenarios, VU count, ramp-up strategy)

## MILESTONE ENTRY CRITERIA

- M4 DoD fully satisfied (reports + ROI dashboard live, all tests green)

- Playwright + Hatchet integration tested in dev (simple test case → Hatchet job → R2 artifact)

- Pilot onboarding docs drafted (checklist, success metrics, support channel setup)

- Feature flag rollout strategy documented (automation.playwright_runner dark launch → internal canary → GA)

- MVP readiness gate criteria published (P0/P1 thresholds, observability SLOs, pilot engagement targets)

- Test data pipeline operational (factories for generating automation runs, flake scenarios)

## TASK BREAKDOWN (WEEK-WISE)

### WEEK 1: AUTOMATION RUNNER INFRA (2026-07-27 → 2026-08-02)

W1 Goal: Playwright runner core + Hatchet job execution + R2 artifact upload fully functional.

#### MS5-T001: Playwright Test Runner Skeleton

Description: Build headless Playwright runner that accepts a test spec (JSON or hand-written .test.ts), executes steps, captures screenshots + HAR + console logs at each step, and saves artifacts to R2.

Details:

- Implement runner class: PlaywrightRunner (TypeScript, in NestJS service or FastAPI sidecar)

- Accept test spec format: {name, steps: [{action, selector, value?, screenshot?}]}

- Browser launch modes: headed (for dev) + headless (for CI/Hatchet)

- Screenshot capture at each step + on failure

- HAR file generation (via browser.context.recordHAR())

- Console log capture (via page.on('console'))

- Environment snapshot (OS, browser version, viewport size, network speed simulation)

- R2 upload wrapper: uploadArtifact(runId, artifactType, blob) → R2 URL

- Error handling: step failure stops run, returns error context

Priority: P0
Estimate: 20 hours
Owner: Backend Engineer (Automation)
Dependencies: M3 test_results schema, M3 evidence_files schema, R2 creds in Doppler
US-ID: US-008
TB/EP: TB-006, EP-039

#### MS5-T002: Hatchet Job Definition + Worker Pool

Description: Create Hatchet workflow for automation runs: enqueue → allocate worker → execute runner → upload artifacts → mark result.

Details:

- Hatchet workflow YAML: automation-run.yaml

  - Trigger: API call (/api/automation/runs/enqueue) or cron (scheduled)

  - Step 1: Allocate worker from pool (max 3 concurrent, based on pilot count)

  - Step 2: Execute PlaywrightRunner (pass test spec + run context)

  - Step 3: Upload artifacts to R2 (retry 3x on transient failure)

  - Step 4: Update test_results with pass/fail + artifact URLs

  - Step 5: Emit event to UI (WebSocket or polling via API)

- Worker image: Docker container with Chromium (via Playwright) + Node.js

- Max concurrency: 3 per Oracle VM (1 per core, CPU throttle at 80%)

- Retry: exponential backoff (1s, 2s, 4s, 8s) up to 3 attempts

- Timeout: 5 min per run (hardcoded, no override per job)

Priority: P0
Estimate: 16 hours
Owner: DevOps + Backend
Dependencies: Hatchet running (M0+), Cloudflare R2, Docker registry
US-ID: US-008
TB/EP: None (Hatchet job, not exposed as endpoint yet)

#### MS5-T003: Test Run Execution API (Create Run, Enqueue, Poll Status)

Description: NestJS endpoints for test automation: create run, link test cases, enqueue, poll status, fetch results.

Details:

- POST /api/automation/runs — create new automation run (project, env, test cases)

- POST /api/automation/runs/:id/enqueue — enqueue to Hatchet (return jobId)

- GET /api/automation/runs/:id/status — poll status (queued, running, done) + progress

- GET /api/automation/runs/:id/results — fetch all test results + artifact URLs

- GET /api/automation/artifacts/:artifactId — redirect to R2 signed URL (screenshot, HAR, logs)

- Request validation: ensure test cases exist, env valid, user has project access (RBAC)

- Response: JSON with run metadata, results array, artifact links

- Pagination: results per 25, sortable by status/duration

Priority: P0
Estimate: 14 hours
Owner: Backend Engineer (API)
Dependencies: MS5-T001, MS5-T002, Project Service (RBAC guard)
US-ID: US-008
TB/EP: EP-035 (new), EP-036 (new), EP-037 (modified)

#### MS5-T004: R2 Upload & Artifact Lifecycle Management

Description: Cloudflare R2 integration for evidence storage with lifecycle policies.

Details:

- R2 bucket structure: qaix-artifacts/{projectId}/{runId}/{artifactType}-{timestamp}.{ext}

- Artifact types: screenshot, har, console-log, env-snapshot, video (optional)

- Upload flow:

  - Multipart upload for files >100MB (videos)

  - Server-side signed URL generation (1-hour expiry)

  - Retry on transient failure (503, 429)

  - Metadata: Content-Type, Cache-Control: public, max-age=31536000 (1 year)

- Lifecycle policy: Auto-delete artifacts >90 days old (configurable per project)

- Quota tracking: Warn at 80% bucket utilization, enforce soft quota

- Fallback: If R2 fails, store as base64 blob in Postgres (temp, ≤100 MB)

Priority: P0
Estimate: 12 hours
Owner: DevOps
Dependencies: R2 API keys in Doppler, Postgres evidence_files schema
US-ID: US-008
TB/EP: EP-039 (modified)

#### MS5-T005: Web-Based Test Spec Editor / Playwright Codegen Integration

Description: UI for creating test specs (both hand-written and AI-generated). Reuse Playwright Codegen for recording.

Details:

- Manual authoring:

  - TipTap block editor: test-step block type (action + selector + value + screenshot toggle)

  - Block types: navigate, click, fill, screenshot, wait, assertion

  - Drag-reorder steps, delete, clone

  - Auto-save to automation_suites.spec_json

- Codegen mode:

  - Launch browser recorder (Playwright Inspector) in new window

  - Record user actions (clicks, fills, navigations)

  - Auto-insert screenshot at each step

  - Import generated code into editor

- Validation:

  - Check selector syntax (CSS + XPath)

  - Dry-run on dev browser (small form)

  - Show error if selector not found

Priority: P1
Estimate: 18 hours
Owner: Frontend Engineer
Dependencies: MS5-T001, TipTap editor, Playwright Inspector
US-ID: US-008
TB/EP: EP-030 (modified for automation)

### WEEK 2: FLAKE DETECTION + BASIC REPORTS (2026-08-03 → 2026-08-09)

W2 Goal: Flake detection live + 3 basic report dashboards shipped + AI step generation gated behind flag.

#### MS5-T006: Flake Detection Algorithm (5-Run Strategy)

Description: Classify tests as "flaky" if they pass/fail inconsistently. Run same test 5 times on failure; compute pass rate over last 10 runs; flag if 20–80%.

Details:

- Trigger: When test fails during automation run

  - Automatically enqueue 5 re-runs of same test (sequential, isolated browser)

  - Collect pass count, fail count

  - Compute current pass rate: passCount / 5

  - Query flake_signals table for same test (last 10 runs)

  - Compute historical pass rate (sliding window, 10-run average)

  - Classification:

    - If historical pass rate 20–80%: FLAKY (emit warning badge in UI)

    - If ≤20%: BROKEN (not flaky, consistently fails)

    - If ≥80%: STABLE (not flaky, consistently passes or random outlier)

- Flake signals table:

- CREATE TABLE flake_signals (
  id UUID PRIMARY KEY,
  automation_run_id UUID,
  test_case_id UUID,
  pass_rate_5run DECIMAL(3,2),
  pass_rate_10run_historical DECIMAL(3,2),
  classification TEXT ('FLAKY', 'STABLE', 'BROKEN'),
  rerun_count INT,
  first_detected_at TIMESTAMP,
  last_confirmed_at TIMESTAMP,
  created_at TIMESTAMP
);

- Caching: Redis cache flake_signals per test (key: flake:{testId}:{projectId}, TTL 24h)

- Confidence: Show badge only if ≥2 recent occurrences (at least 2 re-run rounds)

- UI Display: Flake badge (amber) with tooltip "Flaky: 60% pass rate (6/10 recent runs)"

Priority: P0
Estimate: 16 hours
Owner: Backend Engineer (Analytics)
Dependencies: MS5-T001 (test execution data), Redis, PostgreSQL flake_signals table
US-ID: US-008
TB/EP: TB-006 (new flake_signals), EP-037 (modified with flake status)

#### MS5-T007: Materialized Views for Report KPIs

Description: Pre-compute report metrics via PostgreSQL materialized views, refreshed hourly.

Details:

- View 1: run_summary_metrics (for KPI card: total runs, pass rate, avg duration)

- SELECT
  project_id,
  COUNT(*) as total_runs,
  ROUND(100.0 * COUNT(CASE WHEN status = 'pass' THEN 1 END) / COUNT(*), 2) as pass_rate_pct,
  ROUND(AVG(EXTRACT(EPOCH FROM (ended_at - started_at))), 0) as avg_duration_sec,
  MAX(updated_at) as last_run_at
FROM test_runs
WHERE updated_at >= NOW() - INTERVAL '30 days'
GROUP BY project_id;

- View 2: defect_summary_metrics (for KPI card: open count by severity, MTTR, reopens)

- SELECT
  project_id,
  COUNT(CASE WHEN status = 'open' AND severity = 'critical' THEN 1 END) as open_critical,
  COUNT(CASE WHEN status = 'open' AND severity = 'major' THEN 1 END) as open_major,
  COUNT(CASE WHEN status = 'open' AND severity = 'minor' THEN 1 END) as open_minor,
  ROUND(AVG(EXTRACT(EPOCH FROM (resolved_at - created_at))), 0)::INT as mttr_sec,
  COUNT(CASE WHEN reopen_count > 0 THEN 1 END) as reopen_count
FROM defects
WHERE created_at >= NOW() - INTERVAL '30 days'
GROUP BY project_id;

- View 3: pass_fail_trend (for 30-day stacked area chart)

- SELECT
  DATE_TRUNC('day', test_runs.created_at)::DATE as date,
  COUNT(CASE WHEN status = 'pass' THEN 1 END) as passed,
  COUNT(CASE WHEN status = 'fail' THEN 1 END) as failed,
  COUNT(*) as total
FROM test_runs
WHERE created_at >= NOW() - INTERVAL '30 days'
GROUP BY date
ORDER BY date;

- Refresh strategy:

  - Hatchet cron job: refresh-reports-views runs hourly at XX:00

  - Command: REFRESH MATERIALIZED VIEW CONCURRENTLY run_summary_metrics;

  - Concurrency prevents locks; safe for live queries

- Index:

  - Create index on (project_id) for quick lookups

Priority: P0
Estimate: 12 hours
Owner: Backend Engineer (DB)
Dependencies: Test execution + defect data seeded, PostgreSQL
US-ID: US-009, US-010
TB/EP: TB-006 (views only, not table)

#### MS5-T008: Basic Reports Backend (3 Dashboards: Run Summary, Defect Summary, Trend)

Description: NestJS endpoints that query materialized views + compute KPI cards.

Details:

- Endpoint 1: GET /api/reports/dashboards/automation-summary

  - Query: run_summary_metrics for project

  - Response:

  - {
  "projectId": "...",
  "period": "last_30_days",
  "cards": [
    {"label": "Total Runs", "value": 250, "trend": "+15%", "metadata": {...}},
    {"label": "Pass Rate", "value": "87%", "trend": "-2%", "metadata": {...}},
    {"label": "Avg Duration", "value": "45s", "trend": "stable", "metadata": {...}}
  ],
  "lastUpdated": "2026-08-16T14:30:00Z"
}

- Endpoint 2: GET /api/reports/dashboards/defect-summary

  - Query: defect_summary_metrics for project

  - Response:

  - {
  "projectId": "...",
  "period": "last_30_days",
  "cards": [
    {"label": "Open by Severity", "value": {critical: 3, major: 12, minor: 45}, "trend": "-1 critical"},
    {"label": "Mean Time to Close", "value": "3.2d", "trend": "-0.5d"},
    {"label": "Reopens", "value": 7, "trend": "-2"}
  ],
  "lastUpdated": "2026-08-16T14:30:00Z"
}

- Endpoint 3: GET /api/reports/dashboards/trend-30d?projectId=...

  - Query: pass_fail_trend for project, last 30 days

  - Response: Array of daily data for recharts stacked area chart

  - {
  "data": [
    {"date": "2026-07-17", "passed": 150, "failed": 20, "total": 170},
    {"date": "2026-07-18", "passed": 155, "failed": 18, "total": 173},
    ...
  ],
  "summary": {"avgPassRate": 0.887, "trend": "improving"}
}

- RBAC: User must have Lead or Admin role + project access

- Caching: Redis cache results, TTL 1 hour (refreshes with materialized view)

- Error handling: Return empty cards with "No data available" if project has <5 runs

Priority: P0
Estimate: 14 hours
Owner: Backend Engineer (API)
Dependencies: MS5-T007 (materialized views), Project Service (RBAC)
US-ID: US-009, US-010
TB/EP: EP-053 (new automation dashboard), EP-054 (modified)

#### MS5-T009: Basic Reports Frontend (React Components: KPI Cards, Trend Chart)

Description: Next.js pages + React components for 3 dashboards using recharts for visualization.

Details:

- Page 1: Automation Summary Dashboard (/reports/automation-summary)

  - 3 KPI cards (horizontal layout, light card bg)

  - Each card: label + primary value + trend badge (up/down/stable arrow)

  - Refresh button (top-right) + auto-refresh toggle (every 5 min)

  - Loading skeleton while fetching

  - Error state: "Failed to load. Retry?"

- Page 2: Defect Summary Dashboard (/reports/defect-summary)

  - Mirrors automation summary: 3 cards

  - Card 1: severity breakdown (open critical/major/minor as mini bars or text)

  - Card 2: MTTR (days.hours format)

  - Card 3: reopen count + trend

- Page 3: 30-Day Pass/Fail Trend (/reports/trend)

  - recharts AreaChart component

  - X-axis: dates (last 30 days)

  - Y-axis: count (0 to max)

  - Stacked area: passed (green), failed (red)

  - Tooltip on hover: date + counts

  - Legend (top): Passed, Failed

  - Responsive: full width, 300px min height

  - Export as image (Save As PNG)

- Navigation:

  - Left sidebar: Reports menu

  - Breadcrumb: Home > Reports > [Automation/Defect/Trend]

  - Tab navigation: "Automation | Defect | Trend"

- Accessibility:

  - WCAG 2.2 AA: colour + icon for card trends

  - Keyboard shortcut: ⌘R to refresh current dashboard

  - Alt text for chart images

Priority: P0
Estimate: 18 hours
Owner: Frontend Engineer
Dependencies: MS5-T008 (backend endpoints), recharts, DESIGN.md
US-ID: US-009, US-010
TB/EP: EP-053, EP-054

#### MS5-T010: AI-Assisted Playwright Step Generation (LangGraph Variant, Gated Flag)

Description: Extend LangGraph agent (reuse A1 context gen) to emit test.step calls instead of doc sections. Gate behind ai.auto_playwright flag (dark launch, disabled by default).

Details:

- Input: Natural-language test scenario (e.g., "User logs in with valid credentials")

- LangGraph graph variant: GeneratePlaywrightSteps (fork of A1 doc gen)

  - Node 1: Clarification Questions (same gate as A1) — user confirms scenario scope

  - Node 2: Fetch similar past tests (A2 semantic search) — provide context

  - Node 3: LLM generates Playwright steps — output format:

  - {
  "steps": [
    {"action": "navigate", "url": "https://app.example.com/login", "screenshot": true},
    {"action": "fill", "selector": "input[name='email']", "value": "user@example.com", "screenshot": false},
    {"action": "fill", "selector": "input[name='password']", "value": "password", "screenshot": false},
    {"action": "click", "selector": "button[type='submit']", "screenshot": true},
    {"action": "wait", "selector": "text=Dashboard", "timeout": 5000, "screenshot": true},
    {"action": "assertion", "type": "text", "selector": ".greeting", "expected": "Hello User"}
  ]
}

  - Node 4: Human-in-the-loop approval (user reviews, edits, saves)

- Feature flag: ai.auto_playwright

  - Default: false (disabled)

  - Rollout: Dark → Internal Iksula (week 2) → Canary 10% (week 3) → GA (week 3)

  - Kill switch: unleash disable ai.auto_playwright

- Integration:

  - Endpoint: POST /api/automation/generate-steps (async via Hatchet)

  - Accepts natural-language description + optional context (app URL, past test IDs)

  - Returns: job ID for polling

  - Result: Array of steps (JSON) ready to save as test spec

- Confidence scoring:

  - LLM outputs confidence: 0.0–1.0 per step

  - Show warning if <0.6 ("This step might fail; please review")

  - Auto-approve only if all steps ≥0.8

- Fallback: If Ollama offline, redirect to Gemini 2.5 Flash (free tier)

Priority: P1 (gated, dark launch)
Estimate: 16 hours
Owner: AI Engineer + Backend
Dependencies: LangGraph (M1+), Ollama/Gemini fallback, Hatchet, Feature flags (Unleash)
US-ID: US-011 (partial, automation variant)
TB/EP: None (new endpoint, not in ERD yet)

#### MS5-T011: Basic Reports Feature Flag Integration

Description: Gate basic reports behind reports.basic_v1 flag for safe canary rollout.

Details:

- Flag config (Unleash):

  - Name: reports.basic_v1

  - Default: false (disabled)

  - Strategy 1: Dark launch (internal flag, enable for test)

  - Strategy 2: Canary 20% (week 2, Thursday) — enable for 1 pilot project

  - Strategy 3: GA (week 3, Monday) — enable for all projects

  - Kill switch: unleash disable reports.basic_v1

- Frontend flag check:

  - In report pages, check flag at load time

  - If disabled: show "Coming soon" placeholder

  - If enabled: show dashboards (normal flow)

  - Use Unleash SDK (React context provider)

- Backend flag check:

  - NestJS guard on report endpoints: @UseGuards(FeatureFlagGuard) with reports.basic_v1

  - If disabled: return 410 Gone + message "Reports not yet available"

- Monitoring:

  - SigNoz dashboard: flag enable/disable events, latency per flag state

  - Alert if flag disabled unexpectedly (possible rollback)

Priority: P1
Estimate: 6 hours
Owner: Backend + Frontend
Dependencies: Unleash SDK integration (M0+), MS5-T008/T009
US-ID: US-009, US-010
TB/EP: None (feature flag, not endpoint)

### WEEK 3: MVP LAUNCH CHECKLIST + HARDENING (2026-08-10 → 2026-08-16)

W3 Goal: Zero P0 bugs, <3 P1 open, observability green 7 days, go/no-go gate passed, 2–3 pilots launched.

#### MS5-T012: MVP Readiness Checklist + Go/No-Go Review

Description: Formalize MVP launch gate criteria; conduct final go/no-go review with team + leadership.

Details:

- Acceptance Criteria Matrix (Launch Gate):

  - Defect Quality: 0 open P0 bugs, <3 open P1 bugs (all P2 acceptable), <10 open P3

  - Observability: SigNoz/GlitchTip dashboards green (no error rate >2%, p95 latency <target for all critical paths) for 7 consecutive days before launch

  - Feature Completeness: All 20 sections of M5 task breakdown complete (code merged, tests green)

  - Performance: p95 API latency <300ms, p95 doc gen <60s, p95 RCA <10s, p95 search <500ms

  - Test Coverage: Unit tests ≥80% (code), integration tests ≥70% (critical paths), E2E Playwright tests passing (3 journeys: auth → test case → defect → report)

  - Accessibility: WCAG 2.2 AA audit complete, <5 unfixed failures (all critical fixed)

  - Documentation: Release notes drafted, user guide updated, API docs in OpenAPI, admin runbook published

  - Pilot Readiness: 2–3 Iksula projects recruited, kick-off scheduled, success metrics defined (engagement, defect flow, adoption)

  - On-Call Readiness: Runbook for P0–P2 scenarios ready, escalation path defined, on-call roster assigned

  - Backup/Restore: Point-in-time recovery tested (restore from R2 snapshot, verify data integrity)

- Review Meeting: Friday, 2026-08-22, 2–3 PM (1 hour)

  - Attendees: Engineering Lead, PM, QA Lead, DevOps

  - Go/No-Go decision: All 8 criteria must be "Go" (no Conditional Go)

  - If No-Go: Identify blockers, reassess launch date (push to next week or descope feature)

  - Record decision + signatures in Jira ticket

Priority: P0
Estimate: 10 hours
Owner: PM + Tech Lead
Dependencies: All M5 tasks complete
US-ID: N/A (meta task)
TB/EP: N/A

#### MS5-T013: Pilot Onboarding Program (Training + Kickoff)

Description: Create pilot onboarding docs + conduct live training sessions with 2–3 Iksula teams.

Details:

- Deliverables:

  - Pilot Onboarding Checklist (1-page)

    - Pre-kickoff: VPN access, project setup, user invites

    - Day 1: 30-min intro call (features, success metrics, support channel)

    - Week 1: 1-hour hands-on training (test case creation, defect logging, report viewing)

    - Week 2–4: Weekly 15-min check-ins + async support (Slack channel)

  - User Guide (5–10 pages)

    - "Getting Started" walkthrough (create project, add team, author test)

    - "Common Tasks" (log defect, view report, generate test plan)

    - Keyboard shortcuts (⌘K, ⌘Enter, ⌘⇧D)

    - FAQ + troubleshooting

  - Admin Guide (for Iksula IT ops)

    - User provisioning (bulk CSV import)

    - RBAC setup (assign roles per project)

    - Jira integration troubleshooting

    - Backup/restore procedures

  - Success Metrics Dashboard (live in QA Nexus admin panel)

    - Per-pilot metrics: login frequency, test cases created, defects logged, reports viewed

    - Cohort metrics: engagement (% active 4+ days/week), adoption (% defects flowing QA Nexus → Jira)

    - Real-time telemetry (last 24h activity)

- Training Sessions:

  - Session 1 (Mon, 2026-08-17, 10:00 AM): Pilot A (5 QAs) — 1 hour live + recorded

  - Session 2 (Wed, 2026-08-19, 10:00 AM): Pilot B + C (8 QAs) — 1 hour live + recorded

  - Format: Screen share, live demo, Q&A, recording uploaded to KB

- Support Channel:

  - Slack channel: #qa-nexus-pilots

  - Responders: AI Engineer + QA Lead (on-call during pilot week 1–4)

  - SLA: <2h response time for issues blocking work

Priority: P0
Estimate: 20 hours
Owner: PM + QA Lead + Technical Writer
Dependencies: Pilot projects confirmed
US-ID: GM-001 (adoption metric)
TB/EP: N/A

#### MS5-T014: Performance Optimization & Load Testing

Description: Identify and fix performance bottlenecks; validate system can handle 3 concurrent pilots (10 simultaneous users).

Details:

- Performance Profiling:

  - Use SigNoz APM to identify slow endpoints (p95 >300ms)

  - Profile Ollama inference (Gemma 4 step generation) — target <5s per step batch

  - Profile DB query slowness (materialized views, report queries) — target <200ms

  - Profile search latency (pgvector similarity search) — target <500ms

- Optimizations (if needed):

  - Add Redis caching layer to frequently queried endpoints

  - Optimize DB indexes (if not already done in earlier milestones)

  - Add connection pooling to Postgres (PgBouncer on Oracle VM)

  - Batch Ollama inference requests (queue up 10 requests, run in single model invocation)

  - Implement pagination for large result sets (avoid loading full dataset into memory)

- Load Testing:

  - Tool: k6 (lightweight, scriptable)

  - Scenario: 10 concurrent VUs (virtual users) for 5 min

  - Actions per VU: login, create test case, run automation, view report (repeat 5×)

  - Success criteria:

    - p95 latency <500ms (should be <300ms, but 500ms acceptable for load test)

    - Error rate <2%

    - No server crashes, no database connection exhaustion

  - Run 3× (baseline, with cache layer, with DB index optimization)

  - Report: Before/after latency histogram + error rate

- Monitoring during test:

  - SigNoz dashboard: CPU, memory, disk I/O, error rate, latency percentiles

  - Alert if any metric exceeds threshold (e.g., CPU >80%, error rate >2%)

Priority: P0
Estimate: 16 hours
Owner: DevOps + Backend
Dependencies: All features complete, production-like test data seeded
US-ID: GM-014 (performance SLO)
TB/EP: None (infrastructure, not endpoint)

#### MS5-T015: Backup / Restore Testing (End-to-End)

Description: Validate that point-in-time recovery from R2 snapshot works and restores all data correctly.

Details:

- Backup Procedure (existing, validate):

  - Daily Hatchet cron job: pg_dump qaix_prod > /tmp/qaix-$(date +%Y%m%d).sql.gz

  - Upload to R2: s3cmd put /tmp/qaix-$(date +%Y%m%d).sql.gz s3://iksula-backups/qaix-prod/

  - Retention: keep last 30 daily backups

  - Verify: log success/failure to SigNoz

- Restore Test:

  - On staging DB: stop services, drop current data

  - Download latest backup from R2

  - Restore: psql -f /tmp/qaix-latest.sql

  - Verify data integrity:

    - Row counts match (sample 10 tables)

    - Foreign key constraints pass

    - No orphaned records

  - Restart services, verify connectivity

  - Check UI: load homepage, view project data

  - Document time-to-restore (target: <4h including RTO)

- Documentation:

  - Update admin runbook with restore procedure

  - Add troubleshooting section (e.g., "restore hangs" → increase work_mem)

Priority: P0
Estimate: 8 hours
Owner: DevOps
Dependencies: R2 backup automation (M0+), PostgreSQL
US-ID: None (infrastructure)
TB/EP: None

#### MS5-T016: WCAG 2.2 AA Accessibility Audit + Remediation

Description: Conduct automated + manual accessibility audit; fix critical/major failures.

Details:

- Automated Audit Tools:

  - axe DevTools (Chrome plugin): run on all 25+ screens, report violations

  - Lighthouse (Chrome DevTools): Accessibility tab, review score

  - Expected: ≥90% Lighthouse accessibility score

- Manual Audit (by QA):

  - Keyboard navigation: Can all interactive elements be reached via Tab? Focus visible?

  - Colour contrast: All text ≥4.5:1 (WCAG AA)?

  - Form labels: All inputs have associated labels?

  - Images: All images have alt text (or aria-hidden if decorative)?

  - Screen reader (NVDA on Windows, VoiceOver on Mac): Spot-check 5 critical flows (auth, test case, defect, report)

- Issue Categories:

  - Critical: Error states not announced, required field not marked, colour-only status indication

  - Major: Form label missing, focus trap, low contrast (<4.5:1)

  - Minor: Missing alt text on non-critical image, suboptimal keyboard order

- Remediation:

  - Fix all critical issues (zero tolerance)

  - Fix ≥80% of major issues (acceptable if minor <3)

  - Document deferred issues in GitHub (backlog for v1.5)

- Accessibility Conformance Report:

  - VPAT (Voluntary Product Accessibility Template) 2.2

  - Claim WCAG 2.2 AA conformance for critical paths (auth, test case, defect, report)

  - Store in Google Drive for compliance audit

Priority: P0
Estimate: 14 hours
Owner: Frontend Engineer + QA Lead
Dependencies: M5 frontend tasks complete
US-ID: GM-012 (product quality — a11y is part of quality gate)
TB/EP: None (design + frontend QA, not endpoint)

#### MS5-T017: E2E Tests (Playwright Self-Test via Playwright Runner)

Description: Write 3 critical Playwright journeys; execute via Playwright runner to validate runner itself.

Details:

- Journey 1: Authentication Flow

  - Navigate to login page

  - Fill email + password

  - Click "Login"

  - Assertion: redirected to Project Picker, greeting shows user name

  - Artifacts captured: screenshot per step, HAR file, console logs

- Journey 2: Test Case Creation (A1 Generator)

  - Log in, select project

  - Click "New Test Case"

  - Fill title + description

  - Click "A1 Generate Steps"

  - Assertion: steps populated in editor, confidence badges visible

  - Click "Save"

  - Assertion: case visible in list

- Journey 3: Defect Creation from Run + Jira Push

  - Create test run, execute 1 case, fail intentionally

  - Click "Log Defect" button

  - Assertion: form pre-filled with run context

  - Fill severity + notes

  - Click "Push to Jira"

  - Assertion: defect created, Jira link shown

  - Poll Jira API: verify issue exists in target project

- Execution:

  - Tests authored in TipTap editor (MS5-T005)

  - Enqueue via runner API (MS5-T003)

  - Collect artifacts from R2

  - Results: pass/fail + artifacts in test_results table

  - CI Gate: Tests run on every merge to main, block merge if any fail

- Reporting:

  - Dashboards: E2E test status card in admin panel

  - Alert: if E2E tests fail >2h before launch, escalate to Tech Lead

Priority: P0
Estimate: 14 hours
Owner: QA Engineer + Automation
Dependencies: MS5-T001 (runner), MS5-T005 (test editor), MS5-T003 (API)
US-ID: N/A (test infrastructure)
TB/EP: None

#### MS5-T018: Flake Detection Validation (Synthetic Test Generator)

Description: Create synthetic test scenarios that are intentionally flaky (50% pass rate) to validate flake detection algorithm.

Details:

- Synthetic Test Suite:

  - Create 5 test specs with controlled flakiness:

    - Test A: 100% pass (baseline)

    - Test B: 50% pass (sleep 1–5s, randomize success)

    - Test C: 80% pass (fail if time-of-day in [1–2 AM UTC])

    - Test D: 20% pass (broken selector, fixed mid-test)

    - Test E: 100% fail (assertion fails always)

  - Enqueue 10 runs of each (total 50 runs)

- Validation:

  - Test A: Should classify as STABLE (0% flake rate)

  - Test B: Should classify as FLAKY (50% pass rate in 20–80% range)

  - Test C: Should classify as FLAKY (80% is edge, but still flaky)

  - Test D: Should classify as BROKEN or IMPROVING (depends on when fixed)

  - Test E: Should classify as BROKEN (0% pass rate)

- Flake signals table: Verify records created + confidence computed

- UI: Verify flaky badges appear correctly on dashboard + test case detail page

Priority: P1
Estimate: 10 hours
Owner: QA Engineer
Dependencies: MS5-T001 (runner), MS5-T006 (flake detection)
US-ID: N/A (test infrastructure)
TB/EP: None

#### MS5-T019: On-Call Runbook Authoring (P0–P2 Scenarios)

Description: Document step-by-step playbooks for incident response. Target scenarios: Ollama offline, pgvector full, Oracle VM disk full, Hatchet job queue backlog.

Details:

- Runbook Format (per scenario):

  - Symptom: What does on-call see in monitoring?

  - Impact: Which users/features affected?

  - Root cause: Most likely culprit

  - Investigation steps: How to confirm

  - Resolution: Step-by-step fix

  - Escalation: Who to contact if not resolved in X min

  - Post-incident: Log in Jira, alert PM/leadership

- Scenarios:

  - Ollama Offline (P0)

    - Symptom: Document generation fails ("LLM unavailable")

    - Investigation: ssh oracle-vm; curl -s http://localhost:11434/api/tags

    - Fix: systemctl restart ollama OR failover to Gemini 2.5 Flash (set flag)

    - Escalation: If restart fails, page infrastructure on-call

  - pgvector Index Full (P1)

    - Symptom: Search latency spikes (>5s), insert errors ("pgvector index full")

    - Investigation: SELECT count(*) FROM pgvector_entries; (should be <5M)

    - Fix: Archive old vectors (move to cold storage), or scale to Qdrant

    - Escalation: Plan scale-out in next sprint

  - Oracle VM Disk 95%+ Full (P0)

    - Symptom: Postgres inserts fail, log rotation fails

    - Investigation: df -h / ; du -sh /var/lib/postgresql/*

    - Fix: Delete old logs, purge R2 artifact cache, extend block storage

    - Escalation: Infrastructure on-call

  - Hatchet Job Queue Backlog >1000 Jobs (P1)

    - Symptom: Automation runs queued >30 min, users see "Queued" status

    - Investigation: hatchet job list --status queued | wc -l

    - Fix: Increase worker concurrency (add new worker pool), or pause non-urgent jobs

    - Escalation: If >2h, notify pilots + descope non-critical features

- Distribution:

  - Runbook pinned in Slack #oncall channel

  - Printed + taped to monitor (physical backup)

  - Annual review + update (Q1 each year)

Priority: P0
Estimate: 10 hours
Owner: DevOps + Backend Lead
Dependencies: M0–M5 infrastructure complete
US-ID: None (operations)
TB/EP: None

#### MS5-T020: Feature Flag Rollout Execution (Dark → Internal → Canary → GA)

Description: Gradually enable automation + reports + AI step gen via feature flags over week 3, monitored for issues.

Details:

- Timeline:

| - Date | - Feature | - Status | - Scope | - SLO |
| --- | --- | --- | --- | --- |
| - Mon 2026-08-17 | - automation.playwright_runner | - Dark | - Internal test only | - — |
| - Tue 2026-08-18 | - reports.basic_v1 | - Dark | - Internal test only | - — |
| - Wed 2026-08-19 | - ai.auto_playwright | - Dark | - Internal test only | - — |
| - Wed 2026-08-19 (PM) | - automation.playwright_runner | - Canary 10% | - Pilot A (1/3 pilots) | - <2% error rate |
| - Thu 2026-08-20 | - reports.basic_v1 | - Canary 20% | - Pilot A + B (2/3 pilots) | - p95 latency <500ms |
| - Fri 2026-08-21 | - All flags | - Canary 50% | - All pilots | - All SLOs met |
| - Sat 2026-08-22 | - All flags | - GA | - All projects | - All SLOs met, 0 P0 bugs |

- Monitoring per stage:

  - Error rate (target <2%)

  - Latency (target p95 <500ms for reports, <5s for automation)

  - User feedback (Slack #qa-nexus-pilots, watch for complaints)

  - Jira tickets (auto-filed errors in QA Nexus project)

- Rollback trigger: If any SLO breached for >10 min, disable flag + investigate

- Communication: Post updates to #qa-nexus-pilots daily during rollout

Priority: P0
Estimate: 6 hours (mostly monitoring, not coding)
Owner: PM + DevOps
Dependencies: All flags wired + SigNoz dashboards ready
US-ID: None (ops)
TB/EP: None

#### MS5-T021: Release Notes Drafting

Description: User-facing narrative of MVP features + getting started guide.

Details:

- Content (2–3 pages):

  - Headline: "QA Nexus MVP Launches: Playwright Automation + AI-Powered Reports"

  - What's New (3 sections):

    - Playwright Automation Runner — Run tests in browser, capture evidence auto, detect flaky tests

    - Basic Reports Dashboards — 3 KPI cards + 30-day trend chart, auto-refreshing

    - AI-Assisted Test Generation — Write tests from natural language (beta, opt-in)

  - Getting Started (Quick Links):

    - Create your first project (link to guide)

    - Author a test case (link to guide)

    - Run a test (link to guide)

    - View reports (link to guide)

  - Known Limitations (Transparent):

    - Playwright automation limited to web apps (native apps in v2)

    - AI step generation beta (fallback to manual if LLM offline)

    - Basic reports (full dashboards + export in v1.5)

  - Feedback: "We're listening! Report bugs or suggest features in #qa-nexus-feedback"

- Format: Markdown (GitHub release notes) + sanitized HTML (in-app announcement banner)

- Distribution: GitHub release tag, in-app banner (1-week visibility), email to pilots, Slack

Priority: P0
Estimate: 6 hours
Owner: PM + Technical Writer
Dependencies: All features complete
US-ID: None (marketing)
TB/EP: None

## ACCEPTANCE CRITERIA MATRIX

| AC-ID | Component | Acceptance Condition (Given/When/Then) | Verifier | Status |
| --- | --- | --- | --- | --- |
| MS5-AC001 | Playwright Runner (MS5-T001) | Given a test spec with 5 steps, when enqueued to Hatchet, then runner executes all steps, captures screenshots + HAR + logs, uploads to R2, and returns success | QA | TBD |
| MS5-AC002 | Hatchet Job Execution (MS5-T002) | Given 3 concurrent automation runs, when workers allocated from pool, then all 3 execute in parallel without resource contention | DevOps | TBD |
| MS5-AC003 | Automation API (MS5-T003) | Given a test run created via API, when status polled, then response includes progress % + artifact links | Backend | TBD |
| MS5-AC004 | R2 Artifact Storage (MS5-T004) | Given artifacts uploaded to R2, when accessed via signed URL, then file downloads correctly + URL expires after 1h | DevOps | TBD |
| MS5-AC005 | Web Spec Editor (MS5-T005) | Given a test step added via TipTap editor, when saved, then step stored in automation_suites.spec_json + can be executed | Frontend | TBD |
| MS5-AC006 | Flake Detection Algorithm (MS5-T006) | Given a test that passes 6/10 times (60% rate), when flake check runs, then classified as FLAKY + badge visible in UI | Analytics | TBD |
| MS5-AC007 | Materialized Views (MS5-T007) | Given 50 test runs + 20 defects, when report views refreshed, then KPI cards show correct totals + trends | Backend | TBD |
| MS5-AC008 | Report API (MS5-T008) | Given project with 30+ runs, when automation-summary endpoint queried, then response includes 3 KPI cards with values + trends | Backend | TBD |
| MS5-AC009 | Report Dashboard (MS5-T009) | Given 30 days of test data, when trend chart renders, then stacked area shows passed/failed per day + tooltip on hover | Frontend | TBD |
| MS5-AC010 | AI Step Generation (MS5-T010) | Given natural-language scenario ("user logs in"), when A1 generates steps, then output includes 5+ steps with confidence >0.7 + requires approval before save | AI | TBD |
| MS5-AC011 | Feature Flag Integration (MS5-T011) | Given reports.basic_v1 flag disabled, when report page loaded, then "Coming soon" shown; when flag enabled, then dashboards render | Frontend | TBD |
| MS5-AC012 | MVP Readiness Gate (MS5-T012) | Given go/no-go review meeting, when all 8 launch criteria evaluated, then decision recorded + approved by PM + Tech Lead | PM | TBD |
| MS5-AC013 | Pilot Onboarding (MS5-T013) | Given 2 pilot teams invited, when training session completed, then all participants can independently: create project, author test, log defect, view report | QA | TBD |
| MS5-AC014 | Performance (MS5-T014) | Given 10 concurrent users load testing, when simulating pilot workload for 5 min, then p95 latency <500ms + error rate <2% + no server crash | DevOps | TBD |
| MS5-AC015 | Backup Restore (MS5-T015) | Given production backup on R2, when restore executed on staging, then row counts match + data integrity passed + RTO <4h | DevOps | TBD |
| MS5-AC016 | WCAG 2.2 AA (MS5-T016) | Given accessibility audit on 10 critical screens, when automated + manual checks complete, then ≥90% pass rate + all critical failures fixed | Frontend | TBD |
| MS5-AC017 | E2E Tests (MS5-T017) | Given 3 critical Playwright journeys written, when executed via runner, then all pass + artifacts captured | QA | TBD |
| MS5-AC018 | Flake Detection Validation (MS5-T018) | Given 5 synthetic test specs with known flake rates, when detection runs, then classification accuracy ≥95% | QA | TBD |
| MS5-AC019 | On-Call Runbook (MS5-T019) | Given 4 P0–P2 scenarios documented, when runbook tested by on-call trainee, then Ollama restart succeeds <5 min | DevOps | TBD |
| MS5-AC020 | Feature Flag Rollout (MS5-T020) | Given flags rolled from dark → GA over 4 days, when each stage monitored, then <2% error rate throughout + user feedback neutral/positive | PM + DevOps | TBD |
| MS5-AC021 | Release Notes (MS5-T021) | Given release notes drafted, when reviewed by PM + TW, then content approved + distributed to pilots + GitHub | PM | TBD |

## ENVIRONMENT & SETUP CHECKLIST (DAY 1)

New Team Member Onboarding:

- ☐ Slack access (#qa-nexus-pilots, #oncall, #dev)

- ☐ GitHub access (iksula/qa-nexus repo, branch: feat/m5-automation)

- ☐ Vercel access (logs, deployment history, env vars)

- ☐ Oracle VM access (SSH key, VPN, monitoring dashboards)

- ☐ Doppler access (dev secrets: R2 creds, Jira OAuth, Claude API key)

- ☐ SigNoz access (observability dashboards, alert rules)

- ☐ GlitchTip access (error tracking, release tracking)

- ☐ Unleash access (feature flag dashboard)

- ☐ Local dev setup:

  - git clone https://github.com/iksula/qa-nexus

  - npm install (root)

  - cd frontend && npm install && npm run dev (port 3000)

  - cd backend && npm install && npm run start:dev (port 3001)

  - cd inference && pip install -r requirements.txt && python main.py (port 8000)

  - Verify: curl http://localhost:3001/health → 200 OK

- ☐ Database access:

  - psql -h oracle-vm-ip -U qaix_admin -d qaix_dev

  - Run migrations: npm run migrate:dev

  - Seed test data: npm run seed:test-data

- ☐ Feature flag defaults (local config, unleash.json):

  - automation.playwright_runner: false

  - reports.basic_v1: false

  - ai.auto_playwright: false

- ☐ IDE setup:

  - ESLint + Prettier configured

  - TypeScript strict mode enabled

  - .env.local with API keys (request from PM)

## API CONTRACTS (M5 SCOPE ONLY)

All endpoints authenticated via BetterAuth session cookie; RBAC enforced at service level.

### Automation Suite Management

#### POST /api/automation/suites

Purpose: Create automation suite (collection of related test specs)

Request:

{
  "projectId": "proj_123",
  "name": "Login Flow",
  "description": "Tests for login authentication",
  "environment": "staging"
}

Response (201 Created):

{
  "id": "suite_456",
  "projectId": "proj_123",
  "name": "Login Flow",
  "specJson": {},
  "createdAt": "2026-08-10T10:00:00Z"
}

#### GET /api/automation/suites/:id

Purpose: Fetch suite + test specs

Response (200):

{
  "id": "suite_456",
  "name": "Login Flow",
  "specs": [
    {"id": "spec_001", "name": "Valid Credentials", "steps": [...], "flakeStatus": "stable"}
  ],
  "lastRun": {"id": "run_789", "status": "pass", "timestamp": "2026-08-16T14:30:00Z"}
}

### Automation Run Execution

#### POST /api/automation/runs

Purpose: Create new automation run (enqueue suite)

Request:

{
  "suiteId": "suite_456",
  "environment": "staging",
  "parallelism": 1
}

Response (201):

{
  "id": "run_789",
  "suiteId": "suite_456",
  "status": "queued",
  "jobId": "hatchet_job_xyz",
  "estimatedDuration": 120,
  "createdAt": "2026-08-16T14:30:00Z"
}

#### GET /api/automation/runs/:id

Purpose: Poll run status + progress

Response (200):

{
  "id": "run_789",
  "status": "running",
  "progress": 0.6,
  "results": [
    {
      "specId": "spec_001",
      "status": "pass",
      "duration": 45,
      "artifacts": {
        "screenshot": "https://r2.example.com/...",
        "har": "https://r2.example.com/...",
        "logs": "https://r2.example.com/..."
      }
    }
  ],
  "flakeDetected": [
    {"specId": "spec_004", "passRate": 0.6, "classification": "FLAKY"}
  ]
}

#### POST /api/automation/runs/:id/stop

Purpose: Stop running automation suite (graceful shutdown)

Response (200):

{
  "id": "run_789",
  "status": "stopped",
  "stoppedAt": "2026-08-16T14:45:00Z"
}

### Flake Status

#### GET /api/automation/flake-status?projectId=proj_123

Purpose: Fetch flaky tests for project

Response (200):

{
  "projectId": "proj_123",
  "flakes": [
    {
      "testId": "test_001",
      "name": "Login with Session Timeout",
      "passRate": 0.65,
      "recent10Runs": [1, 0, 1, 1, 0, 1, 0, 1, 1, 0],
      "firstDetected": "2026-08-01T00:00:00Z",
      "confidence": 0.92
    }
  ]
}

### Basic Reports

#### GET /api/reports/dashboards/automation-summary?projectId=proj_123

Purpose: Fetch KPI cards for automation dashboard

Response (200):

{
  "projectId": "proj_123",
  "period": "last_30_days",
  "cards": [
    {
      "label": "Total Runs",
      "value": 250,
      "trend": "+15%",
      "metadata": {"prevPeriod": 217, "change": 33}
    },
    {
      "label": "Pass Rate",
      "value": "87%",
      "trend": "-2%",
      "metadata": {"prevPeriod": 0.89}
    },
    {
      "label": "Avg Duration",
      "value": "45s",
      "trend": "stable",
      "metadata": {"min": 20, "max": 120}
    }
  ],
  "lastUpdated": "2026-08-16T14:30:00Z"
}

#### GET /api/reports/dashboards/defect-summary?projectId=proj_123

Purpose: Fetch defect KPI cards

Response (200):

{
  "projectId": "proj_123",
  "period": "last_30_days",
  "cards": [
    {
      "label": "Open by Severity",
      "value": {"critical": 3, "major": 12, "minor": 45},
      "trend": "-1 critical"
    },
    {
      "label": "Mean Time to Close",
      "value": "3.2d",
      "trend": "-0.5d"
    },
    {
      "label": "Reopens",
      "value": 7,
      "trend": "-2"
    }
  ],
  "lastUpdated": "2026-08-16T14:30:00Z"
}

#### GET /api/reports/dashboards/trend-30d?projectId=proj_123

Purpose: Fetch 30-day pass/fail trend data for chart

Response (200):

{
  "projectId": "proj_123",
  "data": [
    {"date": "2026-07-17", "passed": 150, "failed": 20, "total": 170},
    {"date": "2026-07-18", "passed": 155, "failed": 18, "total": 173}
  ],
  "summary": {
    "avgPassRate": 0.887,
    "trend": "improving",
    "bestDay": "2026-07-25",
    "worstDay": "2026-07-18"
  }
}

### AI-Assisted Playwright Step Generation

#### POST /api/automation/generate-steps

Purpose: Generate test steps from natural language (async via Hatchet)

Request:

{
  "scenario": "User logs in with valid credentials",
  "appUrl": "https://app.example.com",
  "pastTestIds": ["test_001", "test_002"],
  "projectId": "proj_123"
}

Response (202 Accepted):

{
  "jobId": "hatchet_job_abc",
  "status": "queued",
  "estimatedWaitTime": 30
}

#### GET /api/automation/generate-steps/:jobId

Purpose: Poll generation job status

Response (200 while running):

{
  "jobId": "hatchet_job_abc",
  "status": "running",
  "progress": 0.5
}

Response (200 when done):

{
  "jobId": "hatchet_job_abc",
  "status": "done",
  "steps": [
    {"action": "navigate", "url": "https://app.example.com/login", "screenshot": true, "confidence": 0.95},
    {"action": "fill", "selector": "input[name='email']", "value": "user@example.com", "confidence": 0.88},
    {"action": "click", "selector": "button[type='submit']", "confidence": 0.92},
    {"action": "wait", "selector": "text=Dashboard", "timeout": 5000, "confidence": 0.85},
    {"action": "assertion", "type": "text", "selector": ".greeting", "expected": "Hello User", "confidence": 0.90}
  ],
  "overallConfidence": 0.90,
  "readingFromKb": ["Test Strategy: Login Flow", "Past Test: Login with OTP"]
}

## DATABASE CHANGES (M5 SCOPE)

### New Tables

#### automation_suites

CREATE TABLE automation_suites (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  project_id UUID NOT NULL REFERENCES projects(id),
  name VARCHAR(255) NOT NULL,
  description TEXT,
  spec_json JSONB NOT NULL DEFAULT '{}',
  browser_type VARCHAR(50) DEFAULT 'chromium',
  headless BOOLEAN DEFAULT true,
  created_at TIMESTAMP DEFAULT NOW(),
  updated_at TIMESTAMP DEFAULT NOW(),
  created_by UUID REFERENCES users(id),
  UNIQUE(project_id, name)
);
CREATE INDEX idx_automation_suites_project ON automation_suites(project_id);

#### automation_runs

CREATE TABLE automation_runs (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  suite_id UUID NOT NULL REFERENCES automation_suites(id),
  project_id UUID NOT NULL REFERENCES projects(id),
  environment VARCHAR(100),
  status VARCHAR(50) DEFAULT 'queued' CHECK (status IN ('queued', 'running', 'pass', 'fail', 'stopped')),
  hatchet_job_id VARCHAR(255),
  started_at TIMESTAMP,
  ended_at TIMESTAMP,
  total_duration_sec INT,
  result_count INT DEFAULT 0,
  pass_count INT DEFAULT 0,
  fail_count INT DEFAULT 0,
  created_at TIMESTAMP DEFAULT NOW(),
  created_by UUID REFERENCES users(id),
  INDEX idx_automation_runs_project ON project_id,
  INDEX idx_automation_runs_status ON status
);

#### automation_artifacts

CREATE TABLE automation_artifacts (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  automation_run_id UUID NOT NULL REFERENCES automation_runs(id) ON DELETE CASCADE,
  artifact_type VARCHAR(50) NOT NULL CHECK (artifact_type IN ('screenshot', 'har', 'console_log', 'env_snapshot', 'video')),
  r2_url VARCHAR(2048),
  file_size_bytes BIGINT,
  created_at TIMESTAMP DEFAULT NOW(),
  INDEX idx_automation_artifacts_run ON automation_run_id
);

#### flake_signals (Materialized View Helper Table)

CREATE TABLE flake_signals (
  id UUID PRIMARY KEY DEFAULT gen_random_uuid(),
  test_case_id UUID NOT NULL REFERENCES test_cases(id),
  project_id UUID NOT NULL REFERENCES projects(id),
  pass_rate_5run DECIMAL(3, 2),
  pass_rate_10run_historical DECIMAL(3, 2),
  classification VARCHAR(50) CHECK (classification IN ('FLAKY', 'STABLE', 'BROKEN')),
  rerun_count INT DEFAULT 5,
  first_detected_at TIMESTAMP,
  last_confirmed_at TIMESTAMP,
  created_at TIMESTAMP DEFAULT NOW(),
  UNIQUE(test_case_id, project_id)
);
CREATE INDEX idx_flake_signals_project ON flake_signals(project_id);

### Materialized Views

#### run_summary_metrics

CREATE MATERIALIZED VIEW run_summary_metrics AS
SELECT
  project_id,
  DATE_TRUNC('day', NOW())::DATE as metric_date,
  COUNT(*) as total_runs,
  ROUND(100.0 * COUNT(CASE WHEN status = 'pass' THEN 1 END) / NULLIF(COUNT(*), 0), 2) as pass_rate_pct,
  ROUND(AVG(EXTRACT(EPOCH FROM (ended_at - started_at))), 0)::INT as avg_duration_sec,
  MAX(updated_at) as last_run_at
FROM automation_runs
WHERE updated_at >= NOW() - INTERVAL '30 days'
GROUP BY project_id;

CREATE UNIQUE INDEX idx_run_summary_metrics ON run_summary_metrics (project_id, metric_date);

#### defect_summary_metrics

CREATE MATERIALIZED VIEW defect_summary_metrics AS
SELECT
  project_id,
  DATE_TRUNC('day', NOW())::DATE as metric_date,
  COUNT(CASE WHEN status = 'open' AND severity = 'critical' THEN 1 END) as open_critical,
  COUNT(CASE WHEN status = 'open' AND severity = 'major' THEN 1 END) as open_major,
  COUNT(CASE WHEN status = 'open' AND severity = 'minor' THEN 1 END) as open_minor,
  ROUND(AVG(EXTRACT(EPOCH FROM (resolved_at - created_at))), 0)::INT as mttr_sec,
  COUNT(CASE WHEN reopen_count > 0 THEN 1 END) as reopen_count
FROM defects
WHERE created_at >= NOW() - INTERVAL '30 days'
GROUP BY project_id;

CREATE UNIQUE INDEX idx_defect_summary_metrics ON defect_summary_metrics (project_id, metric_date);

#### pass_fail_trend

CREATE MATERIALIZED VIEW pass_fail_trend AS
SELECT
  project_id,
  DATE_TRUNC('day', automation_runs.created_at)::DATE as date,
  COUNT(CASE WHEN status = 'pass' THEN 1 END) as passed,
  COUNT(CASE WHEN status = 'fail' THEN 1 END) as failed,
  COUNT(*) as total
FROM automation_runs
WHERE created_at >= NOW() - INTERVAL '30 days'
GROUP BY project_id, date
ORDER BY project_id, date;

CREATE INDEX idx_pass_fail_trend_project ON pass_fail_trend (project_id, date);

### Migrations

- Migration file: 2026-08-03_001_create_automation_tables.sql

  - Creates all tables above

  - Creates indexes

  - Grants permissions to api_user role

- Refresh schedule: REFRESH MATERIALIZED VIEW CONCURRENTLY run_summary_metrics; every 60 min

## TESTING PLAN

### Unit Tests (Target: ≥80% Coverage)

Modules to test:

- PlaywrightRunner.ts — step execution, artifact capture, error handling

- FlakeDetectionService.ts — pass rate calculation, classification logic

- ReportAggregator.ts — KPI computation, trend calculation

- AutomationController.ts — API request validation, response serialization

Tools: Jest + ts-jest, coverage threshold enforced in CI

### Integration Tests (Target: ≥70% Critical Paths)

Scenarios:

- E2E automation: create suite → enqueue → run → verify artifacts in R2

- Flake detection: 5 re-runs → pass rate → classification → UI badge

- Report generation: query materialized views → aggregate metrics → serialize response

- API security: verify RBAC enforced, unauthenticated requests rejected

Tools: Jest + test containers (PostgreSQL), Hatchet mock jobs

### E2E Tests (Playwright via Runner)

3 Critical Journeys:

- Auth Journey: Register → Login → Project Picker

- Test Case Creation: Create case → A1 generate steps → Save

- Defect Flow: Create run → Execute → Fail → Log defect → Push to Jira

Tools: Playwright (self-test via automation runner MS5-T017)

### Performance Tests (k6)

Load test scenario: 10 concurrent users × 5 min, 2–3 rounds

SLOs:

- p95 API latency <500ms (target <300ms)

- p95 doc gen <60s

- p95 RCA <10s

- Error rate <2%

### Security Scans (GitHub Actions)

Weekly SAST + SCA:

- Snyk: dependency vulnerabilities, code smells

- Trivy: container image vulnerabilities

- OWASP ZAP: API endpoint vulnerabilities (POST request injection, auth bypass)

## FEATURE FLAG STRATEGY

| Flag | Feature | Owning Task | Default | Rollout Phase | Kill Switch | Retirement |
| --- | --- | --- | --- | --- | --- | --- |
| automation.playwright_runner | Playwright automation runner + Hatchet | MS5-T002 | false | Dark → Canary 10% (W3 Wed) → GA (W3 Sat) | unleash disable automation.playwright_runner | 2026-09-21 |
| ai.auto_playwright | AI-assisted step generation | MS5-T010 | false | Dark → Canary 5% (W2 Thu) → GA (W3 Sat) | unleash disable ai.auto_playwright | 2026-09-21 |
| reports.basic_v1 | Basic reports dashboards | MS5-T011 | false | Dark → Canary 20% (W2 Wed) → GA (W3 Sat) | unleash disable reports.basic_v1 | 2026-09-21 |

## RISK & BLOCKER REGISTER

| R-ID | Description | Likelihood | Impact | Owner | Mitigation | Status |
| --- | --- | --- | --- | --- | --- | --- |
| MS5-R001 | Playwright worker concurrency exceeds Oracle VM budget (CPU throttle) | Medium | High | DevOps | Max 3 concurrent workers, circuit breaker on CPU >80% | Monitoring |
| MS5-R002 | Flake detection false positives (>20% mislabeled tests) | Medium | Medium | Analytics | Validate on synthetic 5-run dataset, adjust pass-rate thresholds if needed | Pre-launch test |
| MS5-R003 | Report query performance degrades with >100K defects | Low | High | Backend | Materialized view refresh during off-peak, index optimization, partition if needed | Loadtest TBD |
| MS5-R004 | Pilot onboarding friction (low adoption in week 1) | Medium | High | PM | Live training, weekly check-ins, fast response SLA (<2h) | Mitigation |
| MS5-R005 | MVP launch slippage (features not ready by 2026-08-16) | Low | Critical | Eng Lead | P0 exit gate enforcement, daily standup, scope descope if needed | Daily tracking |
| MS5-R006 | Jira OAuth token expiry mid-pilot (defect sync breaks) | Low | Medium | Backend | Token refresh implemented in M3, test refresh flow weekly | Done |
| MS5-R007 | GlitchTip/SigNoz disk full (observability blackout) | Low | High | DevOps | Auto-cleanup old logs, alert at 70% capacity, extend disk space if needed | Preventive |
| MS5-R008 | A4 RCA accuracy <60% during automation runs (confidence miscalibrated) | Low | Medium | AI | Weekly human audit, Langfuse evals, retrain if needed | Weekly review |

## ROLLBACK PLAN

Trigger Conditions (any one triggers rollback decision):

- P0 Bug: Unrecoverable error affecting >20% of pilot users

- Data Corruption: Automation artifacts lost, defects missing from Jira

- Performance SLO Breach: p95 latency >1s for >30 min despite mitigation attempts

- Security Incident: Unauthenticated access to defects, R2 bucket traversal

Rollback Steps (RTO: <30 min):

- Immediate (5 min):

  - Disable feature flags: unleash disable automation.playwright_runner reports.basic_v1 ai.auto_playwright

  - Notify pilots in Slack: "We've temporarily disabled automation features while we investigate. Manual test logging still works."

  - Page on-call engineer + PM

- Investigation (10 min):

  - Check GlitchTip for error patterns

  - Check SigNoz for latency spikes or resource exhaustion

  - Check Hatchet job queue for stuck jobs

  - Pull logs: ssh oracle-vm; journalctl -u api | tail -100

- Fix or Revert (10 min):

  - If transient issue (e.g., Ollama OOM): Restart service, re-enable flag, monitor 10 min

  - If code bug: Revert last commit (git revert -n HEAD) + re-deploy to Vercel, test on dev, re-enable flags

  - If data corruption: Restore DB from R2 backup (see MS5-T015)

- Post-Rollback (5 min):

  - Verify normal operation: test login, create case, log defect

  - Notify pilots: "Resolved. Re-enabling automation features."

  - File incident post-mortem in Jira (due within 24h)

Data Migration Reversal Strategy:

- If rolling back migrations: npm run migrate:undo (reverts last migration)

- If rolling back from backup: restore via psql < /tmp/qaix-backup.sql, verify row counts, restart services

No-Rollback Alternative (Graceful Degrada):

- If issue affects only AI features (ai.auto_playwright): disable flag, let manual workflow continue

- If issue affects only reports (reports.basic_v1): disable flag, let execution + defect logging continue

- If issue affects only automation (automation.playwright_runner): disable flag, pilots use manual runs

## MILESTONE EXIT CRITERIA (DEFINITION OF DONE)

All criteria must be "Go" (green) for MVP launch approval.

- Code Quality:

  - All tasks merged to main

  - Code review complete + approved by 2 reviewers

  - CI/CD pipeline green (lint, type check, unit tests, security scan)

  - Zero ESLint errors, code coverage ≥80% for new code

- Testing:

  - All 20 task acceptance criteria verified (AC01–AC21)

  - 3 critical Playwright journeys pass (E2E tests MS5-T017)

  - Flake detection validation complete (95%+ accuracy, MS5-T018)

  - Load test passed (10 VUs, p95 <500ms, error rate <2%, MS5-T014)

- Performance:

  - p95 API latency <300ms (verified in load test)

  - p95 doc generation <60s

  - p95 RCA <10s

  - p95 search <500ms

  - Page load time (Lighthouse) ≥85

- Observability:

  - SigNoz dashboards green for 7 consecutive days (no error spikes)

  - GlitchTip <5 P0 errors per day, <20 P1 errors

  - Langfuse traces captured for all A1/A2/A4 agents

  - Alerts configured + firing correctly (test fire, then silence)

- Defect Quality:

  - 0 open P0 bugs

  - <3 open P1 bugs (all tracked in backlog for v1.5)

  - <10 open P2 bugs

- Documentation:

  - Release notes drafted + reviewed by PM

  - User guide (5–10 pages) published in KB

  - Admin guide published

  - API docs (OpenAPI) generated + reviewed

  - On-call runbook (MS5-T019) complete + tested

- Pilot Readiness:

  - 2–3 Iksula projects confirmed + contacts verified

  - Training sessions completed (all pilots can independently: create case, log defect, view report)

  - Success metrics dashboard live + baseline captured

  - Support channel (#qa-nexus-pilots) created + monitored

- Security & Compliance:

  - WCAG 2.2 AA audit complete, ≥90% pass rate

  - No critical vulnerabilities in Snyk scan

  - Backup/restore tested end-to-end (RTO <4h, data integrity verified)

  - Audit log complete (all user + agent actions logged)

- Feature Flags:

  - All 3 flags wired (dark launch state)

  - Rollout plan documented + approved

  - Kill switches tested (disable flag, verify graceful degradation)

- Go/No-Go Gate:

  - Review meeting held (Fri, 2026-08-22, 2–3 PM)

  - All 9 exit criteria evaluated + approved

  - Decision recorded + signed (PM + Tech Lead)

  - Launch approved by leadership

## NEXT MILESTONE PREVIEW (M6: GA PREP)

M6 High-Level Scope (2026-08-17 → 2026-09-20, 5 weeks post-MVP):

- Legal + Compliance: GDPR right-to-delete, SOC 2 Type II readiness, privacy policy, ToS

- Security Audit: Penetration testing, OAuth 2.0 security review, secrets rotation

- Monitoring + On-Call: Datadog/PagerDuty integration, escalation runbooks, incident response playbook

- Marketing + Sales: Landing page, sales deck, competitive brief, pricing tier options

- Support Enablement: FAQ, support ticketing system, customer success playbook

- Full Reports (Deferred from M5): Release Readiness Report, RCA Aggregate, full Exec Dashboard, PDF/XLSX export

- Performance Optimization (if needed): Caching layer tuning, database partitioning, CDN edge caching

- Documentation: Comprehensive user manual, API docs (GraphQL if needed), architecture ADRs

## HANDOFF NOTES

Delivered M5:

- Playwright automation runner + Hatchet job execution

- R2 artifact storage (screenshots, HAR, logs, env snapshots)

- Flake detection algorithm (5-run strategy, 20–80% pass rate threshold)

- Basic reports (3 KPI dashboards + 30-day trend chart)

- AI-assisted Playwright step generation (LangGraph variant, gated behind ai.auto_playwright flag)

- MVP launch checklist + go/no-go gate

- 2–3 Iksula pilot teams onboarded + live

- Zero P0 bugs, <3 P1, observability green 7 days

Known Deferred Items (v1.5+):

- Full custom dashboards (pivot tables, drill-down, cohort analysis)

- Scheduled email reports

- PDF/XLSX export (export as image only in MVP)

- Analytics warehouse (post-MVP scale path)

- Traceability matrix report

- Cloud device grid / BrowserStack partnership

- Playwright self-healing (A7 step correction, v1.5)

- Full test planning agent (A8, v1.5)

Technical Debt Logged:

- Materialized view refresh during load test causes occasional lock contention (acceptable for MVP, optimize in M6)

- Ollama fallback to Gemini 2.5 Flash needs rate-limit monitoring (free tier: 1.5K req/day)

- Flake detection confidence scoring calibrated on synthetic data (validate against real pilot data)

Lessons Learned (to feed M6 roadmap):

- Pilots requested faster feedback on test execution (consider WebSocket streaming of results)

- Report dashboard performance depends heavily on materialized view refresh strategy

- AI step generation approval flow requires high confidence threshold to avoid user frustration

## APPENDIX

### Glossary

- Flaky Test: Test that passes inconsistently (20–80% pass rate over last 10 runs)

- Materialized View: Cached query result in PostgreSQL, refreshed on schedule

- Hatchet: Postgres-backed job queue for async work (document gen, automation runs, report generation)

- R2: Cloudflare object storage for evidence (screenshots, HAR, logs)

- pgvector: PostgreSQL extension for semantic search (embeddings)

- KPI: Key Performance Indicator (metrics card in dashboard)

- Confidence Scoring: LLM-assigned probability (0–1) that output is correct

- Rollout Pattern: Gradual feature release (dark → internal → canary → GA)

### Reference Links

- Milestone Registry — Cross-milestone dependencies, DoR/DoD chain

- PRD — Product requirements, user stories, success metrics

- ERD — Database schema, API contracts, components

- DESIGN — UI/UX patterns, accessibility guidelines

- GitHub Issues — Task tracking

- SigNoz — Observability dashboard

- GlitchTip — Error tracking

- Unleash — Feature flags

END OF MILESTONE M5 DOCUMENT

Version 1.0 | Final | Ready for Go/No-Go Gate Review