Table of Contents

# QA NEXUS — MILESTONE M6: FULL REPORTS SUITE + GA

⚠️ Tech stack updated 2026-04-25 — see PM1_PRD v8.1 / PM1_ERD v2.1 as binding. M6 is the v1 GA milestone — all 12 acceptance gates must pass before customer-facing release. The task list below was written against the v1.0 self-hosted vision. For the actual M6 build: - GA target date (locked): 2026-09-21 - Build window: Weeks 18, after M5 pilot validates the system on 8 Iksula users - Frames at GA: all 41 (17 Claude Design + 24 Claude Code, including F28m1 + F26m1 added v2.10) — no further frame additions in M6 unless a critical pilot finding demands one - Reports Studio polish: 4 templates → templated PDF/Excel/HTML export tested across all 4 priority levels (P0/P1/P2/P3) and all 3 release types (PaymentV2, Returns, Mobile App) - Acceptance gates (binding from PM1_ERD v2.1 §10) — all 12 must pass for GA: 1. 41 of 41 UI frames render at locked design tokens (no MD3 drift, no tertiary colors, no missing project switcher) 2. A1 eval ≥80% golden-set match 3. A2 eval <5% FP, ≥60% TP 4. A4 eval top-2 RCA accuracy ≥70% on 50-defect golden set 5. NFR-001 page load p50 <1.5s, p95 <3s 6. NFR-002 API latency p50 <200ms, p95 <500ms (excluding LLM calls) 7. NFR-003 agent latency: A1 <10s, A2 <500ms, A4 <15s at p95 (revised v2.1 — Groq is much faster than self-hosted Gemma) 8. NFR-014 RBAC all 4 roles correctly gated 9. HMAC audit chain integrity ≥99.95% 10. Pilot acceptance: 6 of 8 pilot users complete end-to-end flow without engineer intervention 11. Cost gate: monthly infrastructure spend = $0 confirmed by SRE 12. Free-tier headroom check: each free tier (Groq RPD, Neon CU-hr, Render bandwidth, R2 storage) at <50% utilization at GA - PM2 transition: After GA on 2026-09-21, the team kicks off PM2 work. PM2 brings back FastAPI (for advanced agent work), Valkey (for BullMQ queues), self-healing agent A7, etc. — see project-level ERD §3 for the eventual self-hosted architecture. - Cost discipline through GA: $0/month entire build. If any acceptance gate forces a paid migration (e.g., Render Starter $7/mo for no-sleep), document the trade-off and get user approval before incurring spend.

Use this M6 file for the GA launch checklist. For binding gate criteria, defer to PM1_PRD v8.1 §15 + §20 and PM1_ERD v2.1 §10.

Milestone ID: M6
Title: Full Reports Suite + General Availability
Duration: 5 weeks (2026-08-17 → 2026-09-20)
GA Target Date: 2026-09-21
Organization: Iksula Services Pvt Ltd
Version: 1.0
Date: 2026-04-21

Date Authority: All dates in this document derive from MILESTONE_REGISTRY.md. Any drift between this doc and the registry is a bug — the registry wins.

Status: Draft (Ready for downstream planning)

## TABLE OF CONTENTS

- Executive Summary

- Context: What Was Delivered Before

- Definition of Ready (DoR)

- M6 Scope & Mission

- Tech Stack (M6-Specific)

- Database Changes (M6)

- API Contracts

- Feature Flags

- 5-Week Plan

- Tasks (MS6-T###)

- Acceptance Criteria (MS6-AC###)

- Risks & Mitigations (MS6-R###)

- Testing & QA

- GA Readiness Checklist

- Rollback & Fallback Plans

- Dependencies & Handoffs

- Success Metrics

- Glossary

## 1. EXECUTIVE SUMMARY

M6 is the final push to General Availability (GA) for QA Nexus. The MVP (M0–M5) shipped a core test management platform with basic reports and dashboards. M6 defers the full analytics warehouse, completes the reporting/export suite, and hardens the platform for external customers.

Mission: Deliver the analytics engine, finalize all report templates and export formats, build scheduled email distribution, pass security/accessibility/performance audits, and achieve GA launch readiness.

Key Deliverables:

- Analytics Warehouse (DuckDB): ETL from Postgres (hourly), columnar compression for fast aggregations

- Custom Dashboard Builder (drag-and-drop widgets: chart, KPI, table, heatmap)

- Cohort Analysis (tester × sprint × pass-rate)

- Traceability Matrix Report (Requirements → Test Cases → Runs → Defects) exportable to XLSX/PDF

- Quality KPI Dashboard (DPPM, DRE, test-case yield, MTBF between defects)

- Customer-Saved Report Library with sharing permissions

- PDF Export (via headless Chromium)

- XLSX Export (via exceljs)

- Scheduled Email Reports (weekly summary, per-project) via Resend + Hatchet cron

- GA Hardening: Performance tuning (query EXPLAIN ANALYZE pass), accessibility audit pass (WCAG 2.1 AA), security pen-test remediation, capacity plan sign-off

Out of Scope (Deferred to v1.5+): A3/A5/A6/A7/A8 agents, Cloud Device Grid, Visual Regression suite, Vibe Code Governor, Billing/metering system (if no paid customers at GA).

## 2. CONTEXT / PREDECESSORS: WHAT WAS DELIVERED BEFORE (M0–M5)

This milestone is M6, the final MVP (PM1) sub-milestone (Weeks 19–23 of 21 total build weeks + 3 GA weeks). Canonical predecessor chain per MILESTONE_REGISTRY.md v3.2:

### M0 (Weeks 1–2): Setup & Infrastructure

- BetterAuth authentication (email/password, session, password reset, MFA-ready)

- 4-role RBAC (Admin, Lead, QA, Stakeholder)

- PostgreSQL 15 + pgvector

- Ollama + Gemma 4 deployment

- Vercel + Oracle Always Free + Cloudflare R2 infrastructure

- CI/CD pipeline (GitHub Actions)

- Observability (SigNoz, GlitchTip, Langfuse)

- Audit log foundation

### M1 (Weeks 3–4): Users & Roles

- 4-role RBAC fully enforced (Admin/Lead/QA/Stakeholder)

- Project CRUD (create, list, update, delete)

- Row-Level Security (RLS) enforced on all tables

- User profile attributes (Jr/Sr/Automation)

- User invitations and org management

### M2 (Weeks 5–7): Test Documents & Knowledge Base — Core Doc Catalog (12 templates)

- KB CRUD + approval workflow

- RAG pipeline (BGE embeddings + pgvector)

- 12 document templates (Strategy, Plan, RTM, Daily/Weekly/Sprint/Release reports, Defect Report, RCA, Charter, Regression)

- Document Intelligence Layer (A1 context-gathering)

- PDF export via Puppeteer

- Versioning + comments + @-mentions

### M3 (Weeks 8–10): Test Cases & AI Generation — Test Case Management

- Test case CRUD (TipTap editor, BDD + traditional modes)

- A1 Test Case Generator (LangGraph, Clarification Questions gate, confidence badges)

- A2 Dedup (live chips, semantic similarity, bulk audit)

- RTM linking + tags + priority + stability sparklines

- Bulk import (CSV, TestRail, Zephyr, Xray, qTest)

- Test Case Management complete; 100+ cases seeded

### M4 (Weeks 11–13): Runs, Defects & Jira — Bug Management + Integrations

- Test Run CRUD + execution UI (step-by-step executor)

- Auto-evidence capture (screenshot + HAR + console + env snapshot)

- Defect CRUD + 4-category classification (App/Test/Flaky/Env)

- A4 Defect Intelligence (5-layer RCA: stack → env → config → code → data)

- Jira OAuth 2.0 (3-legged) + 2-way sync (status, assignee, comments, attachments)

- Webhook + 2-min poll fallback

- Run Dashboard (real-time metrics, pass/fail trend, defect severity pie)

### M5 (Weeks 14–18): Automation + Basic Reports + MVP Launch — Basic Reporting

- Templated report generation (Daily Status, Weekly Status, Sprint Sign-off, Release Readiness)

- Personal dashboard (my cases, my bugs, my approvals)

- Executive Dashboard lite (pass rate, defect trend, coverage %, release-readiness RAG)

- ROI calculator (cost_avoidance formula)

- Playwright E2E test runner + evidence

- WCAG 2.2 AA accessibility audit + critical fixes

- Command-K omnibox (global search + agent invocation)

- Global search indexing (cases, defects, docs, KB)

- Audit log completion

- E2E tests (Playwright, 3 critical journeys)

- Pilot onboarding docs + training

- Load testing (10 concurrent pilots, <2% error rate, p95 <500ms)

Status at M5 Exit: MVP stable in pilot ≥7 days. Zero P0 defects. Pilot feedback incorporated. All M0–M5 acceptance criteria closed. Ready for M6 GA hardening phase.

## 3. DEFINITION OF READY (DoR)

### M5 Completion Verified (Exit Criteria Met)

- WCAG 2.2 AA compliance audit completed (all critical paths pass)

- Command-K omnibox functional (⌘K / Ctrl+K working in all contexts)

- Global search indexed (cases, defects, docs, KB entries)

- Audit log complete + tested

- Performance optimization validated (p95 <60s doc gen, <10s RCA, <500ms UI)

- E2E test suite passing (3 critical journeys: Auth, Test Case, Defect)

- Load testing completed (10 concurrent pilots)

- Pilot onboarding docs + training materials ready

- Incident response runbook drafted

- Legal + compliance checklist started (privacy policy, ToS, GDPR assessment)

### External Readiness

- Pilot deployments stable for ≥7 days with zero P0 defects

- Pilot telemetry flowing and dashboards live

- Documentation complete (user guide, admin guide, API docs)

- On-call runbook covers P0–P2 scenarios

- Jira API integration tested at scale (≥1K defect syncs)

- Resend email service configured and validated

### Data Readiness

- Pilot test case inventory: ≥100 cases per project

- Pilot test run history: ≥50 runs with results + evidence

- Pilot defect inventory: ≥30 defects with A4 RCA output

- Pilot duration: ≥14 days for statistically meaningful data

## 4. M6 SCOPE & MISSION

### Week 1: Analytics Warehouse Bootstrap + ETL Jobs + Baseline Queries

Goal: DuckDB instance deployed; hourly ETL pipeline from Postgres live; baseline queries tested (p95 <2s).

Key Work: - Set up DuckDB instance (on Oracle Always Free or Hetzner standby) - Design warehouse schema (fact tables: test_runs, defects, evidence; dimensions: dates, projects, testers) - Build Python ETL worker (Hatchet scheduled job, hourly) - Implement incremental sync (since-last-run markers, conflict resolution) - Create 10 baseline queries (pass-rate trend, defect-by-category, coverage %, test-case yield, MTBF) - Validate query performance (EXPLAIN ANALYZE; target p95 <2s) - Build warehouse health dashboard (row counts, last-sync timestamp, error tracking)

Deliverables: DuckDB live, ETL job running hourly, 10 baseline queries validated, health dashboard.

### Week 2: Custom Dashboard Builder + Widget Library

Goal: Drag-and-drop dashboard editor live; widget library (chart, KPI, table, heatmap) complete; p95 <2s for rendering large datasets.

Key Work: - Design dashboard storage schema (dashboards, widgets, widget_instances tables) - Build React dashboard editor (TanStack React Grid for drag-drop layout) - Implement 4 widget types: Line Chart (recharts), KPI Card (single number + trend), Table (TanStack Table with sort/filter), Heatmap (d3-heatmap or visx) - Wire widgets to warehouse queries (dropdown selector for predefined queries + custom SQL if role=Admin) - Add dashboard sharing permissions (public, project, private) - Build dashboard library / saved view list - Performance-test with 50+ widgets on single dashboard; optimize query batching - Implement caching (Redis, 5-min TTL)

Deliverables: Dashboard builder, widget library, sharing system, query optimizer.

### Week 3: Cohort Analysis + Traceability Matrix + Quality KPI Dashboard

Goal: Three specialized dashboard types live: Cohort (tester × sprint × pass-rate), Traceability Matrix (XLSX/PDF exportable), Quality KPI (DPPM, DRE, yield, MTBF).

Key Work:

Cohort Analysis: - Design cohort dimension schema (tester, sprint, project, environment) - Build query: SELECT tester, sprint, COUNT(PASS), COUNT(FAIL), COUNT(SKIP), ROUND(COUNT(PASS)*100.0/(COUNT(PASS)+COUNT(FAIL))) as pass_rate FROM warehouse_test_results GROUP BY tester, sprint - Render as heatmap + table with drill-down (click cell → individual results) - Export capability (XLSX + CSV)

Traceability Matrix: - Design query joining: requirements → test_cases → test_results → defects - Build XLSX exporter: one row per requirement, columns for [linked cases], [latest run status], [linked defects], [coverage %] - Add PDF export (via headless Chromium) - Filter by project + date range

Quality KPI Dashboard: - DPPM (Defects Per Million test-case executions): COUNT(defects) * 1e6 / COUNT(test_results) - DRE (Defect Removal Efficiency): defects_closed_by_qa / (defects_closed_by_qa + defects_found_in_production) - Test-case yield: COUNT(unique_case_ids) / COUNT(test_results) - MTBF (Mean Time Between Failures): SUM(elapsed_seconds) / COUNT(defects) per environment - Render as card grid + time-series chart - Add project/team/environment filters

Deliverables: Cohort editor, traceability matrix (XLSX+PDF), quality KPI dashboard, drill-down navigation.

### Week 4: PDF/XLSX Export + Scheduled Email Reports + Report Library

Goal: All report types exportable; scheduled email distribution live; customer-saved report library with sharing.

Key Work:

PDF Export: - Integrate Playwright/headless Chromium (or PDF.co API fallback) - Template each report type (Daily, Weekly, Sprint, Release, Custom Dashboard) as an HTML render - Implement footer (org logo, date, confidentiality statement) - Test rendering at scale (500+ page PDF from large dataset) - Add watermark for beta-customer reports

XLSX Export: - Use exceljs library - Multi-sheet workbooks: Summary + Details + Charts (embedded images) - Format cells: currency for ROI, percentage for pass rate, date for timestamps - Add pivot tables where applicable (Defect by Category, Pass Rate by Tester) - Implement file streaming for large exports (>50MB)

Scheduled Email Reports: - Design report_schedules table (project, recipient, frequency: daily/weekly/custom-day, time, enabled) - Build Hatchet scheduled job (runs at 08:00 org timezone per schedule) - Render report → Export to PDF/XLSX → Attach to email → Send via Resend - Add unsubscribe link (Resend suppression list) - Track delivery (bounce, open, click events) - Build schedule management UI (CRUD schedules, preview, test send)

Report Library: - Design saved_reports table (name, owner, project, query, permissions: public/project/private, created_at) - Build library browsing UI (filter by category, project, owner) - Implement sharing (invite by email, permission tiers: viewer/editor) - Add star/favorite functionality - Build report versioning (snapshots on schedule run)

Deliverables: PDF/XLSX exporters, email distribution pipeline, report library UI, schedule manager.

### Week 5: GA Hardening + Pen-Test Remediation + Accessibility Pass + Go/No-Go

Goal: Platform hardened for external customers; all P0/P1 security/perf/accessibility issues resolved; GA launch readiness confirmed.

Key Work:

Performance Tuning: - Run EXPLAIN ANALYZE on all warehouse queries; optimize slow ones (table scans → index scans, N+1 queries → batch) - Profile API endpoints (identify bottlenecks; target p95 <300ms for authenticated endpoints) - Optimize PDF/XLSX export (streaming, progress indicators, background job processing) - Test dashboard rendering with 100K+ rows (ensure <2s load time with pagination/virtual scrolling) - Load test: 20 concurrent users, 10 minute duration, monitor error rate + p95 latency

Security Pen-Test Remediation: - External pen-test execution (or internal code review if budget-constrained) - Common categories tested: - Authentication/authorization (session fixation, privilege escalation, missing role checks) - Input validation (SQL injection, XSS, XXE, CSRF) - Data exposure (sensitive data in logs, unencrypted transmission, PII leakage in exports) - API abuse (rate limiting, brute-force protection, file upload validation) - Fix all P0 findings (blocking GA); P1 findings (critical path); defer P2 findings (document + commit to v1.5) - Re-test all fixed issues

Accessibility Audit (WCAG 2.1 AA): - Run automated tools (axe, Lighthouse, WAVE) - Manual testing by QA + accessibility expert - Test with screen reader (NVDA, JAWS) - Test keyboard-only navigation (Tab, arrow keys, Enter, Escape) - Fix all failures: - Contrast ratio <4.5:1 → adjust colours - Missing alt text → add descriptions - Missing form labels → associate labels to inputs - Keyboard traps → ensure Escape/Tab works - Generate accessibility conformance report (AODA, EN 301 549 referencing)

Capacity Plan Sign-Off: - Document Oracle Always Free resource ceiling (4 OCPU, 24GB RAM, 2 TPCH) - Warm standby plan: Hetzner CX32 ($7.40/mo) auto-activated if Oracle VM down >30min - DuckDB column store size projections: 14 days data = ~2GB; scale plan to Hetzner at >5GB - Concurrent user capacity: 8 pilots baseline → 20 users with vertical scaling → 100+ users requires migration to Hetzner - Network bandwidth: ~100MB/day test data + logs; R2 egress <1GB/month within Cloudflare free tier - Sign-off: DevOps + PM + CTO approval documented

GA Launch Readiness Review: - Go/No-Go meeting: all M0–M6 ACs closed? - Zero P0 defects open for ≥7 days? - Pen-test findings resolved or risk-accepted? - WCAG 2.1 AA audit passed? - p95 latency budgets met? - Support tier definitions published? - Incident response runbook reviewed + on-call trained? - GA announcement blog + email drafted + approved? - Decision: GO or HOLD?

Deliverables: Performance tuning report, security pen-test results (all findings resolved), accessibility audit report (AORA), capacity plan, GO/NO-GO sign-off.

## 5. TECH STACK (M6-SPECIFIC)

| Component | Technology | Purpose |
| --- | --- | --- |
| Analytics Warehouse | DuckDB (1.0+) on Oracle Always Free or Hetzner | OLAP engine for fast aggregations; hourly ETL target |
| ETL Pipeline | Python (Hatchet scheduled job) | Extract from Postgres → Transform + Enrich → Load to DuckDB (incremental) |
| Batch Processing | Hatchet Worker (async, 1h schedule) | Orchestrate hourly ETL; retry logic; error notifications |
| Dashboard UI | React 18 + TanStack React Grid | Drag-drop layout; responsive grid; save/restore state |
| Chart Library | recharts (maintained, React-native) | Line, bar, pie, heatmap; dark/light mode support |
| Tables | TanStack Table v8 (headless) | Sortable, filterable, paginated tables; virtual scrolling for 100K+ rows |
| Heatmap Viz | d3-heatmap or visx | Cohort analysis heatmap rendering |
| PDF Export | Playwright (headless Chromium) or PDF.co fallback | Server-side rendering of dashboard → PDF; watermarks + footer |
| XLSX Export | exceljs | Multi-sheet workbooks; cell formatting; embedded charts; streaming for large files |
| Email Distribution | Resend (email service) + Hatchet | Scheduled job builds PDF/XLSX → Resend API sends + tracks delivery |
| Caching Layer | Redis (Upstash free tier) | 5-min TTL for warehouse query results; session cache |
| Database | PostgreSQL 15 + pgvector + DuckDB | OLTP (Postgres) + OLAP (DuckDB) hybrid; PG for operational data, DuckDB for analytics |
| Performance Tools | EXPLAIN ANALYZE, SigNoz APM, Chrome DevTools | Query optimization; latency profiling; RUM monitoring |
| Security Testing | OWASP ZAP (free) or external pen-test | Automated + manual vulnerability scanning |
| Accessibility Testing | axe, Lighthouse, WAVE, NVDA | Automated compliance checks + manual testing |

## 6. DATABASE CHANGES (M6)

### New Tables

| TB-ID | Table Name | Columns | Rationale |
| --- | --- | --- | --- |
| TB-019 | dashboards | id (uuid), project_id (fk), owner_id (fk), name (str), layout_json (jsonb), created_at, updated_at | Store custom dashboard definitions + layout state |
| TB-020 | widgets | id (uuid), dashboard_id (fk), widget_type (enum: chart/kpi/table/heatmap), config_json (jsonb), query_id (fk, optional) | Store widget config (size, position, query binding) |
| TB-021 | widget_instances | id (uuid), widget_id (fk), dashboard_id (fk), grid_x, grid_y, grid_w, grid_h, updated_at | Store widget placement on dashboard |
| TB-022 | report_schedules | id (uuid), project_id (fk), recipient_email (str), frequency (enum: daily/weekly/custom), day_of_week (int, 0–6), time (time), report_type (enum: daily/weekly/sprint/release/custom), enabled (bool), last_run_at, next_run_at, created_at | Store scheduled report subscriptions |
| TB-023 | saved_queries | id (uuid), project_id (fk), owner_id (fk), name (str), sql_text (text), category (str), created_at, updated_at | Store custom warehouse queries (reusable) |
| TB-024 | saved_reports | id (uuid), project_id (fk), owner_id (fk), name (str), query_id (fk), export_format (enum: pdf/xlsx), permissions (enum: public/project/private), created_at, updated_at | Store saved report definitions + sharing rules |
| TB-025 | report_versions | id (uuid), saved_report_id (fk), version_num (int), data_snapshot (jsonb), generated_at, created_by_id (fk) | Store report run snapshots (for audit + re-export) |
| TB-026 | dashboard_permissions | id (uuid), dashboard_id (fk), user_id (fk), permission_level (enum: viewer/editor/owner), created_at | Store dashboard sharing (per-user) |
| TB-027 | warehouse_syncs | id (uuid), sync_id (str), last_sync_at (timestamp), rows_extracted (int), rows_loaded (int), error_message (text, nullable), status (enum: pending/running/success/failed) | Track ETL health + performance |

### Modified Tables

| Table | Column Changes | Rationale |
| --- | --- | --- |
| feature_flags | Add reports.warehouse_duckdb (bool, default false), reports.custom_dashboards (bool), reports.pdf_export (bool), reports.xlsx_export (bool), reports.scheduled_email (bool), ga.external_signup (bool) | M6-specific feature flags for gradual rollout |
| users | Add warehouse_access_role (enum: none/viewer/analyst/admin, default viewer) | Control user access to custom SQL / saved queries |

### DuckDB Warehouse Schema (Separate Instance)

-- Fact Tables
CREATE TABLE warehouse_test_results (
    run_id UUID,
    case_id UUID,
    result_status VARCHAR, -- PASS, FAIL, SKIP
    tester_id UUID,
    environment VARCHAR,
    sprint VARCHAR,
    passed_at TIMESTAMP,
    duration_ms INT,
    project_id UUID
);

CREATE TABLE warehouse_defects (
    defect_id UUID,
    category VARCHAR, -- App, Test, Flaky, Env
    found_by_id UUID,
    assigned_to_id UUID,
    severity VARCHAR,
    status VARCHAR,
    created_date DATE,
    closed_date DATE,
    project_id UUID
);

-- Dimension Tables
CREATE TABLE warehouse_date_dim (
    date_id INT,
    date DATE,
    year INT,
    month INT,
    day INT,
    week INT,
    quarter INT,
    day_of_week VARCHAR
);

CREATE TABLE warehouse_project_dim (
    project_id UUID,
    project_name VARCHAR,
    jira_key VARCHAR,
    created_date DATE
);

-- Indexes for fast aggregation
CREATE INDEX idx_results_project_date ON warehouse_test_results(project_id, passed_at);
CREATE INDEX idx_results_tester_status ON warehouse_test_results(tester_id, result_status);
CREATE INDEX idx_defects_project_date ON warehouse_defects(project_id, created_date);

## 7. API CONTRACTS

### New Endpoints (M6)

| EP-ID | Path | Method | Purpose | Auth Required | Async |
| --- | --- | --- | --- | --- | --- |
| EP-061 | /api/dashboards | GET | List dashboards (project-scoped) | Yes (viewer+) | No |
| EP-062 | /api/dashboards | POST | Create dashboard | Yes (lead+) | No |
| EP-063 | /api/dashboards/:id | GET | Fetch dashboard + widgets | Yes (viewer+) | No |
| EP-064 | /api/dashboards/:id | PATCH | Update dashboard layout/config | Yes (editor+) | No |
| EP-065 | /api/dashboards/:id/permissions | GET | List share permissions | Yes (owner+) | No |
| EP-066 | /api/dashboards/:id/permissions | POST | Add/update user permission | Yes (owner+) | No |
| EP-067 | /api/widgets | POST | Add widget to dashboard | Yes (editor+) | No |
| EP-068 | /api/widgets/:id | PATCH | Update widget config/query | Yes (editor+) | No |
| EP-069 | /api/widgets/:id | DELETE | Remove widget from dashboard | Yes (editor+) | No |
| EP-070 | /api/warehouse/query | POST | Execute custom warehouse query | Yes (analyst+) | No |
| EP-071 | /api/warehouse/health | GET | Warehouse sync health + metrics | Yes (admin+) | No |
| EP-072 | /api/cohort-analysis | POST | Generate cohort heatmap data | Yes (lead+) | No |
| EP-073 | /api/traceability-matrix | POST | Generate RTM XLSX/PDF | Yes (lead+) | Yes (Hatchet job) |
| EP-074 | /api/quality-kpi | GET | Fetch KPI metrics (DPPM, DRE, yield, MTBF) | Yes (lead+) | No |
| EP-075 | /api/reports/export | POST | Export report to PDF/XLSX | Yes (viewer+) | Yes (Hatchet job) |
| EP-076 | /api/reports/export/:job_id | GET | Poll export job status + download link | Yes (viewer+) | No |
| EP-077 | /api/report-schedules | GET | List scheduled reports (project-scoped) | Yes (lead+) | No |
| EP-078 | /api/report-schedules | POST | Create/update email report schedule | Yes (lead+) | No |
| EP-079 | /api/report-schedules/:id | DELETE | Disable schedule | Yes (lead+) | No |
| EP-080 | /api/report-schedules/:id/test-send | POST | Send test email preview | Yes (lead+) | No |
| EP-081 | /api/saved-queries | GET | List custom warehouse queries | Yes (analyst+) | No |
| EP-082 | /api/saved-queries | POST | Save custom warehouse query | Yes (analyst+) | No |
| EP-083 | /api/saved-reports | GET | List saved report definitions | Yes (viewer+) | No |
| EP-084 | /api/saved-reports | POST | Save report + sharing rules | Yes (lead+) | No |
| EP-085 | /api/saved-reports/:id | PATCH | Update saved report | Yes (editor+) | No |
| EP-086 | /api/saved-reports/:id/permissions | GET/POST | Share saved report | Yes (owner+) | No |

### Modified Endpoints (M6)

| EP-ID | Path | Changes |
| --- | --- | --- |
| EP-053 | /api/dashboards/exec | Now backed by warehouse queries (cached); add warehouse_refresh_at timestamp to response |
| EP-076 | /api/reports/* | Extend to support PDF/XLSX format parameter + streaming download |

## 8. FEATURE FLAGS

| Flag Name | Default | Purpose | Rollout Strategy |
| --- | --- | --- | --- |
| reports.warehouse_duckdb | false | Enable DuckDB warehouse instance | Enabled for internal pilots week 1; external customers week 3 (after validation) |
| reports.custom_dashboards | false | Enable dashboard builder UI | Enabled week 2; internal pilots first |
| reports.cohort_analysis | false | Enable cohort heatmap analysis | Enabled week 3; measure adoption |
| reports.traceability_matrix | false | Enable RTM export (XLSX/PDF) | Enabled week 3; test with 50K+ cases first |
| reports.quality_kpi | false | Enable DPPM/DRE/yield/MTBF dashboard | Enabled week 3 |
| reports.pdf_export | false | Enable PDF export for dashboards + reports | Enabled week 4 after Playwright validation |
| reports.xlsx_export | false | Enable XLSX export | Enabled week 4 |
| reports.scheduled_email | false | Enable email report scheduling | Enabled week 4; test with 10 schedules |
| reports.saved_report_library | false | Enable saved reports + sharing | Enabled week 4 |
| ga.external_signup | false | FINAL GA SWITCH — allow external customers to sign up | Enabled 2026-09-21 EOD after sign-off |

## 9. 5-WEEK PLAN

### Week 1 (Aug 17–23): Warehouse Bootstrap + ETL

| Day | Task | Owner | Outcome |
| --- | --- | --- | --- |
| Mon–Tue | Provision DuckDB + design schema | Backend Eng | Schema approved; instance deployed; test data loaded |
| Tue–Wed | Build Python ETL worker (incremental sync) | Backend Eng | Hourly job running; incremental sync validated |
| Wed–Thu | Implement 10 baseline queries | Data Eng | Queries optimized; EXPLAIN ANALYZE passed; <2s p95 |
| Thu–Fri | Build warehouse health dashboard | Backend Eng | Health dashboard live; monitoring alerts configured |
| Fri | E2E test ETL pipeline (100 test runs, 50 defects) | QA | Zero data loss; 100% sync success; idempotency validated |

Exit Gate: Warehouse queries returning correct data in <2s; no ETL failures in 24h run.

### Week 2 (Aug 24–30): Dashboard Builder + Widget Library

| Day | Task | Owner | Outcome |
| --- | --- | --- | --- |
| Mon–Tue | Design + implement dashboard storage schema | Backend Eng | TB-019, TB-020, TB-021 migrated; CRUD endpoints live |
| Tue–Wed | Build React dashboard editor (TanStack React Grid) | Frontend Eng | Drag-drop working; grid layout persists; add/remove widgets |
| Wed–Thu | Implement 4 widget types (chart, KPI, table, heatmap) | Frontend Eng | All widgets render; wire to warehouse queries; performance test (50 widgets) |
| Thu | Dashboard sharing (permissions, public/project/private) | Backend Eng | Dashboard permission checks enforced; sharing UI works |
| Fri | Performance validation (p95 <2s for 50+ widgets) | QA | Caching strategy validated; latency budget met |

Exit Gate: Custom dashboard live; all 4 widget types working; p95 <2s with 100K rows.

### Week 3 (Aug 31–Sep 6): Cohort + Traceability + Quality KPI

| Day | Task | Owner | Outcome |
| --- | --- | --- | --- |
| Mon–Tue | Cohort analysis query + heatmap rendering | Data Eng + Frontend | Heatmap interactive; drill-down to individual results |
| Tue–Wed | Traceability Matrix query (Req → Case → Run → Defect) | Data Eng | Query joins all tables; returns complete coverage matrix |
| Wed–Thu | RTM XLSX exporter + PDF renderer | Backend Eng | XLSX + PDF exports tested; 5K-row matrix completes in <30s |
| Thu–Fri | Quality KPI dashboard (DPPM, DRE, yield, MTBF) | Frontend + Data Eng | All 4 KPIs calculated; card grid + time-series chart renders |
| Fri | Validation: Cohort + RTM + QKI with pilot data | QA | Data accuracy verified; drill-down tested; exports validated |

Exit Gate: Cohort, RTM, Quality KPI dashboards live; all exports functional.

### Week 4 (Sep 7–13): PDF/XLSX Export + Scheduled Email + Report Library

| Day | Task | Owner | Outcome |
| --- | --- | --- | --- |
| Mon–Tue | PDF export (Playwright integration + templates) | Backend Eng | Dashboard → PDF rendering working; watermark + footer applied |
| Tue–Wed | XLSX export (exceljs, multi-sheet, formatting) | Backend Eng | Dashboard/Report → XLSX; pivot tables; cell formatting working |
| Wed | Scheduled email job (Hatchet + Resend) | Backend Eng | Email schedules CRUD; cron job triggers; delivery tracked |
| Thu | Report library + sharing (TB-024, TB-026) | Frontend + Backend | Saved reports browsable; permissions enforced; star/favorite |
| Fri | E2E test: Export (PDF/XLSX) + Email delivery (10 schedules) | QA | All exports complete; emails delivered; unsubscribe tested |

Exit Gate: PDF/XLSX exporters live; 10 email schedules running successfully; report library operational.

### Week 5 (Sep 14–20): GA Hardening + Pen-Test Remediation + Accessibility + Go/No-Go

| Day | Task | Owner | Outcome |
| --- | --- | --- | --- |
| Mon | Query optimization (EXPLAIN ANALYZE all M6 queries) | Data Eng | Slow queries optimized; index tuning complete |
| Mon–Tue | Performance profiling (API endpoints, dashboard rendering) | Backend + Frontend | p95 latency budgets validated; bottlenecks resolved |
| Tue–Wed | Security pen-test (external or internal review) | Security / QA | All P0 findings remediated; P1 findings triaged |
| Wed–Thu | Accessibility audit (WCAG 2.1 AA, manual + automated) | Design + QA | All critical failures fixed; conformance report generated |
| Thu | Capacity plan sign-off + incident response runbook review | DevOps + PM + CTO | Document approved; on-call trained |
| Fri | GA Go/No-Go meeting + final sign-off | PM + CTO + Business | Decision: GO or HOLD; GA announcement approved |

Exit Gate: All M0–M6 ACs closed; zero P0 defects; pen-test/accessibility/perf budgets met; GO decision documented.

## 10. TASKS (MS6-T###)

### M6 Task List (55–75 tasks, 20% buffer included)

| Task ID | Title | Owner | Effort (story points) | Week | Dependency |
| --- | --- | --- | --- | --- | --- |
| MS6-T001 | DuckDB instance provisioning + schema design | Backend Eng | 8 | W1 | M5 complete |
| MS6-T002 | ETL worker scaffolding (Python + Hatchet) | Backend Eng | 5 | W1 | MS6-T001 |
| MS6-T003 | Incremental sync logic (since-last-run markers) | Backend Eng | 8 | W1 | MS6-T002 |
| MS6-T004 | Fact table ETL (test_results, defects, evidence) | Backend Eng | 5 | W1 | MS6-T003 |
| MS6-T005 | Dimension table ETL (dates, projects, users) | Backend Eng | 3 | W1 | MS6-T003 |
| MS6-T006 | Baseline query suite (10 queries, optimized) | Data Eng | 8 | W1 | MS6-T001 |
| MS6-T007 | Warehouse health dashboard + monitoring | Backend Eng | 5 | W1 | MS6-T006 |
| MS6-T008 | ETL integration test (100% sync success, idempotency) | QA | 5 | W1 | MS6-T004, T005 |
| MS6-T009 | Dashboard CRUD schema + migrations (TB-019–021) | Backend Eng | 5 | W2 | M5 complete |
| MS6-T010 | Dashboard API endpoints (EP-061–069) | Backend Eng | 8 | W2 | MS6-T009 |
| MS6-T011 | React dashboard editor (TanStack React Grid) | Frontend Eng | 13 | W2 | M5 UI complete |
| MS6-T012 | Widget library scaffolding + config schema | Frontend Eng | 5 | W2 | MS6-T011 |
| MS6-T013 | Line chart widget (recharts) | Frontend Eng | 5 | W2 | MS6-T012 |
| MS6-T014 | KPI card widget (single number + trend) | Frontend Eng | 3 | W2 | MS6-T012 |
| MS6-T015 | Table widget (TanStack Table, sort/filter) | Frontend Eng | 8 | W2 | MS6-T012 |
| MS6-T016 | Heatmap widget (d3/visx) | Frontend Eng | 8 | W2 | MS6-T012 |
| MS6-T017 | Widget query binding + warehouse integration | Backend Eng | 8 | W2 | MS6-T010, T013–016 |
| MS6-T018 | Dashboard sharing permissions (TB-026) | Backend Eng | 5 | W2 | MS6-T010 |
| MS6-T019 | Query caching (Redis, 5-min TTL) | Backend Eng | 5 | W2 | MS6-T017 |
| MS6-T020 | Dashboard performance testing (50+ widgets) | QA | 5 | W2 | MS6-T013–016, T019 |
| MS6-T021 | Cohort analysis query (tester × sprint × pass-rate) | Data Eng | 8 | W3 | MS6-T006 |
| MS6-T022 | Cohort heatmap rendering + drill-down | Frontend Eng | 8 | W3 | MS6-T021 |
| MS6-T023 | Traceability matrix query (Req → Case → Run → Defect) | Data Eng | 8 | W3 | MS6-T006 |
| MS6-T024 | RTM XLSX exporter | Backend Eng | 5 | W3 | MS6-T023 |
| MS6-T025 | RTM PDF exporter (Playwright) | Backend Eng | 5 | W3 | MS6-T023 |
| MS6-T026 | Quality KPI queries (DPPM, DRE, yield, MTBF) | Data Eng | 8 | W3 | MS6-T006 |
| MS6-T027 | Quality KPI dashboard UI (card grid + chart) | Frontend Eng | 5 | W3 | MS6-T026 |
| MS6-T028 | Cohort + RTM + QKI validation (pilot data) | QA | 8 | W3 | MS6-T022, T024–025, T027 |
| MS6-T029 | PDF export integration (Playwright + templates) | Backend Eng | 8 | W4 | M4 report templates |
| MS6-T030 | XLSX export integration (exceljs, streaming) | Backend Eng | 8 | W4 | M4 report templates |
| MS6-T031 | Report scheduling schema + API (TB-022, EP-077–080) | Backend Eng | 8 | W4 | M4 complete |
| MS6-T032 | Email template design (weekly summary, per-project) | Design | 3 | W4 | MS6-T031 |
| MS6-T033 | Resend integration + email job (Hatchet) | Backend Eng | 8 | W4 | MS6-T032 |
| MS6-T034 | Unsubscribe + delivery tracking | Backend Eng | 5 | W4 | MS6-T033 |
| MS6-T035 | Saved report library schema + API (TB-024–025, EP-083–086) | Backend Eng | 8 | W4 | M4 complete |
| MS6-T036 | Report library UI (browsing, filtering, sharing) | Frontend Eng | 8 | W4 | MS6-T035 |
| MS6-T037 | Export job queue + progress tracking | Backend Eng | 5 | W4 | MS6-T029–030 |
| MS6-T038 | E2E test: PDF/XLSX exports + email delivery | QA | 8 | W4 | MS6-T029–030, T033 |
| MS6-T039 | Query performance optimization (EXPLAIN ANALYZE all M6 queries) | Data Eng | 8 | W5 | MS6-T006, T021, T023, T026 |
| MS6-T040 | API latency profiling + optimization | Backend Eng | 8 | W5 | M0–M5 endpoints |
| MS6-T041 | Dashboard rendering performance tuning (virtual scrolling, pagination) | Frontend Eng | 5 | W5 | MS6-T011–016 |
| MS6-T042 | Load test: 20 concurrent users, 10 minute duration | QA | 5 | W5 | MS6-T040–041 |
| MS6-T043 | Security pen-test execution (OWASP top 10) | Security / QA | 13 | W5 | All M6 features |
| MS6-T044 | Pen-test finding remediation (P0 + P1) | Backend Eng + Frontend Eng | 13 | W5 | MS6-T043 |
| MS6-T045 | Pen-test re-test (all fixes verified) | QA | 5 | W5 | MS6-T044 |
| MS6-T046 | WCAG 2.1 AA accessibility audit (automated + manual) | QA + Design | 8 | W5 | M0–M6 UI |
| MS6-T047 | Accessibility failure remediation | Frontend Eng + Design | 8 | W5 | MS6-T046 |
| MS6-T048 | Accessibility conformance report generation | Design | 3 | W5 | MS6-T047 |
| MS6-T049 | Feature flags implementation (reports.*, ga.external_signup) | Backend Eng | 5 | W5 | All M6 features |
| MS6-T050 | Capacity plan documentation (Oracle → Hetzner migration) | DevOps + PM | 5 | W5 | M0–M6 infra |
| MS6-T051 | On-call runbook review + training | DevOps + PM | 3 | W5 | M5 runbook |
| MS6-T052 | GA Go/No-Go decision meeting | PM + CTO + Business | 2 | W5 | MS6-T044, T047, T051 |
| MS6-T053 | GA announcement blog + email approval | Marketing + PM | 5 | W5 | MS6-T052 |
| MS6-T054 | External customer onboarding flow (sign-up, billing onboarding, training) | Product + Support | 8 | W5 | M5 complete + legal |
| MS6-T055 | Support tier definition + SLA documentation | Support + PM | 3 | W5 | MS6-T054 |
| MS6-T056 | Status page setup (Statuspage.io or Upstash) | DevOps | 3 | W5 | M0 infra |
| MS6-T057 | Legal + compliance sign-off (privacy policy, ToS, GDPR, SOC2 readiness) | Legal + PM | 5 | W5 | M5 complete |
| MS6-T058 | Marketing site update (pricing, GA features, case studies) | Marketing + PM | 8 | W5 | MS6-T053 |
| MS6-T059 | Pilot feedback synthesis + documentation | Product | 3 | W5 | M5 pilot data |
| MS6-T060 | Release notes draft (M0–M6 feature summary) | PM + Eng | 3 | W5 | All milestones |

Total Effort: 60–70 story points equivalent; ~20 FTE across 5 weeks with parallelization.

## 11. ACCEPTANCE CRITERIA (MS6-AC###)

### M6 Acceptance Criteria (50–65 criteria)

| AC-ID | Title | Definition of Done | Owner | Week |
| --- | --- | --- | --- | --- |
| MS6-AC001 | DuckDB warehouse deployed | Instance running on Oracle Always Free; schema migrated; test data loaded; <500ms query latency achieved | Backend | W1 |
| MS6-AC002 | Hourly ETL running successfully | Hatchet job triggers every hour; 100% sync success rate measured over 24h; idempotency validated (re-run same hour = no duplicates) | Backend + QA | W1 |
| MS6-AC003 | Baseline queries optimized | All 10 queries use indexed scans; EXPLAIN ANALYZE shows <100ms execution time; p95 <2s with 1M rows | Data Eng + QA | W1 |
| MS6-AC004 | Warehouse health dashboard live | Displays row count, last sync time, error count, sync duration; alerts configured for >5min delay or sync failure | Backend | W1 |
| MS6-AC005 | Dashboard creation working | User can create new dashboard; drag-drop layout persists; add/remove widgets without errors | Frontend | W2 |
| MS6-AC006 | All 4 widget types render | Line chart, KPI card, table, heatmap all render correctly with sample data; dark/light mode parity | Frontend | W2 |
| MS6-AC007 | Widget-query binding functional | Widget config selects predefined warehouse query; query executes on widget load; data renders in <2s | Backend + Frontend | W2 |
| MS6-AC008 | Dashboard sharing enforced | Viewer cannot edit; editor cannot change permissions; permission checks tested for all roles | Backend | W2 |
| MS6-AC009 | Dashboard p95 latency <2s | 50 widgets on one dashboard loads in <2s; caching strategy validated; no N+1 queries | Frontend + Data Eng + QA | W2 |
| MS6-AC010 | Cohort analysis query returns correct data | Cohort query groups by tester/sprint; pass_rate calculation verified; total rows match warehouse_test_results | Data Eng + QA | W3 |
| MS6-AC011 | Cohort heatmap interactive | Click cell → drill-down to individual results; cell colour represents pass rate; WCAG contrast ≥4.5:1 | Frontend + QA | W3 |
| MS6-AC012 | Traceability matrix query complete | Query joins requirements → test_cases → test_results → defects; coverage % calculated correctly | Data Eng + QA | W3 |
| MS6-AC013 | RTM XLSX export functional | Export completes in <30s for 5K rows; multi-sheet format correct; cell formatting (headers bold, currency, %) applied | Backend + QA | W3 |
| MS6-AC014 | RTM PDF export functional | PDF renders in <5s; watermark + footer applied; file size <10MB for 5K rows | Backend + QA | W3 |
| MS6-AC015 | Quality KPI calculations correct | DPPM = (defects × 1e6) / test_results; DRE = closed_by_qa / (closed_by_qa + found_in_prod); yield = unique_cases / runs; MTBF = uptime / defects | Data Eng + QA | W3 |
| MS6-AC016 | Quality KPI dashboard renders | Card grid (4 KPIs) + time-series chart (30-day trend); all KPIs visible without scrolling on 1920×1080 | Frontend + QA | W3 |
| MS6-AC017 | PDF export templates render | Dashboard/Report → PDF includes page break, header/footer, watermark, date; file downloads to user browser | Backend | W4 |
| MS6-AC018 | XLSX export multi-sheet working | Dashboard/Report → XLSX includes Summary sheet + Details sheet + Charts sheet (embedded images); file size <50MB | Backend | W4 |
| MS6-AC019 | Email schedule CRUD working | Create/update/delete schedules via UI; schedule persists in DB; test-send button sends preview email | Backend + Frontend | W4 |
| MS6-AC020 | Hatchet cron job triggers correctly | 10 schedules created; cron fires at expected times; email sent within 5min of trigger time | Backend + QA | W4 |
| MS6-AC021 | Email delivery tracked | Resend webhook updates sent/bounced/opened events; unsubscribe link included; tracking dashboard shows delivery rate | Backend | W4 |
| MS6-AC022 | Saved report library operational | User can save report definition; browse library; filter by project/owner; pagination works for 100+ reports | Frontend + Backend | W4 |
| MS6-AC023 | Report sharing permissions enforced | Owner can share; viewer cannot edit; editor cannot share; permission revocation immediate | Backend | W4 |
| MS6-AC024 | Export job queue scalable | Export 10 PDFs concurrently; all complete without timeout; progress bar updates in real-time | Backend + QA | W4 |
| MS6-AC025 | All query optimizations applied | EXPLAIN ANALYZE shows index scans (no table scans); slow query log empty for M6 queries; database stats up-to-date | Data Eng + QA | W5 |
| MS6-AC026 | API p95 latency <300ms | All authenticated endpoints (EP-061–086) measured over 28 days; p95 <300ms; p99 <1000ms | Backend + QA | W5 |
| MS6-AC027 | Dashboard rendering p95 <2s | 100K rows in table; heatmap with 1000+ cells; all render in <2s with pagination/virtual scrolling | Frontend + QA | W5 |
| MS6-AC028 | Load test passed | 20 concurrent users for 10 minutes; error rate <2%; p95 latency <2s for dashboard queries | QA | W5 |
| MS6-AC029 | All P0 pen-test findings remediated | Pen-test identified 0 critical vulnerabilities remaining; all P0 findings fixed and re-tested | Security + Backend | W5 |
| MS6-AC030 | All P1 pen-test findings triaged | P1 findings risk-accepted or scheduled for v1.5; documented in risk register | Security + PM | W5 |
| MS6-AC031 | WCAG 2.1 AA audit passed | Automated audit (axe, Lighthouse) passes 100%; manual testing with NVDA/JAWS passes; conformance report generated | QA + Design | W5 |
| MS6-AC032 | All critical accessibility failures resolved | Colour contrast ≥4.5:1 for all text; alt text present for all images; form labels associated; keyboard navigation works | Frontend + Design | W5 |
| MS6-AC033 | Feature flags operational | All 9 flags (reports.*, ga.external_signup) toggle without redeployment; feature states logged; rollout tested | Backend | W5 |
| MS6-AC034 | Capacity plan documented | Oracle Always Free limits documented; Hetzner CX32 warm standby plan written; scale trigger thresholds defined | DevOps + PM | W5 |
| MS6-AC035 | On-call runbook reviewed | 5+ runbooks for P0–P2 scenarios (Gemma offline, pgvector full, Oracle failure, etc.); on-call trained and signed-off | DevOps | W5 |
| MS6-AC036 | Incident response runbook executed | Dry-run incident (e.g., simulate warehouse query failure); team responds <30min; post-mortem documented | DevOps + Eng | W5 |
| MS6-AC037 | Privacy policy + ToS reviewed | Legal review complete; GDPR assessment done; data retention policy defined (1y logs, 90d audit, 7y PII-stripped) | Legal | W5 |
| MS6-AC038 | SOC2 readiness checkpoint | Audit log immutability confirmed; change control process documented; monitoring dashboards live | DevOps | W5 |
| MS6-AC039 | GA go/no-go decision documented | Meeting held 2026-09-20; decision (GO or HOLD) signed off by PM + CTO + Business; blockers documented if HOLD | PM | W5 |
| MS6-AC040 | GA announcement approved | Blog post + email draft approved by marketing + PM; social media calendar prepared; launch timeline confirmed | Marketing | W5 |
| MS6-AC041 | External onboarding flow ready | Sign-up form live; email verification working; default project created; training materials accessible | Product + Support | W5 |
| MS6-AC042 | Support tier SLAs defined | Bronze/Silver/Gold defined (response time, availability, features); pricing (if applicable) aligned with billing | Support + PM | W5 |
| MS6-AC043 | Status page live | Statuspage.io or Upstash configured; component statuses update automatically; public access enabled | DevOps | W5 |
| MS6-AC044 | M0–M5 ACs closure verified | Spot-check: ≥10 random M0–M5 ACs re-verified for continued compliance; any regressions documented | QA | W5 |
| MS6-AC045 | Zero P0 defects for ≥7 days | No critical/blocker defects open from 2026-08-17–2026-09-20 | QA | W5 |
| MS6-AC046 | Pilot feedback incorporated | ≥5 pilot feature requests reviewed; ≥80% resolved or documented in v1.5 roadmap | Product | W5 |
| MS6-AC047 | Documentation complete | API docs (OpenAPI), user guide (5+ pages), admin guide (3+ pages), troubleshooting (FAQ 10+ items) | PM + Eng | W5 |
| MS6-AC048 | Release notes approved | M0–M6 feature summary, migration guide (if needed), known issues, deprecations documented | PM + Eng | W5 |
| MS6-AC049 | Marketing site updated | Homepage mentions M6 features (warehouse, exports, email); pricing page live (if applicable); blog post scheduled | Marketing | W5 |
| MS6-AC050 | Pilot metrics dashboard live | Tracks adoption (login %), defect flow (%), time-to-log-defect, A1 auto-approval rate, ROI value | Product | W5 |

Total ACs: 50 (buffer for ad-hoc discovery ACs = target 50–65).

## 12. RISKS & MITIGATIONS (MS6-R###)

| Risk ID | Title | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- | --- |
| MS6-R001 | Warehouse ETL data skew (e.g., duplicate rows from failed sync retries) | Medium | High | Implement idempotency tokens (sync_id + timestamp); test re-run same hour multiple times; audit logs compare row counts pre/post-sync | Backend Eng |
| MS6-R002 | Dashboard builder perf degrades with large data (100K+ rows) | Medium | High | Implement virtual scrolling (TanStack Table); pagination (limit 1000 rows/page); query-level aggregation (GROUP BY before rendering); load-test with 100K rows in W2 | Frontend Eng + Data Eng |
| MS6-R003 | PDF rendering timeouts (Playwright > 30s for large PDF) | Medium | Medium | Use streaming PDF generation (paginate by 50 rows); set 60s timeout; queue exports to async job; implement progress bar | Backend Eng |
| MS6-R004 | Pen-test finds critical auth/data-exposure vulnerability late (W5) | Low | Critical | Conduct internal security review in W4 (before external pen-test); fix low-hanging fruit early; allocate 2x buffer in W5 for fixes | Security + Backend |
| MS6-R005 | WCAG audit fails critical paths (e.g., dashboard keyboard nav broken) | Medium | High | Run automated checks in W2 (flag CONTRAST issues early); manual testing with NVDA in W3; accessibility champion reviews M6 UI | QA + Design |
| MS6-R006 | Resend email delivery rate <90% (bounces, spam folder) | Low | Medium | Validate DKIM/SPF/DMARC before W4; test email templates with multiple clients (Gmail, Outlook); implement bounce handling + retry | Backend Eng |
| MS6-R007 | External pen-test unavailable on schedule (budget/resource constraint) | Low | High | Plan internal code review as fallback (W4 budget); prioritise OWASP top 10 manually; defer P2 findings to v1.5 if pen-test delayed | Security |
| MS6-R008 | Capacity plan miscalculation (Oracle Always Free hits ceiling before W5) | Low | High | Monitor DuckDB size + pgvector row count daily; trigger Hetzner warm-standby activation at 70% capacity; document migration runbook in W1 | DevOps |
| MS6-R009 | GA launch delayed by pending legal review (ToS/privacy/GDPR) | Medium | High | Start legal review in W1 (parallel to dev); use template language (SOC2 ready, GDPR compliance by design); brief legal weekly | PM + Legal |
| MS6-R010 | Pilot customers demand v1.5 features (A3/A5) before GA launch | Low | Medium | Document deferred features in roadmap; set expectations in GA announcement; commit to v1.5 timeline (Q4 2026) | PM |

## 13. TESTING & QA

### Test Strategy (M6)

| Test Level | Scope | Responsible | Approach |
| --- | --- | --- | --- |
| Unit Tests | ETL jobs, query functions, widget configs | Backend/Data Eng | pytest (Python), Jest (JavaScript); ≥80% coverage for M6-specific code |
| Integration Tests | Warehouse ↔ API ↔ Frontend; email delivery | Backend + QA | Hatchet job test harness; in-memory DuckDB; Resend mock; multi-service orchestration |
| E2E Tests | Dashboard CRUD, export (PDF/XLSX), email send | QA + Frontend | Playwright; 3 critical journeys (create dashboard → add widget → export PDF; save report → schedule email; view cohort → drill-down) |
| Performance Tests | Dashboard rendering (50+ widgets), query latency, PDF generation | QA + Data Eng | Artillery.io (load test), Chrome DevTools (RUM), EXPLAIN ANALYZE; SLO validation |
| Security Tests | Pen-test, SAST, SCA, API abuse | Security + QA | OWASP ZAP (automated), manual pen-test (external), GitHub Dependabot (SCA), rate-limit fuzzing |
| Accessibility Tests | WCAG 2.1 AA (automated + manual) | QA + Design | axe DevTools, Lighthouse, manual testing with NVDA/JAWS, keyboard navigation audit |
| Data Validation | ETL correctness, query accuracy, export fidelity | QA + Data Eng | Row count audit (pre/post-sync), sample data spot-checks, export file format validation |

### Defect Targets

- P0 (Blocker): Zero defects 7 days before GA launch

- P1 (Critical): ≤2 open (risk-accepted or scheduled for v1.5)

- P2 (Major): ≤5 open (documented in known issues)

- P3 (Minor): No limit (defer to v1.5)

## 14. GA READINESS CHECKLIST

Final Gate (2026-09-20, EOD):

- ☐ All M0–M6 ACs closed (verified via checklist in AC section)

- ☐ Zero P0/P1 defects open for ≥7 days

- ☐ Pen-test findings (all P0) remediated + re-tested

- ☐ Accessibility audit WCAG 2.1 AA passes (100% critical paths)

- ☐ p95 latency budgets met (API <300ms, dashboard <2s, doc gen <60s)

- ☐ Load test passed (20 users, 10 min, <2% error rate)

- ☐ Capacity plan signed off (DevOps + PM + CTO)

- ☐ External customer contract templates ready (legal review complete)

- ☐ Billing/metering system decision (shipped or deferred to v1.5 if no paid customers)

- ☐ Support tier definitions published (SLA, features, pricing if applicable)

- ☐ Status page live + monitored

- ☐ Incident response runbook reviewed + on-call trained

- ☐ GA announcement blog + email draft approved

- ☐ Release notes approved

- ☐ Documentation complete + published

- ☐ Pilot metrics dashboard live

- ☐ Go/No-Go meeting held + decision documented

- ☐ GA LAUNCH APPROVAL SIGNED (PM + CTO + Business)

If GO: Enable ga.external_signup flag EOD 2026-09-21; announce GA.

If HOLD: Document blockers; commit to re-evaluation date; communicate delay to stakeholders.

## 15. ROLLBACK & FALLBACK PLANS

### Fallback for Warehouse ETL Failure

Scenario: DuckDB becomes unavailable or ETL fails for >1 hour.

Fallback Strategy: 1. Disable reports.warehouse_duckdb flag 2. All report/dashboard queries fall back to live Postgres aggregates (slower but functional) 3. Dashboards show stale data (last-sync timestamp visible) but don’t error 4. Notify users in banner: “Warehouse under maintenance; refresh every 5 minutes” 5. SRE initiates DuckDB recovery (check disk space, query log for hanging queries, restart Ollama if dependent) 6. Re-enable flag once health check passes

RTO: <30 minutes
Data Loss: None (incremental ETL resumes from last sync marker)

### Fallback for Pen-Test Findings (P0)

Scenario: External pen-test discovers critical vulnerability 48h before GA launch.

Fallback Strategy: 1. Halt GA launch (HOLD decision in Go/No-Go) 2. Assemble incident response team (Backend + Security + PM) 3. Remediate within 24h; full re-test within 48h 4. Re-evaluate GA launch decision 5. If fix not possible: disable affected feature flag; document workaround; defer to v1.5

Acceptance: P0 findings must be remediated; cannot ship GA with P0 open.

### Fallback for Accessibility Audit Failure

Scenario: WCAG 2.1 AA audit reveals critical path inaccessible (e.g., dashboard editor keyboard nav broken).

Fallback Strategy: 1. Mark feature as Beta (feature flag reports.custom_dashboards → false by default) 2. Only enable for internal pilots; external customers see warning 3. Schedule fix for v1.5; commit to timeline in GA announcement 4. Ship GA with templated dashboards only (no custom builder)

Acceptance: If dashboard builder not fixed, ship without it; all other M6 features ship.

### Fallback for Capacity Constraint

Scenario: Oracle Always Free VM hits resource ceiling (4 OCPU, 24GB) in W4.

Fallback Strategy: 1. Migrate DuckDB to warm-standby Hetzner CX32 ($7.40/mo) 2. PostgreSQL remains on Oracle; DuckDB syncs via secure tunnel 3. No code changes; containerised deployment seamlessly switches infrastructure 4. Update capacity plan + incident runbook 5. Monitor Hetzner metrics; plan scale to CX52 if >80% utilisation

RTO: <2 hours
GA Impact: None (migration transparent to users)

## 16. DEPENDENCIES & HANDOFFS

### External Dependencies

| Dependency | Owner | Status | Mitigation |
| --- | --- | --- | --- |
| Pen-test vendor availability (W5) | External security firm | Assumed available | Book slot in advance; fallback to internal review |
| Resend email service (W4) | Resend | Stable (production) | Rate-limit awareness; fallback to SendGrid if needed |
| Playwright/Chromium reliability (W4) | Microsoft/community | Stable (open-source) | Fallback to PDF.co API for rendering |
| Hetzner infrastructure (warm standby) | Hetzner | Assumed available | Account pre-provisioned; terraform code ready |
| Legal review of ToS/privacy (W5) | Internal/external legal | TBD | Start in W1 to avoid W5 bottleneck |

### Internal Handoffs

| Handoff | From | To | Artifact | Timing |
| --- | --- | --- | --- | --- |
| DuckDB schema + ETL design review | Backend Eng | Data Eng | Detailed schema doc + query patterns | EOD W1 |
| Dashboard builder mockups | Design | Frontend Eng | Figma file + interaction spec | EOD W2 |
| Performance tuning results | Frontend + Data Eng | QA | Optimisation report + benchmark data | EOD W4 |
| Pen-test findings | Security | Backend Eng | Vulnerability report (CVSS scores) | EOD W5 |
| Accessibility audit results | QA + Design | Frontend Eng | AODA report + remediation checklist | EOD W5 |
| Go/No-Go decision | PM + CTO | Business | Decision document + launch timeline | 2026-09-20 EOD |

## 17. SUCCESS METRICS

### KPIs (M6 Exit)

| Metric | Target | Baseline | Measurement |
| --- | --- | --- | --- |
| Warehouse query p95 latency | <2 s | — | SigNoz dashboard (28-day rolling) |
| Dashboard rendering p95 latency | <2 s | — | RUM + Playwright test |
| PDF export completion rate | ≥99% | — | Success/failure logs (Hatchet) |
| Email delivery rate | ≥95% | — | Resend webhook events |
| Pen-test P0 findings | 0 | — | Re-test report |
| WCAG 2.1 AA audit | 100% pass on critical paths | — | Automated + manual report |
| Load test error rate | <2% | — | Artillery.io final report |
| Capacity utilisation (Oracle VM) | <70% at launch | — | CloudWatch metrics |

### Business Outcomes (Post-GA)

| Metric | 30-Day Target | 90-Day Target |
| --- | --- | --- |
| External customer sign-ups | ≥5 | ≥15 |
| Weekly active users (new cohort) | ≥20 | ≥50 |
| Defect flow rate (QA Nexus → Jira) | ≥70% | ≥85% |
| Time-to-log-defect (median) | ≤90 s | ≤60 s |
| ROI dashboard usage | ≥60% of leads | ≥80% |
| Customer NPS (pilot feedback) | ≥50 | ≥65 |

## 18. GLOSSARY

| Term | Definition |
| --- | --- |
| DuckDB | Columnar SQL database for OLAP; embedded or standalone; ideal for analytics warehouse |
| ETL | Extract-Transform-Load; pipeline moving data from Postgres (OLTP) to DuckDB (OLAP) |
| Hatchet | Task queue + job scheduler; orchestrates async work (doc gen, ETL, email sends) |
| Resend | Email service API; handles transactional + bulk email with delivery tracking |
| Playwright | Browser automation + headless rendering; used for PDF export of dashboards |
| recharts | React charting library; composable, accessible, dark-mode-ready |
| TanStack Table | Headless React table library; sortable, filterable, virtual-scrolling |
| TanStack React Grid | Draggable grid layout for dashboard builder |
| DPPM | Defects Per Million (test-case executions); quality KPI |
| DRE | Defect Removal Efficiency; % of defects caught before production |
| MTBF | Mean Time Between Failures; reliability metric |
| RTM | Requirements Traceability Matrix; links requirements → test cases → results → defects |
| Cohort Analysis | Grouping users/testers by dimension (sprint, tester, environment) to compare metrics |
| Feature Flag | Runtime toggle enabling/disabling features without redeployment |
| GA | General Availability; production-ready, external customers supported |
| SRE | Site Reliability Engineer; owns production health, incident response |
| WCAG 2.1 AA | Web Content Accessibility Guidelines level AA; 4.5:1 contrast minimum, keyboard navigation required |
| Pen-Test | Penetration test; security assessment by skilled attacker; identifies vulnerabilities |
| OWASP Top 10 | Open Web Application Security Project; 10 most critical web vulnerabilities |

## APPENDIX A: WAREHOUSE QUERY EXAMPLES

-- Example 1: Daily Pass Rate Trend
SELECT 
    DATE(passed_at) as date,
    COUNT(*) as total_runs,
    SUM(CASE WHEN result_status = 'PASS' THEN 1 ELSE 0 END) as passed,
    ROUND(100.0 * SUM(CASE WHEN result_status = 'PASS' THEN 1 ELSE 0 END) / COUNT(*)) as pass_rate
FROM warehouse_test_results
WHERE project_id = $1
GROUP BY DATE(passed_at)
ORDER BY date DESC
LIMIT 30;

-- Example 2: Defect by Category (Last 30 Days)
SELECT 
    category,
    COUNT(*) as count,
    ROUND(100.0 * COUNT(*) / SUM(COUNT(*)) OVER ()) as pct
FROM warehouse_defects
WHERE project_id = $1 AND created_date >= CURRENT_DATE - 30
GROUP BY category
ORDER BY count DESC;

-- Example 3: Cohort Analysis (Tester × Sprint)
SELECT 
    w.tester_id,
    w.sprint,
    COUNT(*) as total_runs,
    SUM(CASE WHEN w.result_status = 'PASS' THEN 1 ELSE 0 END) as passed,
    ROUND(100.0 * SUM(CASE WHEN w.result_status = 'PASS' THEN 1 ELSE 0 END) / COUNT(*)) as pass_rate
FROM warehouse_test_results w
WHERE w.project_id = $1
GROUP BY w.tester_id, w.sprint
ORDER BY w.sprint DESC, pass_rate DESC;

-- Example 4: DPPM (Defects Per Million)
SELECT 
    project_id,
    COUNT(DISTINCT defect_id) as defect_count,
    COUNT(*) as total_runs,
    ROUND(COUNT(DISTINCT defect_id) * 1.0e6 / COUNT(*)) as dppm
FROM warehouse_test_results
WHERE project_id = $1
GROUP BY project_id;

## APPENDIX B: FEATURE FLAG ROLLOUT SCHEDULE

| Week | Flag | Enabled For | Validation Gate |
| --- | --- | --- | --- |
| W1 | (none) | — | — |
| W2 | reports.warehouse_duckdb | Internal pilots | ETL 100% success over 24h |
| W2 | reports.custom_dashboards | Internal pilots | Dashboard rendering <2s, 50 widgets tested |
| W3 | reports.cohort_analysis | Internal pilots | Heatmap drill-down validated with pilot data |
| W3 | reports.traceability_matrix | Internal pilots | RTM export tested with 5K+ cases |
| W3 | reports.quality_kpi | Internal pilots | KPI calculations verified against manual calc |
| W4 | reports.pdf_export | Internal pilots | 10 PDFs tested; rendering <30s |
| W4 | reports.xlsx_export | Internal pilots | 5 XLSXs tested; multi-sheet format correct |
| W4 | reports.scheduled_email | Internal pilots | 10 schedules running; delivery rate >95% |
| W4 | reports.saved_report_library | Internal pilots | Library browsing + sharing tested |
| W5 | (none, pre-GA validation) | — | Pen-test + accessibility audit completion |
| W5 (EOD) | ga.external_signup | All | GO decision made + signed off |

## APPENDIX C: SAMPLE GO/NO-GO CHECKLIST (2026-09-20)

Conducted by: PM + CTO + Business
Attendees: Backend Lead, Data Eng, Frontend Lead, QA Lead, DevOps, Legal, Support
Duration: 1 hour

### Questions

- All M0–M6 ACs closed? ✓ (verify against AC checklist)

- Zero P0 defects for ≥7 days? ✓ (query defect tracking system; last P0 closed 2026-09-20)

- Pen-test findings remediated (P0) or risk-accepted (P1)? ✓ (1 P0 fixed; 2 P1 documented in known issues)

- WCAG 2.1 AA audit passed? ✓ (100% critical paths; 3 minor issues documented for v1.5)

- p95 latency budgets met? ✓ (API 250ms, dashboard 1.8s, doc gen 45s)

- Load test passed? ✓ (20 users, 10 min, 1.2% error rate)

- Capacity plan signed off? ✓ (DevOps green-light; Hetzner standby provisioned)

- External customer onboarding ready? ✓ (sign-up flow tested; training materials final)

- Support tier SLAs defined? ✓ (Bronze/Silver/Gold published)

- Incident response runbook reviewed? ✓ (on-call trained; dry-run executed)

- GA announcement approved? ✓ (blog + email final; social calendar scheduled)

### Decision

VOTE: - PM: GO - CTO: GO - Business: GO

Outcome: GO FOR GA LAUNCH
Effective Date: 2026-09-21 EOD
Action: Enable ga.external_signup flag; publish announcement.

End of Milestone M6 Document

## Document Metadata

| Property | Value |
| --- | --- |
| Document ID | M6–FULL-REPORTS-GA-v1.0 |
| Created | 2026-04-21 |
| Last Updated | 2026-04-21 |
| Status | Draft (Ready for Handoff) |
| Reviewers | PM (approval pending), CTO (approval pending), Business (approval pending) |
| Version History | 1.0 (initial) |