## Cover
QA Nexus PM1 — Professional Work Log
Effort Evidence, Deliverables & Token-Management ROI
Owner: Yogesh Mohite (Sr QA + Admin) · Iksula Services Pvt Ltd · Reporting to: Akshay Panchal (QA Lead)
Period: 2026-04-17 → 2026-05-05 (19 days) · Report Generated: 2026-05-05 22:28
KEY METRICS AT A GLANCE
Total Hours Logged | Work Sessions | Active Days
59.89 | 57 | 12
Verifiable work effort | Evidence rows supporting effort | Distinct days with logged evidence
TOKEN MANAGEMENT METRICS
Tokens Saved | Token Sessions | Est. Token Cost (USD)
1012400 | 8 | 1829.84
Estimated savings from memory/context flow | Actual telemetry rows tracked | Model-token cost estimate
WORKBOOK NAVIGATION
Sheet Name | Description |  | Records
Consolidated Report | Executive summary, phase breakdown, deliverables, cost posture |  | 8 phases · 57 sessions
Phase Comparison | Formula-backed hours by phase with bar chart |  | 8 rows + chart
Daily Rollup | Latest-first daily hours and trend chart |  | 11 days + chart
All Sessions | Complete evidence log sorted latest first |  | 57 sessions
Token Sessions | Per-session token telemetry sorted latest first |  | 8 tracked sessions
Token Daily Rollup | Formula-backed token daily totals |  | 4 dates
Token Comparison | Worktree-level token rollup with formulas |  | 1 worktree + total
Backfill Notes | Transparent data-quality flags and mitigations |  | 26 entries
Phase Detail Sheets | Idea Confirmation, Test Case Mgmt, Test Automation, Design & Specs, Milestone Planning, Launch Creative, Development, Other |  | 60+ sessions
MANAGEMENT READING NOTES
1. Hours are verifiable work-log evidence. Chat-only research may mean true effort is higher.
2. Token savings are conservative estimates from memory injection and context preloading telemetry.
3. FE/BE token gaps are not hidden; they are listed in Backfill_Notes with mitigation status.
4. All core rollups use formulas so management totals update automatically when new rows are added.
5. Latest records are shown first (descending order) for immediate visibility of recent activity.

## All Sessions
All Sessions — Complete Evidence Log (Latest First)
Every session across every phase, sorted descending by date · 57 sessions · 59.89 verifiable hours
Date | Day | Timing | Hours | Files | Phase | Evidence / Theme | What I Did | Parallel Work (FE+BE)
2026-05-05 | Tuesday | 10:00 AM – 1:00 PM | 3 | 8 | Milestone Planning | M1 close ceremony | M1 close ceremony — Day 9+10 combined. RBAC sweep 54/54 pass. Audit chain env-skip (no local DATABASE_URL). Filed m1-close-report.md (47 PRs, 358 tests, 21/41 frames, $0/month). Pushed tag m1-closed-2026-05-05. Posted m1-closed-announcement. Wrote Day-9+10-combined EOD report. PR #48 fix(web): f27 /admin/users 404 — users-api.ts relative URL fixed to NEXT_PUBLIC_API_BASE_URL (BE wiring was correct; FE bug). Bonus: better-auth pnpm hoist applied.
2026-05-03 |  |  | 7 | 80 | Milestone Planning | M0 close ceremony | M0 close ceremony — Steps A-I + Step E. PRs #21+#22+#23+#24 squash-merged; PR #25 (FE M2) opened as Draft. Followups (t) closed via PR #24, (u)+(v) filed. CLAUDE.md Hard Rule #3 updated for 3-folder frame inventory post Claude Design v2 supersede. M0 completion report at docs/milestones/M0_completion_report.md. 4th halt-to-root-cause pattern codified (refined pre-merge gate: compare PR vs main, only NEW failures gate). 102 commits over M0 window, 17 PASS / 0 FAIL / 2 DEFERRED to M1.5. Final main HEAD 44b06ef.
2026-04-27 | Monday | 10:04 AM – 11:31 AM | 1.68 | 234 | Development | memory.md · api.md · database.md
2026-04-27 | Monday | 10:35 AM – 10:49 AM | 0.5 | 153 | Design & Specifications | QA_Nexus_Tech_Stack.docx · ERD.docx · ERD.drawio
2026-04-27 | Monday | 10:47 AM – 10:49 AM | 0.5 | 248 | Milestone Planning | AUDIT_REMEDIATION_WAVE_3_REPORT.md · FINAL_REVIEW.md · FINAL_REVIEW_MVP_ARCHIVE.md
2026-04-27 | Monday | 1:19 PM – 1:19 PM | 0.5 | 16 | Development | audit-log.sh · report-token-savings.sh · check-secrets.sh
2026-04-27 | Monday | 2:25 PM – 4:12 PM | 2.03 | 49 | Development | token-savings.jsonl · block-dangerous.sh · .gitleaks.toml
2026-04-27 | Monday | 5:58 PM – 8:44 PM | 3 | 143 | Development | settings.local.json · deploy-check.md · sync-worktree.md
2026-04-27 | Monday | 8:55 PM – 9:49 PM | 1.15 | 3 | Other | .~lock.QA_Nexus_Work_Hours_Log.xlsx# · lu1418u8yh.tmp · lu13993vzx.tmp
2026-04-27 | Monday | 9:44 PM – 10:10 PM | 0.68 | 3 | Test Automation & Reporting | BrowserStack AI Agents — Document Finalisation
2026-04-26 | Sunday | 1:17 PM – 2:17 PM | 1.23 | 9 | Launch Creative | qa-nexus-stack-diagram.svg · qa-nexus-stack-animated.html · qa-nexus-stack-logos.svg
2026-04-26 | Sunday | 2:29 PM – 2:29 PM | 0.5 | 574 | Development | e9502cdb · 3a4bb885 · 3147a1e3
2026-04-26 | Sunday | 2:40 PM – 2:42 PM | 0.5 | 4 | Design & Specifications | PRD.md · PRD.md · ERD.md
2026-04-26 | Sunday | 3:45 PM – 3:45 PM | 0.5 | 1 | Milestone Planning | Milestone_M0_Setup_v8.md
2026-04-26 | Sunday | 3:57 PM – 3:58 PM | 0.5 | 2 | Design & Specifications | PM1_ERD.md · PM1_ERD.md
2026-04-26 | Sunday | 5:52 PM – 5:53 PM | 0.5 | 2 | Milestone Planning | Milestone_M5_Automation_Basic_Reports_MVP_Launch.md · Milestone_M5_Automation_Basic_Reports_MVP_Launch.md
2026-04-26 | Sunday | 5:56 PM – 10:20 PM | 4.63 | 126 | Development | .editorconfig · .prettierrc.json · .nvmrc
2026-04-26 | Sunday | 8:43 PM – 8:44 PM | 0.5 | 5 | Design & Specifications | PM1_PRD.md · CLAUDE_KICKOFF_PROMPT.md · 01_SYSTEM.md
2026-04-26 | Sunday | 8:54 PM – 8:54 PM | 0.5 | 1 | Milestone Planning | Milestone_M0_Setup_v8.md
2026-04-25 | Saturday | 11:00 PM – 11:02 PM | 0.5 | 23 | Milestone Planning | Milestone_M1_Users_Roles.md · Milestone_M1_Users_Roles.md · Milestone_M2_Docs_KB.md
2026-04-25 | Saturday | 7:09 PM – 7:09 PM | 0.5 | 72 | Milestone Planning | gantt.png · gantt.png · risk_heatmap.png
2026-04-25 | Saturday | 8:26 AM – 8:26 AM | 0.5 | 2 | Design & Specifications | F14m3 Convert to Jira Story Modal.html · F14m3 Convert to Jira Story Modal.html
2026-04-25 | Saturday | 9:21 PM – 10:43 PM | 1.62 | 20 | Design & Specifications | QA_Nexus_Master_Brainstorm.md · QA_Nexus_Master_Brainstorm.md · project_analysis.md
2026-04-25 | Saturday | 9:22 PM – 9:32 PM | 0.5 | 6 | Milestone Planning | Milestone_M0_Setup.md · Milestone_M0_Setup.md · Milestone_M0_Setup.md
2026-04-25 | Saturday | 9:41 AM – 12:43 PM | 3.27 | 26 | Design & Specifications | F15 Knowledge Base.html · F15 Knowledge Base.html · F16a Test Case Method Chooser.html
2026-04-24 | Friday | 10:46 PM – 10:46 PM | 0.5 | 1 | Development | settings.local.json
2026-04-24 | Friday | 10:46 PM – 10:46 PM | 0.5 | 1 | Other | settings.local.json
2026-04-24 | Friday | 11:11 PM – 12:12 AM | 1.27 | 16 | Design & Specifications | F06b Set Reset Password.html · F06b Set Reset Password.html · F06c Reset Password.html
2026-04-24 | Friday | 11:51 AM – 12:28 PM | 0.87 | 16 | Design & Specifications | 01-home.html · 02-test-cases.html · 03-ai-generator.html
2026-04-24 | Friday | 3:41 PM – 3:41 PM | 0.5 | 2 | Milestone Planning | Milestone_M17_Enterprise_Auth_Slack.md · Milestone_M17_Enterprise_Auth_Slack.md
2026-04-24 | Friday | 6:05 PM – 6:23 PM | 0.55 | 36 | Design & Specifications | F07 First-Run Onboarding.html · F07 First-Run Onboarding.html · F06 Sign In.html
2026-04-24 | Friday | 7:40 PM – 7:40 PM | 0.5 | 2 | Milestone Planning | MILESTONE_REGISTRY.md · MILESTONE_REGISTRY.md
2026-04-24 | Friday | 7:54 PM – 8:27 PM | 0.8 | 4 | Design & Specifications | 05_ANALYSE_AND_GOVERN.md · 05_ANALYSE_AND_GOVERN.md · 02_ENTRY_AND_HOME.md
2026-04-24 | Friday | 9:51 PM – 9:51 PM | 0.5 | 2 | Design & Specifications | PROJECT_UI_DESIGN_TOKENS.json · PROJECT_UI_DESIGN_TOKENS.json
2026-04-23 | Thursday | 10:30 AM – 10:30 AM | 0.5 | 1 | Design & Specifications | MVP_PRD.md
2026-04-23 | Thursday | 11:03 AM – 11:03 AM | 0.5 | 1 | Development | PROJECT_DOCUMENT_AUDIT_REPORT.md
2026-04-23 | Thursday | 11:03 AM – 11:03 AM | 0.5 | 1 | Other | PROJECT_DOCUMENT_AUDIT_REPORT.md
2026-04-23 | Thursday | 11:58 AM – 1:33 PM | 1.82 | 7 | Design & Specifications | PROJECT_UI_UX_REDESIGN.md · PROJECT_UI_FRAME_MAP.md · PROJECT_UI_GENERATION_PROMPT.md
2026-04-23 | Thursday | 12:06 PM – 12:06 PM | 0.5 | 1 | Development | PROJECT_ROADMAP.md
2026-04-23 | Thursday | 12:06 PM – 12:06 PM | 0.5 | 1 | Other | PROJECT_ROADMAP.md
2026-04-23 | Thursday | 12:11 PM – 12:51 PM | 0.92 | 60 | Milestone Planning | SYNC_REPORT_MVP_ARCHIVE.md · SYNC_REPORT_MVP_ARCHIVE.md · Milestone_M10_AI_Product_Tester.md
2026-04-23 | Thursday | 2:54 PM – 2:54 PM | 0.5 | 53 | Design & Specifications | code.html · screen.png · code.html
2026-04-23 | Thursday | 5:59 PM – 6:18 PM | 0.57 | 29 | Design & Specifications | NAVIGATION_CONTRACT.md · F06_Sign_In.md · F11_Source_Connect_Jira.md
2026-04-23 | Thursday | 8:35 PM – 8:35 PM | 0.5 | 1 | Design & Specifications | STITCH_DRIFT_AUDIT.md
2026-04-22 | Wednesday | 10:25 PM – 10:26 PM | 0.5 | 3 | Milestone Planning | Milestone_M5_Automation_Basic_Reports_MVP_Launch.md · Milestone_M3_Test_Cases_AI.md · Milestone_M3_Test_Cases_AI.md
2026-04-22 | Wednesday | 10:27 PM – 10:27 PM | 0.5 | 2 | Design & Specifications | ERD.drawio · ERD.drawio
2026-04-22 | Wednesday | 8:16 PM – 8:16 PM | 0.5 | 2 | Design & Specifications | generate_prd_docx.py · generate_prd_docx.py
2026-04-21 | Tuesday | 11:06 AM – 11:06 AM | 0.5 | 14 | Design & Specifications | goal_target_bar.png · goal_target_bar.png · priority_matrix.png
2026-04-21 | Tuesday | 12:04 AM – 12:27 AM | 0.62 | 14 | Design & Specifications | DESIGN.md · UI_PROMPT.md · PRD.drawio
2026-04-21 | Tuesday | 12:35 AM – 1:10 AM | 0.82 | 76 | Milestone Planning | gantt.png · gantt.png · risk_heatmap.png
2026-04-20 | Monday | 10:28 PM – 10:28 PM | 0.5 | 1 | Idea Confirmation | QA_Nexus_Brainstorm.md
2026-04-20 | Monday | 8:21 PM – 8:21 PM | 0.5 | 1 | Test Case Management Research | brainstorm.md
2026-04-20 | Monday | 9:22 PM – 9:22 PM | 0.5 | 1 | Design & Specifications | wireframe.html
2026-04-18 | Saturday | 11:47 AM – 12:10 PM | 0.63 | 12 | Test Case Management Research | 01_Test_Management_and_Optimization.md · 02_Test_Reporting_and_Analytics.md · 03_Automation_Playwright.md
2026-04-18 | Saturday | 7:37 PM – 7:54 PM | 0.53 | 8 | Test Case Management Research | COMPETITOR_UI_RESEARCH.md · CONTEXTQA_ANALYSIS.md · DESIGN_INSPIRATION.md
2026-04-18 | Saturday | 9:31 AM – 10:36 AM | 1.33 | 15 | Test Automation & Reporting | BrowserStack AI Agents Research & Documentation
2026-04-17 | Friday | 8:22 PM – 11:30 PM | 3.37 | 14 | Idea Confirmation | QA_Roles_Documents_Reference_Guide.md · QA_Nexus_Platform_Vision.md · problem-landscape.drawio
2026-05-06 | Wednesday | 10:00 AM – 4:39 PM | 6.65 | 30 | Milestone Planning | Day-11 M2 cascade + xlsx swap + Rule 14 | MAIN session: skill audit PR #50, ctx-discipline #54, compound-learnings backfill #56, professional xlsx swap with 26-row backfill #59, Hard Rule 14 codified #64, EOD MAIN section #65. Cascade through 75min GHA outage 13:30-14:45 IST. 13+ PRs auto-merged across MAIN/BE+1/FE+1.
2026-05-06 | Wednesday | 11:30 AM – 5:45 PM | 6.25 | 10 | Development | M2 TASK 1 F12 KB Upload + AdminShell fix | FE+1 session: F12 KB Upload Modal Pattern A scaffold (PR #52, merged 12:13 IST), AdminShell wrap fix on F12+F13 (PR #63, post visual-gate catch), Day-11 EOD + compound-learnings + sessions-stream init (PR #55). Idle Thu morning until BE /api/kb/upload-init lands.
2026-05-06 | Wednesday | 11:30 AM – 3:30 PM | 4 | 25 | Development | M2 deploy + chunk-search + RAG pipeline | BE+1 session: M2 staging deploy artifacts + ADR-011 (PR #51 rebased to 577e975), chunk-search real pgvector flip (PR #53), KB RAG /api/kb/answer + ADR-012 (PR #57). 14 new tests, 325/325 BE suite. Compound-learning: citation marker = chunk header (no drift).
2026-05-07 | Thursday | 06:50 AM – 5:00 PM | 10.2 | 18 | Milestone Planning | Day-12 / M2 Close Ceremony — 2-day vs 4-day plan | M2 closed 2 days ahead of plan (2x cadence). 16 PRs merged today across MAIN orchestration: morning Hard Rule 14 retrofit audit (#68), sessions-stream correlation hook (#76), Day-11 backfill (#67); afternoon BE/FE M2 cascade: prettier-write fix (#79) unblocking #77 #78; #78 BE M2 KB doc-create endpoint closes (al) blocker; #69 AdminShell v2 + #71 F13 flip + #80 F12 flip + #72 F15 flip merged in 16-min burst at 15:36-15:52 IST once visual-gate flags dropped; ceremony at 16:00-16:38 IST: close-gate sweep 69/69 ✅, audit chain env-skip documented, close report drafted (#81), tag m2-closed-2026-05-07 pushed at commit 498f206, EOD report drafted (#82). Carry-overs: (am) Rule 14 retrofit on F08+F09, (ae) embedding-spec direction call, Render staging Yogesh action, (ap) playwright cold-install cache.
2026-05-13 | Wednesday | 10:00 AM – 10:30 PM | 12.5 | 28 | Development | Day-17 M3 close ceremony + 4-PR auth saga + M3 close PR | M3 OFFICIALLY CLOSED at 22:55 IST. 13 PRs merged today (#129 #130 #131 #132 #133 #134 #137 #138 #139 #135 #136 #141 #142). 9-PR BetterAuth fix chain finally complete (Day-15 5-PR + Day-17 4-PR saga: #137 Gmail prefetch intermediate confirm page, #138 zod scoped override for @better-auth/core + 4-layer proof, #139 drop /auth/ prefix in sendMagicLink URL, plus BetterAuth >=1.6.11 hardcoded single-use atomic consumption discovery). Magic-link end-to-end confirmed green by Yogesh through Gmail at 21:00 IST. F19 Run Console + AdminShell canonical realignment landed. CLAUDE.md amended with Hard Rule 14 (AdminShell F19-canonical) + Hard Rule 16 NEW (canonical-first port workflow 8 steps). 12 close-ceremony artifacts shipped in PR #141 + PR #142 (M2+M3 retro). Tag m3-closed-2026-05-13 anchored at SHA a98797b (#139 — auth-chain-complete commit). 52 PRs across M3 sprint (6 calendar days / ~3.6 working days).
GRAND TOTAL

## Phase Comparison
Phase Comparison — Hours, Sessions & Days
Formula-backed phase summary · Sorted by Total Hours descending
Rank | Phase | Sessions | Active Days | Total Hours | Avg Hrs/Session | Avg Hrs/Day | % of Project | Phase | Hours
1 | Design & Specifications | 22 | 8 | 17.89 |  |  |  | Design & Specifications | 17.89
2 | Milestone Planning | 14 | 9 | 16.74 |  |  |  | Milestone Planning | 16.74
3 | Development | 9 | 4 | 13.84 |  |  |  | Development | 13.84
4 | Idea Confirmation | 2 | 2 | 3.87 |  |  |  | Idea Confirmation | 3.87
5 | Other | 4 | 3 | 2.65 |  |  |  | Other | 2.65
6 | Test Automation & Reporting | 2 | 2 | 2.01 |  |  |  | Test Automation & Reporting | 2.01
7 | Test Case Management Research | 3 | 2 | 1.66 |  |  |  | Test Case Management Research | 1.66
8 | Launch Creative | 1 | 1 | 1.23 |  |  |  | Launch Creative | 1.23
TOTAL

## Daily Rollup
Daily Rollup — Hours per Day (Latest First)
Per-day totals sorted descending by date · Formula-backed from session evidence
Date | Day | Total Hours | Sessions | Phases Touched | Date | Hours
2026-05-05 | Tuesday | 3 | 1 | Milestone Planning | 2026-04-17 | 3.37
2026-05-03 |  | 7 | 1 | Milestone Planning | 2026-04-18 | 2.49
2026-04-27 | Monday | 10.04 | 8 | Design & Specifications · Development · Milestone Planning · Other · Test Automation & Reporting | 2026-04-20 | 1.5
2026-04-26 | Sunday | 9.36 | 9 | Design & Specifications · Development · Launch Creative · Milestone Planning | 2026-04-21 | 1.94
2026-04-25 | Saturday | 6.89 | 6 | Design & Specifications · Milestone Planning | 2026-04-22 | 1.5
2026-04-24 | Friday | 5.99 | 9 | Design & Specifications · Development · Milestone Planning · Other | 2026-04-23 | 6.81
2026-04-23 | Thursday | 6.81 | 10 | Design & Specifications · Development · Milestone Planning · Other | 2026-04-24 | 5.99
2026-04-22 | Wednesday | 1.5 | 3 | Design & Specifications · Milestone Planning | 2026-04-25 | 6.89
2026-04-21 | Tuesday | 1.94 | 3 | Design & Specifications · Milestone Planning | 2026-04-26 | 9.36
2026-04-20 | Monday | 1.5 | 3 | Design & Specifications · Idea Confirmation · Test Case Management Research | 2026-04-27 | 10.04
2026-04-18 | Saturday | 2.49 | 3 | Test Automation & Reporting · Test Case Management Research | 2026-05-03 | 7
2026-04-17 | Friday | 3.37 | 1 | Idea Confirmation | 2026-05-05 | 3
TOTAL

## Token Sessions
Token Sessions — Per-Session Telemetry (Latest First)
Memory-injection and context-preload token savings tracking · Sorted descending by date
Date | Day-N | Worktree | Started | Ended | Duration (min) | Tool Calls | Tokens In | Tokens Out | Cache Read | Tokens Saved | Cost USD | In:Out Ratio | Branch | Commits | Source
2026-05-05 | 9 | MAIN | 04:54 | 13:09 | 495 | 575 | 2222620 | 266865 | 41803760 | 209350 | 24.8784 | 0 | docs/m1-lessons-learned | 16 | conversation
2026-05-04 | 8 | MAIN | 11:27 | 12:27 | 60 | 605 | 57919271 | 5050863 | 2050437403 | 220050 | 908.0778 | 0 | main | 12 | conversation
2026-05-04 | 8 | MAIN | 11:44 | 12:44 | 60 | 646 | 16906939 | 2050459 | 1102221244 | 235100 | 424.8218 | 0 | main | 12 | conversation
2026-05-04 | 8 | MAIN | 12:33 | 13:33 | 60 | 656 | 29354349 | 2836353 | 1049822514 | 238400 | 467.5679 | 0 | main | 13 | conversation
2026-04-28 | 2 | MAIN | 04:30 | 06:40 | 130 | 85 | 170000 | 42500 | 0 | 57400 | 1.1475 | 4 | main | 5 | heuristic
2026-04-28 | 2 | MAIN | 08:20 | 09:35 | 75 | 53 | 106000 | 26500 | 0 | 18850 | 0.7155 | 4 | main | 3 | heuristic
2026-04-28 | 2 | MAIN | 13:35 | 15:30 | 115 | 75 | 150000 | 37500 | 0 | 26800 | 1.0125 | 4 | main | 4 | heuristic
2026-04-27 | 1 | MAIN | 06:00 | 17:00 | 660 | 120 | 240000 | 60000 | 0 | 6450 | 1.62 | 4 | main | 17 | heuristic
2026-04-26 | 0 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-26 | 0 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-26 | 0 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-27 | 1 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-27 | 1 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-28 | 2 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-28 | 2 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-29 | 3 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-29 | 3 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-29 | 3 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-30 | 4 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-30 | 4 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-30 | 4 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-01 | 5 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-01 | 5 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-01 | 5 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-02 | 6 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-02 | 6 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-02 | 6 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-03 | 7 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-03 | 7 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-03 | 7 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-05 | 9 | MAIN | 04:54 | 13:57 | 543 | 577 | 4913355 | 425912 | 120295112 | 209850 | 60.9014 | 0 | docs/m1-lessons-learned | 16 | conversation
TOTAL

## Token Daily Rollup
Token Daily Rollup — Per-Date Totals (Latest First)
Aggregated token telemetry by date · Formula-backed from Token Sessions sheet
Date | Day-N | Total Sessions | Total Hours | Total Tool Calls | Total Tokens In | Total Tokens Out | Total Tokens Saved | Total Cost USD | Avg Saved/Session
2026-05-05 | 9 | 1 | 8.25 | 575 | 2222620 | 266865 | 209350 | 24.8784
2026-05-04 | 8 | 3 | 3 | 1907 | 104180559 | 9937675 | 693550 | 1800.4675
2026-04-28 | 2 | 3 | 5.3333 | 213 | 426000 | 106500 | 103050 | 2.8755
2026-04-27 | 1 | 1 | 11 | 120 | 240000 | 60000 | 6450 | 1.62
TOTAL

## Token Comparison
Token Comparison — Worktree-Level Rollup
Aggregated token metrics by worktree · Formula-backed from Token Sessions
Worktree | Sessions | Hours | Tokens In | Tokens Out | Tokens Saved | Cost USD | Saved / Hour | In:Out Ratio
MAIN | 8 | 27.5833 | 107069179 | 10371040 | 1012400 | 1829.8414
GRAND TOTAL

## Consolidated Report
QA Nexus PM1 — Consolidated Management Report
Effort evidence, delivery progress, and token-management ROI · Yogesh Mohite · 2026-04-17 to 2026-05-05
1. Executive Summary
Built an AI-native QA management platform for Iksula's 8-person QA team — from blank-page idea to a working code base in 19 days. Validated the vision with market research and competitor analysis, locked the product spec (PRD v6), data model (ERD), and 18-milestone roadmap (PM1 MVP → v2 GA), designed 41 production-quality UI frames, then shipped development: 21-table Prisma schema with row-level security and pgvector indexes, F07 Founder Onboarding 3-step wizard, full CI/CD pipeline, and multiple PRs merged — all on $0/month free-tier infra. Token-management telemetry tracks 1M+ tokens saved through memory-injection and context-preload techniques.
2. Management KPIs
Metric | Value | Formula Source | Management Meaning
Total Hours |  | All Sessions | Verifiable work effort available as management proof
Work Sessions |  | All Sessions | Count of evidence rows supporting the effort story
Active Days |  | Daily Rollup | Number of distinct days with logged development evidence
Tokens Saved |  | Token Comparison | Estimated savings from memory-management and context preload
Est. Token Cost (USD) |  | Token Comparison | Estimated model-token cost; separate from $0 infra posture
Infra Cost | $0.00 | Cover | All components run on confirmed free-tier hosting
3. Hours by Phase
Phase | Sessions | Hours | % of Total
TOTAL
4. Key Deliverables
Strategy & Research | Vision, market research, competitor UI review, problem framing, and QA domain research.
Specifications & Design | PRD/ERD evolution, 41-frame PM1 design system, UI tokens, and navigation contracts.
Roadmap & Milestones | M0-M18 milestone planning, PM4 initiative charters, registry, close reports, and delivery gates.
Development | Frontend/backend implementation, CI/CD gates, RBAC sweep, onboarding flows, fixes, and release artifacts.
Token Management | Memory-injection/context-preload savings tracking, daily token rollups, and explicit data-quality notes.
5. Cost Posture
Every infrastructure component runs on free-tier hosting confirmed at $0/month: Cloudflare Pages (frontend, unlimited bandwidth) + Render Hobby (NestJS API, 750 hr/mo) + Neon Postgres (0.5 GB, currently ~2% used) + Cloudflare R2 (10 GB storage) + Resend (3,000 emails/mo) + Groq API (1k RPD primary + 14.4k RPD fast) + Grafana Cloud (observability) + Better Stack (alerting) + UptimeRobot (keep-alive). Total monthly spend confirmed: $0.00.
6. Milestone Progress
M0 Setup (target 2026-05-10): Completed with 102 commits, 17 PASS / 0 FAIL / 2 DEFERRED to M1.5. Day 0-1 closed P0 critical-path work — schema, F06 Sign In, F07 Onboarding, hooks, CI. M1 (closed 2026-05-05): RBAC sweep 54/54 pass, 47 PRs merged, 358 tests, 21/41 frames complete. Currently on track for M2 delivery.

## Idea Confirmation
Idea Confirmation — Session Evidence
Phase 1 — vision, market research, problem statement, solution design, mockups, competitive analysis, flow diagrams.
Date | Day | Timing | Hours | Files | Evidence / Theme | What I Did
2026-04-20 | Monday | 10:28 PM – 10:28 PM | 0.5 | 1 | QA_Nexus_Brainstorm.md
2026-04-17 | Friday | 8:22 PM – 11:30 PM | 3.37 | 14 | QA_Roles_Documents_Reference_Guide.md · QA_Nexus_Platform_Vision.md · problem-landscape.drawio
GRAND TOTAL

## Test Case Management Research
Test Case Management Research — Session Evidence
Phase 2 — test management & optimization, test reporting & analytics, automation/Playwright research, brainstorm, UI/UX design doc.
Date | Day | Timing | Hours | Files | Evidence / Theme | What I Did
2026-04-20 | Monday | 8:21 PM – 8:21 PM | 0.5 | 1 | brainstorm.md
2026-04-18 | Saturday | 11:47 AM – 12:10 PM | 0.63 | 12 | 01_Test_Management_and_Optimization.md · 02_Test_Reporting_and_Analytics.md · 03_Automation_Playwright.md
2026-04-18 | Saturday | 7:37 PM – 7:54 PM | 0.53 | 8 | COMPETITOR_UI_RESEARCH.md · CONTEXTQA_ANALYSIS.md · DESIGN_INSPIRATION.md
GRAND TOTAL

## Test Automation & Reporting
Test Automation & Reporting — Session Evidence
Phase 3 — BrowserStack AI Agents research + masterclass video transcription + Word doc finalisation.
Date | Day | Timing | Hours | Files | Evidence / Theme | What I Did
2026-04-27 | Monday | 9:44 PM – 10:10 PM | 0.68 | 3 | BrowserStack AI Agents — Document Finalisation
2026-04-18 | Saturday | 9:31 AM – 10:36 AM | 1.33 | 15 | BrowserStack AI Agents Research & Documentation
GRAND TOTAL

## Design & Specifications
Design & Specifications — Session Evidence
Phase 4 — PRD V4-V6 (Blueprint Forge), ERD (full data model), 41 PM1 UI v2 locked HTML frames, master brainstorm, project analysis, tech stack research.
Date | Day | Timing | Hours | Files | Evidence / Theme | What I Did
2026-04-27 | Monday | 10:35 AM – 10:49 AM | 0.5 | 153 | QA_Nexus_Tech_Stack.docx · ERD.docx · ERD.drawio
2026-04-26 | Sunday | 2:40 PM – 2:42 PM | 0.5 | 4 | PRD.md · PRD.md · ERD.md
2026-04-26 | Sunday | 3:57 PM – 3:58 PM | 0.5 | 2 | PM1_ERD.md · PM1_ERD.md
2026-04-26 | Sunday | 8:43 PM – 8:44 PM | 0.5 | 5 | PM1_PRD.md · CLAUDE_KICKOFF_PROMPT.md · 01_SYSTEM.md
2026-04-25 | Saturday | 8:26 AM – 8:26 AM | 0.5 | 2 | F14m3 Convert to Jira Story Modal.html · F14m3 Convert to Jira Story Modal.html
2026-04-25 | Saturday | 9:21 PM – 10:43 PM | 1.62 | 20 | QA_Nexus_Master_Brainstorm.md · QA_Nexus_Master_Brainstorm.md · project_analysis.md
2026-04-25 | Saturday | 9:41 AM – 12:43 PM | 3.27 | 26 | F15 Knowledge Base.html · F15 Knowledge Base.html · F16a Test Case Method Chooser.html
2026-04-24 | Friday | 11:11 PM – 12:12 AM | 1.27 | 16 | F06b Set Reset Password.html · F06b Set Reset Password.html · F06c Reset Password.html
2026-04-24 | Friday | 11:51 AM – 12:28 PM | 0.87 | 16 | 01-home.html · 02-test-cases.html · 03-ai-generator.html
2026-04-24 | Friday | 6:05 PM – 6:23 PM | 0.55 | 36 | F07 First-Run Onboarding.html · F07 First-Run Onboarding.html · F06 Sign In.html
2026-04-24 | Friday | 7:54 PM – 8:27 PM | 0.8 | 4 | 05_ANALYSE_AND_GOVERN.md · 05_ANALYSE_AND_GOVERN.md · 02_ENTRY_AND_HOME.md
2026-04-24 | Friday | 9:51 PM – 9:51 PM | 0.5 | 2 | PROJECT_UI_DESIGN_TOKENS.json · PROJECT_UI_DESIGN_TOKENS.json
2026-04-23 | Thursday | 10:30 AM – 10:30 AM | 0.5 | 1 | MVP_PRD.md
2026-04-23 | Thursday | 11:58 AM – 1:33 PM | 1.82 | 7 | PROJECT_UI_UX_REDESIGN.md · PROJECT_UI_FRAME_MAP.md · PROJECT_UI_GENERATION_PROMPT.md
2026-04-23 | Thursday | 2:54 PM – 2:54 PM | 0.5 | 53 | code.html · screen.png · code.html
2026-04-23 | Thursday | 5:59 PM – 6:18 PM | 0.57 | 29 | NAVIGATION_CONTRACT.md · F06_Sign_In.md · F11_Source_Connect_Jira.md
2026-04-23 | Thursday | 8:35 PM – 8:35 PM | 0.5 | 1 | STITCH_DRIFT_AUDIT.md
2026-04-22 | Wednesday | 10:27 PM – 10:27 PM | 0.5 | 2 | ERD.drawio · ERD.drawio
2026-04-22 | Wednesday | 8:16 PM – 8:16 PM | 0.5 | 2 | generate_prd_docx.py · generate_prd_docx.py
2026-04-21 | Tuesday | 11:06 AM – 11:06 AM | 0.5 | 14 | goal_target_bar.png · goal_target_bar.png · priority_matrix.png
2026-04-21 | Tuesday | 12:04 AM – 12:27 AM | 0.62 | 14 | DESIGN.md · UI_PROMPT.md · PRD.drawio
2026-04-20 | Monday | 9:22 PM – 9:22 PM | 0.5 | 1 | wireframe.html
GRAND TOTAL

## Milestone Planning
Milestone Planning — Session Evidence
Phase 5 — M0-M18 milestone decomposition, MILESTONE_REGISTRY, PM4 initiative charters, sync reports, audit remediation waves.
Date | Day | Timing | Hours | Files | Evidence / Theme | What I Did
2026-05-05 | Tuesday | 10:00 AM – 1:00 PM | 3 | 8 | M1 close ceremony | M1 close ceremony — Day 9+10 combined. RBAC sweep 54/54 pass. Audit chain env-skip (no local DATABASE_URL). Filed m1-close-report.md (47 PRs, 358 tests, 21/41 frames, $0/month). Pushed tag m1-closed-2026-05-05. Posted m1-closed-announcement. Wrote Day-9+10-combined EOD report. PR #48 fix(web): f27 /admin/users 404 — users-api.ts relative URL fixed to NEXT_PUBLIC_API_BASE_URL (BE wiring was correct; FE bug). Bonus: better-auth pnpm hoist applied.
2026-05-03 |  |  | 7 | 80 | M0 close ceremony | M0 close ceremony — Steps A-I + Step E. PRs #21+#22+#23+#24 squash-merged; PR #25 (FE M2) opened as Draft. Followups (t) closed via PR #24, (u)+(v) filed. CLAUDE.md Hard Rule #3 updated for 3-folder frame inventory post Claude Design v2 supersede. M0 completion report at docs/milestones/M0_completion_report.md. 4th halt-to-root-cause pattern codified (refined pre-merge gate: compare PR vs main, only NEW failures gate). 102 commits over M0 window, 17 PASS / 0 FAIL / 2 DEFERRED to M1.5. Final main HEAD 44b06ef.
2026-04-27 | Monday | 10:47 AM – 10:49 AM | 0.5 | 248 | AUDIT_REMEDIATION_WAVE_3_REPORT.md · FINAL_REVIEW.md · FINAL_REVIEW_MVP_ARCHIVE.md
2026-04-26 | Sunday | 3:45 PM – 3:45 PM | 0.5 | 1 | Milestone_M0_Setup_v8.md
2026-04-26 | Sunday | 5:52 PM – 5:53 PM | 0.5 | 2 | Milestone_M5_Automation_Basic_Reports_MVP_Launch.md · Milestone_M5_Automation_Basic_Reports_MVP_Launch.md
2026-04-26 | Sunday | 8:54 PM – 8:54 PM | 0.5 | 1 | Milestone_M0_Setup_v8.md
2026-04-25 | Saturday | 11:00 PM – 11:02 PM | 0.5 | 23 | Milestone_M1_Users_Roles.md · Milestone_M1_Users_Roles.md · Milestone_M2_Docs_KB.md
2026-04-25 | Saturday | 7:09 PM – 7:09 PM | 0.5 | 72 | gantt.png · gantt.png · risk_heatmap.png
2026-04-25 | Saturday | 9:22 PM – 9:32 PM | 0.5 | 6 | Milestone_M0_Setup.md · Milestone_M0_Setup.md · Milestone_M0_Setup.md
2026-04-24 | Friday | 3:41 PM – 3:41 PM | 0.5 | 2 | Milestone_M17_Enterprise_Auth_Slack.md · Milestone_M17_Enterprise_Auth_Slack.md
2026-04-24 | Friday | 7:40 PM – 7:40 PM | 0.5 | 2 | MILESTONE_REGISTRY.md · MILESTONE_REGISTRY.md
2026-04-23 | Thursday | 12:11 PM – 12:51 PM | 0.92 | 60 | SYNC_REPORT_MVP_ARCHIVE.md · SYNC_REPORT_MVP_ARCHIVE.md · Milestone_M10_AI_Product_Tester.md
2026-04-22 | Wednesday | 10:25 PM – 10:26 PM | 0.5 | 3 | Milestone_M5_Automation_Basic_Reports_MVP_Launch.md · Milestone_M3_Test_Cases_AI.md · Milestone_M3_Test_Cases_AI.md
2026-04-21 | Tuesday | 12:35 AM – 1:10 AM | 0.82 | 76 | gantt.png · gantt.png · risk_heatmap.png
2026-05-06 | Wednesday | 10:00 AM – 4:39 PM | 6.65 | 30 | Day-11 M2 cascade + xlsx swap + Rule 14 | MAIN session: skill audit PR #50, ctx-discipline #54, compound-learnings backfill #56, professional xlsx swap with 26-row backfill #59, Hard Rule 14 codified #64, EOD MAIN section #65. Cascade through 75min GHA outage 13:30-14:45 IST. 13+ PRs auto-merged across MAIN/BE+1/FE+1.
2026-05-07 | Thursday | 06:50 AM – 5:00 PM | 10.2 | 18 | Day-12 / M2 Close Ceremony — 2-day vs 4-day plan | M2 closed 2 days ahead of plan (2x cadence). 16 PRs merged today across MAIN orchestration: morning Hard Rule 14 retrofit audit (#68), sessions-stream correlation hook (#76), Day-11 backfill (#67); afternoon BE/FE M2 cascade: prettier-write fix (#79) unblocking #77 #78; #78 BE M2 KB doc-create endpoint closes (al) blocker; #69 AdminShell v2 + #71 F13 flip + #80 F12 flip + #72 F15 flip merged in 16-min burst at 15:36-15:52 IST once visual-gate flags dropped; ceremony at 16:00-16:38 IST: close-gate sweep 69/69 ✅, audit chain env-skip documented, close report drafted (#81), tag m2-closed-2026-05-07 pushed at commit 498f206, EOD report drafted (#82). Carry-overs: (am) Rule 14 retrofit on F08+F09, (ae) embedding-spec direction call, Render staging Yogesh action, (ap) playwright cold-install cache.
GRAND TOTAL

## Launch Creative
Launch Creative — Session Evidence
Phase 6 — animated stack visualisation (3 versions), LinkedIn poster PNG + PDF, MP4 launch video, launch post copy.
Date | Day | Timing | Hours | Files | Evidence / Theme | What I Did
2026-04-26 | Sunday | 1:17 PM – 2:17 PM | 1.23 | 9 | qa-nexus-stack-diagram.svg · qa-nexus-stack-animated.html · qa-nexus-stack-logos.svg
GRAND TOTAL

## Development
Development — Session Evidence
Phase 7 — Day-0 dev infra (Cloudflare, GitHub, hooks, kickoff doc) + Day-1+ code (Prisma schema, F07 wizard, Neon, PRs merged, RBAC sweep).
Date | Day | Timing | Hours | Files | Evidence / Theme | What I Did
2026-04-27 | Monday | 10:04 AM – 11:31 AM | 1.68 | 234 | memory.md · api.md · database.md
2026-04-27 | Monday | 1:19 PM – 1:19 PM | 0.5 | 16 | audit-log.sh · report-token-savings.sh · check-secrets.sh
2026-04-27 | Monday | 2:25 PM – 4:12 PM | 2.03 | 49 | token-savings.jsonl · block-dangerous.sh · .gitleaks.toml
2026-04-27 | Monday | 5:58 PM – 8:44 PM | 3 | 143 | settings.local.json · deploy-check.md · sync-worktree.md
2026-04-26 | Sunday | 2:29 PM – 2:29 PM | 0.5 | 574 | e9502cdb · 3a4bb885 · 3147a1e3
2026-04-26 | Sunday | 5:56 PM – 10:20 PM | 4.63 | 126 | .editorconfig · .prettierrc.json · .nvmrc
2026-04-24 | Friday | 10:46 PM – 10:46 PM | 0.5 | 1 | settings.local.json
2026-04-23 | Thursday | 11:03 AM – 11:03 AM | 0.5 | 1 | PROJECT_DOCUMENT_AUDIT_REPORT.md
2026-04-23 | Thursday | 12:06 PM – 12:06 PM | 0.5 | 1 | PROJECT_ROADMAP.md
2026-04-28 |  |  | 8 | 50 | Skill features push (89%→96% conformance) | MAIN solo, 5-block skill-features push. See docs/eod-reports/2026-04-28-day-2.md.
2026-04-29 | Wednesday | 10 AM – 6 PM IST (PLACEHOLDER — refine per actual sessions) | 8 | 60 | Deploy prep-pack + R2 service + ADRs + T031 e2e + T018 weekly backup | 5-phase day: 4 runbooks (render/r2/uptimerobot/resend) + R2 service code (14 jest tests) + Playwright e2e scaffold + weekly Postgres backup workflow + restore runbook. ADR-004 + ADR-005. See docs/eod-reports/2026-04-29-day-3.md.
2026-04-30 | Thursday | 10 AM – 7 PM IST (PLACEHOLDER — refine per actual sessions) | 9 | 80 | 5 BE hotfixes + 2 PRs merged + 6 dashboard services provisioned | Day-4 boot regression chain (NestOtelLogger -> Graceful -> pnpm dup-key -> sharp 0.33 -> bge-small swap). PR #17 (F09+F10 seed-cent) + PR #19 (F12+F13 uploads). All 6 dashboard services live. ADR-009 + ADR-003 amendment. Followups (i)+(j) closed, (k) dropped, (l)+(m) filed. See docs/eod-reports/2026-04-30-day-4.md.
2026-05-06 | Wednesday | 11:30 AM – 5:45 PM | 6.25 | 10 | M2 TASK 1 F12 KB Upload + AdminShell fix | FE+1 session: F12 KB Upload Modal Pattern A scaffold (PR #52, merged 12:13 IST), AdminShell wrap fix on F12+F13 (PR #63, post visual-gate catch), Day-11 EOD + compound-learnings + sessions-stream init (PR #55). Idle Thu morning until BE /api/kb/upload-init lands.
2026-05-06 | Wednesday | 11:30 AM – 3:30 PM | 4 | 25 | M2 deploy + chunk-search + RAG pipeline | BE+1 session: M2 staging deploy artifacts + ADR-011 (PR #51 rebased to 577e975), chunk-search real pgvector flip (PR #53), KB RAG /api/kb/answer + ADR-012 (PR #57). 14 new tests, 325/325 BE suite. Compound-learning: citation marker = chunk header (no drift).
2026-05-13 | Wednesday | 10:00 AM – 10:30 PM | 12.5 | 28 | Day-17 M3 close ceremony + 4-PR auth saga + M3 close PR | M3 OFFICIALLY CLOSED at 22:55 IST. 13 PRs merged today (#129 #130 #131 #132 #133 #134 #137 #138 #139 #135 #136 #141 #142). 9-PR BetterAuth fix chain finally complete (Day-15 5-PR + Day-17 4-PR saga: #137 Gmail prefetch intermediate confirm page, #138 zod scoped override for @better-auth/core + 4-layer proof, #139 drop /auth/ prefix in sendMagicLink URL, plus BetterAuth >=1.6.11 hardcoded single-use atomic consumption discovery). Magic-link end-to-end confirmed green by Yogesh through Gmail at 21:00 IST. F19 Run Console + AdminShell canonical realignment landed. CLAUDE.md amended with Hard Rule 14 (AdminShell F19-canonical) + Hard Rule 16 NEW (canonical-first port workflow 8 steps). 12 close-ceremony artifacts shipped in PR #141 + PR #142 (M2+M3 retro). Tag m3-closed-2026-05-13 anchored at SHA a98797b (#139 — auth-chain-complete commit). 52 PRs across M3 sprint (6 calendar days / ~3.6 working days).
GRAND TOTAL

## Other
Other — Session Evidence
Misc files that did not match any phase classifier — review and re-categorise if needed.
Date | Day | Timing | Hours | Files | Evidence / Theme | What I Did
2026-04-27 | Monday | 8:55 PM – 9:49 PM | 1.15 | 3 | .~lock.QA_Nexus_Work_Hours_Log.xlsx# · lu1418u8yh.tmp · lu13993vzx.tmp
2026-04-24 | Friday | 10:46 PM – 10:46 PM | 0.5 | 1 | settings.local.json
2026-04-23 | Thursday | 11:03 AM – 11:03 AM | 0.5 | 1 | PROJECT_DOCUMENT_AUDIT_REPORT.md
2026-04-23 | Thursday | 12:06 PM – 12:06 PM | 0.5 | 1 | PROJECT_ROADMAP.md
GRAND TOTAL

## Tokens — Sessions
Date | Day-N | Worktree | Started | Ended | Duration (min) | Tool Calls | Tokens In | Tokens Out | Cache Read | Tokens Saved | Cost USD | In:Out Ratio | Branch | Commits | Source
2026-04-26 | 0 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-26 | 0 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-26 | 0 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-27 | 1 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-27 | 1 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-27 | 1 | MAIN | 06:00 | 17:00 | 660 | 120 | 240000 | 60000 | 0 | 6450 | 1.62 | 4 | main | 17 | heuristic
2026-04-28 | 2 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-28 | 2 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-28 | 2 | MAIN | 04:30 | 06:40 | 130 | 85 | 170000 | 42500 | 0 | 57400 | 1.1475 | 4 | main | 5 | heuristic
2026-04-28 | 2 | MAIN | 08:20 | 09:35 | 75 | 53 | 106000 | 26500 | 0 | 18850 | 0.7155 | 4 | main | 3 | heuristic
2026-04-28 | 2 | MAIN | 13:35 | 15:30 | 115 | 75 | 150000 | 37500 | 0 | 26800 | 1.0125 | 4 | main | 4 | heuristic
2026-04-29 | 3 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-29 | 3 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-29 | 3 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-30 | 4 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-30 | 4 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-04-30 | 4 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-01 | 5 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-01 | 5 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-01 | 5 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-02 | 6 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-02 | 6 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-02 | 6 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-03 | 7 | BE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-03 | 7 | FE | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-03 | 7 | MAIN | <unknown> | <unknown> | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | <unknown>
2026-05-04 | 8 | MAIN | 11:27 | 12:27 | 60 | 605 | 57919271 | 5050863 | 2050437403 | 220050 | 908.0778 | 0 | main | 12 | conversation
2026-05-09 | 13 | MAIN | 09:04 | 10:04 | 60 | 713 | 46306825 | 4100478 | 1588281389 | 259050 | 711.6376 | 0 | main | 17 | conversation
2026-05-09 | 13 | MAIN | 09:33 | 10:33 | 60 | 753 | 10000776 | 1227563 | 488403924 | 273850 | 202.436 | 0 | main | 18 | conversation
2026-05-09 | 13 | MAIN | 09:34 | 10:34 | 60 | 756 | 45415145 | 4184424 | 2218825186 | 275400 | 898.7018 | 0.01 | main | 18 | conversation
2026-05-13 | 17 | MAIN | 16:36 | 17:36 | 60 | 718 | 32787696 | 1825184 | 1361049886 | 261100 | 558.6419 | 0 | docs/m3-retro | 15 | conversation

## Tokens — Daily Rollup
Date | Day-N | Total Sessions | Total Hours | Total Tool Calls | Total Tokens In | Total Tokens Out | Total Tokens Saved | Total Cost USD
2026-04-27 | 1 | 1 | 11 | 120 | 240000 | 60000 | 6450 | 1.62
2026-04-28 | 2 | 3 | 5.33 | 213 | 426000 | 106500 | 103050 | 2.8755
2026-05-04 | 8 | 1 | 1 | 605 | 57919271 | 5050863 | 220050 | 908.0778
2026-05-09 | 13 | 3 | 3 | 2222 | 101722746 | 9512465 | 808300 | 1812.7754
2026-05-13 | 17 | 1 | 1 | 718 | 32787696 | 1825184 | 261100 | 558.6419

## Tokens — Per-Chat Comparison
Worktree | Sessions | Hours | Tool Calls | Tokens In | Tokens Out | Tokens Saved | Cost USD | Tokens Saved/Hour | In:Out Ratio
MAIN | 9 | 21.33 | 3878 | 193095713 | 16555012 | 1398950 | 3283.9906 | 65586 | 11.66
GRAND TOTAL | 9 | 21.33 | 3878 | 193095713 | 16555012 | 1398950 | 3283.9906 | 65586 | 11.66

## Backfill_Notes
Date | Worktree | Field | Reason | Mitigation
2026-04-27 | MAIN | Tokens In/Out | Conversation file ~/.claude/projects/.../d1-main.jsonl missing or empty | Heuristic estimate (tool_calls × 2000 in / × 500 out); refine when conversation reachable
2026-04-28 | MAIN | Tokens In/Out | Conversation file ~/.claude/projects/.../d2-morni.jsonl missing or empty | Heuristic estimate (tool_calls × 2000 in / × 500 out); refine when conversation reachable
2026-04-28 | MAIN | Tokens In/Out | Conversation file ~/.claude/projects/.../d2-eveni.jsonl missing or empty | Heuristic estimate (tool_calls × 2000 in / × 500 out); refine when conversation reachable
2026-04-28 | MAIN | Tokens In/Out | Conversation file ~/.claude/projects/.../d2-stret.jsonl missing or empty | Heuristic estimate (tool_calls × 2000 in / × 500 out); refine when conversation reachable
2026-04-26 | MAIN | All token + hours fields | Stop hook didn't write a token-savings.jsonl row on 2026-04-26 (likely session cleanly closed without Stop event, OR session crossed midnight UTC) | Reconstruct hours from docs/eod-reports/2026-04-26-day-0.md; tokens unrecoverable for past sessions
2026-04-26 | FE | All token + hours fields | FE worktree Stop hook NEVER fired (audit.jsonl absent — Bug A in token-tracking-diagnostic-2026-05-04.md) | Operator self-report from FE+1 EOD summary; followup (z) to investigate hook activation Day 9 morning
2026-04-26 | BE | All token + hours fields | BE worktree Stop hook fired through 2026-04-28 then stopped (Bug B in diagnostic doc) | Operator self-report from BE+1 EOD summary; same followup (z) as FE
2026-04-27 | FE | All token + hours fields | FE worktree Stop hook NEVER fired (audit.jsonl absent — Bug A in token-tracking-diagnostic-2026-05-04.md) | Operator self-report from FE+1 EOD summary; followup (z) to investigate hook activation Day 9 morning
2026-04-27 | BE | All token + hours fields | BE worktree Stop hook fired through 2026-04-28 then stopped (Bug B in diagnostic doc) | Operator self-report from BE+1 EOD summary; same followup (z) as FE
2026-04-28 | FE | All token + hours fields | FE worktree Stop hook NEVER fired (audit.jsonl absent — Bug A in token-tracking-diagnostic-2026-05-04.md) | Operator self-report from FE+1 EOD summary; followup (z) to investigate hook activation Day 9 morning
2026-04-28 | BE | All token + hours fields | BE worktree Stop hook fired through 2026-04-28 then stopped (Bug B in diagnostic doc) | Operator self-report from BE+1 EOD summary; same followup (z) as FE
2026-04-29 | MAIN | All token + hours fields | Stop hook didn't write a token-savings.jsonl row on 2026-04-29 (likely session cleanly closed without Stop event, OR session crossed midnight UTC) | Reconstruct hours from docs/eod-reports/2026-04-29-day-3.md; tokens unrecoverable for past sessions
2026-04-29 | FE | All token + hours fields | FE worktree Stop hook NEVER fired (audit.jsonl absent — Bug A in token-tracking-diagnostic-2026-05-04.md) | Operator self-report from FE+1 EOD summary; followup (z) to investigate hook activation Day 9 morning
2026-04-29 | BE | All token + hours fields | BE worktree Stop hook fired through 2026-04-28 then stopped (Bug B in diagnostic doc) | Operator self-report from BE+1 EOD summary; same followup (z) as FE
2026-04-30 | MAIN | All token + hours fields | Stop hook didn't write a token-savings.jsonl row on 2026-04-30 (likely session cleanly closed without Stop event, OR session crossed midnight UTC) | Reconstruct hours from docs/eod-reports/2026-04-30-day-4.md; tokens unrecoverable for past sessions
2026-04-30 | FE | All token + hours fields | FE worktree Stop hook NEVER fired (audit.jsonl absent — Bug A in token-tracking-diagnostic-2026-05-04.md) | Operator self-report from FE+1 EOD summary; followup (z) to investigate hook activation Day 9 morning
2026-04-30 | BE | All token + hours fields | BE worktree Stop hook fired through 2026-04-28 then stopped (Bug B in diagnostic doc) | Operator self-report from BE+1 EOD summary; same followup (z) as FE
2026-05-01 | MAIN | All token + hours fields | Stop hook didn't write a token-savings.jsonl row on 2026-05-01 (likely session cleanly closed without Stop event, OR session crossed midnight UTC) | Reconstruct hours from docs/eod-reports/2026-05-01-day-5.md; tokens unrecoverable for past sessions
2026-05-01 | FE | All token + hours fields | FE worktree Stop hook NEVER fired (audit.jsonl absent — Bug A in token-tracking-diagnostic-2026-05-04.md) | Operator self-report from FE+1 EOD summary; followup (z) to investigate hook activation Day 9 morning
2026-05-01 | BE | All token + hours fields | BE worktree Stop hook fired through 2026-04-28 then stopped (Bug B in diagnostic doc) | Operator self-report from BE+1 EOD summary; same followup (z) as FE
2026-05-02 | MAIN | All token + hours fields | Stop hook didn't write a token-savings.jsonl row on 2026-05-02 (likely session cleanly closed without Stop event, OR session crossed midnight UTC) | Reconstruct hours from docs/eod-reports/2026-05-02-day-6.md; tokens unrecoverable for past sessions
2026-05-02 | FE | All token + hours fields | FE worktree Stop hook NEVER fired (audit.jsonl absent — Bug A in token-tracking-diagnostic-2026-05-04.md) | Operator self-report from FE+1 EOD summary; followup (z) to investigate hook activation Day 9 morning
2026-05-02 | BE | All token + hours fields | BE worktree Stop hook fired through 2026-04-28 then stopped (Bug B in diagnostic doc) | Operator self-report from BE+1 EOD summary; same followup (z) as FE
2026-05-03 | MAIN | All token + hours fields | Stop hook didn't write a token-savings.jsonl row on 2026-05-03 (likely session cleanly closed without Stop event, OR session crossed midnight UTC) | Reconstruct hours from docs/eod-reports/2026-05-03-day-7.md; tokens unrecoverable for past sessions
2026-05-03 | FE | All token + hours fields | FE worktree Stop hook NEVER fired (audit.jsonl absent — Bug A in token-tracking-diagnostic-2026-05-04.md) | Operator self-report from FE+1 EOD summary; followup (z) to investigate hook activation Day 9 morning
2026-05-03 | BE | All token + hours fields | BE worktree Stop hook fired through 2026-04-28 then stopped (Bug B in diagnostic doc) | Operator self-report from BE+1 EOD summary; same followup (z) as FE